## GF
Republic of the Philippines
BENGUET PROVINCE
La Trinidad
ANNUAL PROCUREMENT PLAN FOR CY 2021
GENERAL FUND
No. | Project No. | Account Code | Sector | Program/Project Activity | Mode of Procurement | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCES | ESTIMATED BUDGET |  |  | REMARKS | POW IN
[6 empty] | ADS/POST OF IB/REI | SUB/OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING | FUNDS | MOOE | CO | TOTAL
A. MOOE
B. CAPITAL OUTLAY
|  |  |  | TOTAL GENERAL FUND | [6 empty] | 0 | 0 | 0
PREPARED BY: | [11 empty] | APPROVED:
|  | FERDINAND P. CATORES | [10 empty] | MELCHOR D. DICLAS
|  | BAC Secretariat Chairperson | [10 empty] | Provincial Governor
RECOMMENDED BY:
SUNNY G. SACLA |  |  |  |  | BRIAN A. CAMHIT |  |  | FRANCIS N. DITAN |  |  |  | LYDIA K. TICDONEN
BAC Chairperson |  |  |  |  | BAC-Vice Chairperson |  |  | BAC Member |  |  |  | BAC Member
RICHARD ANTERO |  |  |  |  | JENNETTE MARIE G. BANGAO |  |  | JERRY BOCANOG |  |  |  | ELEAZAR B. CARIAS
BAC Member |  |  |  |  | BAC Member-Alternate |  |  | BAC Member |  |  |  | BAC Member

## LDRRMF
Republic of the Philippines
BENGUET PROVINCE
La Trinidad
ANNUAL PROCUREMENT PLAN FOR CY 2021
LOCAL DISASTER RISK REDUCTION MANAGEMENT FUND
No. | Account Code | Project Number | Program/Project Activity | Mode of | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | ESTIMATED BUDGET |  |  | REMARKS | POW IN
|  |  |  | Procure | ADS/POST | SUB/OPEN | NOTICE OF | CONTRACT | MOOE | CO | TOTAL
|  |  |  | ment | OF IB/REI | OF BIDS | AWARD | SIGNING
TOTAL LDRRMF CY 2021 | [8 empty] | 0 | 0 | 0
PREPARED BY: | [8 empty] | APPROVED:
| FERDINAND P. CATORES | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat Chairperson | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | LYDIA K. TICDONEN |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC-Vice Chairperson |  |  |  | BAC Member |  | BAC Chairperson
|  | RICHARD S. ANTERO |  | MARIE JENNETTE G. BANGAO |  |  |  | JERRY L. BOCANOG |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  | BAC Chairperson

## SEF2021
Republic of the Philippines
BENGUET PROVINCE
La Trinidad
ANNUAL PROCUREMENT PLAN FOR CY 2021
SPECIAL EDUCATIONAL FUND (SEF)
No. | Account Code | Project Number | Program/Project Activity | Mode of | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | ESTIMATED BUDGET |  |  | REMARKS | POW IN
|  |  |  | Procure | ADS/POST | SUB/OPEN | NOTICE OF | CONTRACT | MOOE | CO | TOTAL
|  |  |  | ment | OF IB/REI | OF BIDS | AWARD | SIGNING
TOTAL SEF CY 2021 | [8 empty] | 0 | 0 | 0
PREPARED BY: | [8 empty] | APPROVED:
| FERDINAND P. CATORES | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat Chairperson | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | LYDIA K. TICDONEN |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC-Vice Chairperson |  |  |  | BAC Member |  | BAC Chairperson
|  | RICHARD S. ANTERO |  | MARIE JENNETTE G. BANGAO |  |  |  | JERRY L. BOCANOG |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  | BAC Chairperson

## 20%PDF2021
Republic of the Philippines
BENGUET PROVINCE
La Trinidad
ANNUAL PROCUREMENT PLAN FOR CY 2021
20% PROVINCIAL DEVELOPMENT FUND (PDF)
No. | Account Code | Project Number | Program/Project Activity | Mode of | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | ESTIMATED BUDGET |  |  | REMARKS | Opening | POW IN | POW OUT
|  |  |  | Procure | ADS/POST | SUB/OPEN | NOTICE OF | CONTRACT | MOOE | CO | TOTAL
|  |  |  | ment | OF IB/REI | OF BIDS | AWARD | SIGNING
A. ITOGON DISTRICT HOSPITAL
1 | 1-07-03-040 | 21001 | Upgrading of hospital water system at Itogon District Hospital | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
2 | 1-07-04-990 | 21002 | Construction of Material Recovery Facility at Itogon District Hospital | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 300000 | 300000
3 | 1-07-03-050 | 21003 | Electrical Rewiring at Itogon District Hospital | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
|  |  | SUB TOTAL | [5 empty] | 0 | 2800000 | 2800000
B. PROVINCIAL ROADS
4 | 1-07-03-010 | 21004 | Improvement along Bad-ayan - Manhuyuhoy Provincial Road, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
5 | 1-07-03-010 | 21005 | Improvement along Datakan-Labueg-Camp 66 Provincial Road, Kapangan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000 | ok
6 | 1-07-03-010 | 21006 | Improvement along Buyagan-Wangal-Banengbeng Provincial Road, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000 | OK
7 | 1-07-03-010 | 21007 | Improvement along Tulodan-Sayangan Provincial Road, Atok | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000 | OK
8 | 1-07-03-010 | 21008 | Improvement along Badiwan-City Limit Provincial Road, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
9 | 1-07-03-010 | 21010 | Improvement along Suyoc-Beckel Provincial Road, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
10 | 1-07-03-010 | 21009 | Improvement along Taloy-Bayacsan Provincial Road, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000
11 | 1-07-03-010 | 21011 | Improvement of Pugo-Balangabang Provincial Road | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000 | ok
|  |  | SUB TOTAL | [5 empty] | 0 | 36000000 | 36000000
C. OIL DEPOT AND OTHER PROJECT
12 | 1-07-03-010 | 21013 | Improvement of Road at Benguet Animal Learning Site and Farm Tourism, San Pascual, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000 | k
13 | 1-07-04-990 | 21012 | Construction of Oil Depot for the Province, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 10000000 | 10000000
|  |  | SUB TOTAL | [5 empty] | 0 | 11500000 | 11500000
D. RURAL HEALTH UNIT/BARANGAY HEALTH STATIONS/COMFORT ROOM
14 | 1-07-03-990 | 21014 | Completion of Barangay Health Station, Pasbol, Sebang, Buguias | SVP | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 1000000 | 1000000
15 | 1-07-03-990 | 21015 | Improvement of Barangay Health Station (Phase II), Suyoc, Mankayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000 | ok
16 | 1-07-03-990 | 21016 | Construction of Rural Health Unit, Poblacion, Tuba (phase II) | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 4000000 | 4000000
|  |  | SUB TOTAL | [5 empty] | 0 | 6500000 | 6500000
E. WATERWORKS SYSTEM
17 | 1-07-03-990 | 21017 | Improvement of Water Works System at Bobok Proper to Kawal, Bobok Bisal, Bokod | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
18 | 1-07-03-990 | 21018 | Improvement of Dalicno Waterworks, Ampucao, Itogon | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 4000000 | 4000000 | realigned see sapp3
19 | 1-07-03-990 | 21019 | Construction of Payket Water Works System, Dalupirip, Itogon | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
20 | 1-07-03-990 | 21020 | Improvement of Lawiguen Domestic Water Works System, Dalupirip, Itogon | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000 | k
21 | 1-07-03-990 | 21021 | Construction of Soysoyan-Gusaran Water Works System, Gusaran Kabayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
22 | 1-07-03-990 | 21022 | Improvement of Bineng Water Work System, Bineng, La Trinidad | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
23 | 1-07-03-990 | 21023 | Improvement of Tokip-Lamagan-Payeo Water Works System, Bedbed, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000
24 | 1-07-03-990 | 21024 | Construction of Water Works System at Caew, Bulalacao, Mankayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 250000 | 250000
25 | 5-02-13-030 | 21025 | Rehabilitation of Colalo Main Waterworks System, Colalo, Mankayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 500000 |  | 500000 | K
26 | 1-07-03-990 | 21026 | Construction of Water Work System at Bato (Aliona Goyek WWS) Tabio, Mankayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
|  |  | SUB TOTAL | [5 empty] | 500000 | 12250000 | 12750000
F. CHILD DEVELOPMENT CENTERS
27 | 1-07-03-990 | 21027 | Improvement of Paykek Child Development/Day Care Center, Paykek, Kapangan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
28 | 1-07-03-990 | 21028 | Completion of Palpaltogan Day Care (Phase II), Paco, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
|  |  | SUB TOTAL | [5 empty] | 0 | 2500000 | 2500000
G. SCHOOL WATERWORKS SYSTEM
29 | 1-07-03-990 | 21029 | Construction of Water Works System, Lamut, Elementary School (Deepwell), Beckel, La Trinidad | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000
|  |  | SUB TOTAL | [5 empty] | 0 | 500000 | 500000
H. SCHOOL SPORTS FACILITIES (GYM)
30 | 1-07-03-990 | 21030 | Construction of Multi-Purpose Gym for Topdac Elementary School, Topdac, Atok | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
31 | 1-07-03-990 | 21031 | Construction of Multi-Purpose Gym for Abatan Elementary School, Abatan, Buguias (phase II) | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 4000000 | 4000000
32 | 1-07-03-990 | 21032 | Improvement of Multi-Purpose Gym at Alno Kadorie Elementary School, Alno, La Trinidad | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
33 | 1-07-03-990 | 21033 | Construction of Multi-Purpose Gym, Ambongdolan Elementary School, Ambongdolan, Tublay | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000
|  |  | SUB TOTAL | [5 empty] | 0 | 14000000 | 14000000
I. MULTI-PURPOSE BUILDING/GYM/EVACUATION CENTER
34 | 1-07-03-990 | 21034 | Construction of Multi-Purpose Building below Camp Lolita, Virac, Itogon | SVP | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 1000000 | 1000000
35 | 1-07-03-990 | 21035 | Construction of Barangay Multi-Purpose Building, Taba-ao, Kapangan (phase II) | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 3000000 | 3000000
36 | 1-07-03-990 | 21036 | Improvement of Municipal Evacuation Center/ Municipal Gymnasium of Tublay at Caponga, Tublay | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000
37 | 1-07-03-990 | 21037 | Construction of Multi-urpose Gym, Bagu, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000 | OK
38 | 1-07-03-990 | 21038 | Improvement of Multi-Purpose Gym, Colalo, Mankayan | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
|  |  | SUB TOTAL | [5 empty] | 0 | 12000000 | 12000000
J. FLOOD CONTROL/DRAINAGE CANAL/SLOPE PROTECTION/RETAINING WALL
39 | 1-07-03-020 | 21039 | Construction of Mayan Flood Control, Ampusongan, Bakun | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000 | withwith letter from mayor withholding the procurement of the project for more fund
40 | 1-07-03-020 | 21040 | Construction of Longboy Flood Control, Dalipey, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | OK
41 | 1-07-03-040 | 21041 | Construction of Drainage Canal, Bakong, Poblacion, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | OK
42 | 1-07-03-010 | 21042 | Construction of Beyeng Retaining Wall, Poblacion, Bakun | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
43 | 1-07-03-990 | 21043 | Construction of Slope Protection of Bana Pathway at Poblacion, Bakun | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 |  |  | Boss change it to another project
44 | 1-07-03-990 | 21044 | Construction of Open Canal Bano-oy, Baculongan Norte, Buguias | SVP | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 1000000 | 1000000
45 | 1-07-03-040 | 21045 | Construction of canal at Daycong Balasigan, Dontogan, Dalicno, Itogon | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2500000 | 2500000
46 | 1-07-03-990 | 21046 | Construction of concrete retaining wall at 1300 level, Poblacion, Itogon | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 |  |  |  |  | 2000000
47 | 1-07-04-990 | 21047 | Construction of Retaining Wall and rehabilitation of canal along Upper Mangga Turning Point, Tuding, Itogon | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 750000 | 750000
48 | 1-07-03-020 | 21048 | Construction of Flood Control at Proper Lusod, Kabayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
49 | 1-07-03-020 | 21049 | Construction of Flood Control along Lower Proper to Nanbangawan River, Tawangan, Kabayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
50 | 1-07-03-990 | 21050 | Improvement of Canal along Proper Spring, Tawangan, Kabayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
51 | 1-07-03-020 | 21051 | Construction of Ambalideng Flood Control, Poblacion, Kibungan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000 | OK
52 | 1-07-03-040 | 21052 | Construction of Drainage Canal at Central Balili, La Trinidad | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000
53 | 1-07-03-990 | 21053 | Construction of Drainage Canal (Wag-iyen Area), Betag, La Trinidad | SVP | APR 2021 | APR 2021 | APR 2021 | MAY 2021 |  | 500000 | 500000
54 | 1-07-03-040 | 21054 | Improvement of Drainage Canal, Siadto Malinias Luspian Cores Area, Poblacion, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
55 | 1-07-03-010 | 21055 | Construction of drainage canal and improvement of community road at Central Buyagan (Khayog to Ang area), Poblacion, La Trinidad | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | ok
56 | 1-07-03-020 | 21056 | Construction of Flood Control at Bolo Creek, Puguis, La Trinidad | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 1500000 | 1500000
57 | 1-07-03-040 | 21057 | Construction of Drainage Canal Along Lot. No. 3Y-42 Phase II, Block 7, Wangal , La Trinidad | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000
58 | 1-07-03-040 | 21058 | Construction of drainage canal at Lower Balili, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
59 | 1-07-03-010 | 21059 | Construction of Drainage Open Canal, Colalo, Mankayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | K
60 | 1-07-03-010 | 21060 | Improvement of Riprap along Pukitan Road, Paco, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000 | amended in sapp8
61 | 1-07-03-010 | 21061 | Construction of Slope Protection Mangga-Balayon FMR, Camp 3, Tuba | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | K
62 | 1-07-03-020 | 21062 | Continuation of Flood Control at Lower Green Valley (phase II), Camp 6, Tuba | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | K
|  |  | SUB TOTAL | [5 empty] | 0 | 31250000 | 31250000
K. LOCAL ACCESS ROAD (BARANGAY/FARM TO MARKET ROAD)
63 | 1-07-03-010 | 21063 | Improvement of Camp 30 to Catingel Farm to Market Road (Casa Section), Caliking, Atok | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
64 | 1-07-03-010 | 21064 | Construction of Concrete Pavement Along Lang-ayan Timbac, Cattubo, Atok | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
65 | 1-07-03-010 | 21065 | Improvement of Access Road to Barangay Hall of Naguey, Atok | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2500000 | 2500000
66 | 1-07-03-010 | 21066 | Improvement of Pey-as - Dam-ayan FMR, Poblacion, Atok | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
67 | 1-07-03-010 | 21067 | Construction of Concrete Pavement of Pokit FMR, Poblacion, Atok | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
68 | 1-07-03-010 | 21068 | Improvement along Baen to Cabototan FMR, Ampusongan, Bakun | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
69 | 1-07-03-010 | 21069 | Improvement of Ay-ay Kabutotan FMR, Ampusongan, Bakun | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
70 | 1-07-03-010 | 21070 | Opening of Ba-ay to Demeg FMR, Ampusongan, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000
71 | 1-07-03-010 | 21071 | Improvement of Namagtey Access Road. Ampusongan, Bakun | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
72 | 1-07-03-010 | 21072 | Improvement of Tuangan to Lanas Road, Bagu, Bakun | SVP | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 |  | 500000 | 500000 | opened jan. 21 | 2021-01-19 | 2021-01-05
73 | 1-07-03-010 | 21073 | Improvement of Yabyaboan to Copcopit Farm to Market Road, Dalipey, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | OK
74 | 1-07-03-010 | 21074 | Opening of Mankileb-Gamat Farm to Market Road, Dalipey, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
75 | 1-07-03-010 | 21075 | Improvement of Copcopit FMR, Dalipey, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
76 | 1-07-03-010 | 21076 | Improvement of Bangelelaw FMR, Dalipey, Bakun | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | CHECK IF NANGE OR BANGELELAW
77 | 1-07-03-010 | 21077 | Improvement along Mabuhay-Cagam-is FMR, Gambang, Bakun | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
78 | 1-07-03-010 | 21078 | Opening/Improvement of Bay-o FMR, Gambang, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | OK
79 | 1-07-03-010 | 21079 | Improvement of Sookan-Gambang FMR, Gambang, Bakun | BIDDING | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
80 | 1-07-03-010 | 21080 | Improvement of Bengbeng-Beyeng Farm to Market Road, Sinacbat, Bakun | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
81 | 5-02-13-030 | 21081 | Rehabilitation of Mataliktik to Dalingoan FMR, Sinacbat, Bakun | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 1200000 |  | 1200000 | with pow recheck
82 | 1-07-03-010 | 21082 | Construction of Tapogo to Galitaan FMR, Sinacbat, Bakun | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2500000 | 2500000
83 | 1-07-03-010 | 21083 | Improvement of Embasay FMR, Daclan, Bokod | SVP | APR 2021 | APR 2021 | APR 2021 | MAY 2021 |  | 1000000 | 1000000
84 | 1-07-03-010 | 21084 | Improvement of Ikip FMR, Ekip, Bokod | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
85 | 1-07-03-010 | 21085 | Construction and rerouting of Pito Barangay Road, Pito, Bokod | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
86 | 1-07-03-010 | 21086 | Improvement of Cobabeng FMR, Poblacion, Bokod | SVP | APR 2021 | APR 2021 | APR 2021 | MAY 2021 |  | 1000000 | 1000000
87 | 1-07-03-010 | 21087 | Improvement of JFMR Dangpa-Guiwe-Daldal Road, Amgaleyguey, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
88 | 1-07-03-010 | 21088 | Improvement of Saclalan,-Sacyaban, Mabmabtic Farm to Market Road, Amgaleyguey, Buguias | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000 | OK
89 | 1-07-03-010 | 21089 | Improvement of Guioeng-Taguinday FMR, Amlimay, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
90 | 1-07-03-010 | 21090 | Improvement of Akikian-Daclan FMR, Amlimay, Buguias | SVP | APR 2021 | APR 2021 | APR 2021 | MAY 2021 |  | 1000000 | 1000000
91 | 1-07-03-010 | 21091 | Improvement and Extension of Bisel-Soyoc Farm to market Road, Amlimay, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
92 | 1-07-03-010 | 21092 | Improvement of Pugo FMR, Baculongan Norte, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1000000 | 1000000
93 | 1-07-03-010 | 21093 | Improvement of Lamagan FMR Baculongan Norte, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000
94 | 1-07-03-010 | 21094 | Improvement of Pugo-Topinaw FMR, Baculongan Norte, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | K
95 | 1-07-03-010 | 21095 | Improvement of Bad-ayan-Pugo-Lam-ayan Sinto Road (Pugo Section), Baculongan Norte, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000
96 | 1-07-03-010 | 21096 | Improvement of Obanga Balintag-Deckan FMR ( Ili Section), Baculongan Sur, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000 | Clustered with project no. 21098, item no. 98
97 | 1-07-03-010 | 21097 | Improvement of Obanga Balintag-Deckan FMR-(Pua Section), Baculongan Sur, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
98 | 1-07-03-010 | 21098 | Improvement of Obanga Balintog-Deckay FMR (Panegdigon Section), Baculongan Sur, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 500000 | 500000 | Clustered with project no. 21096, item no. 96
99 | 1-07-03-010 | 21099 | Improvement of Obanga Balintag-Deckan FMR, Baculongan Sur, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000 | ok
100 | 1-07-03-010 | 21100 | Improvement of J204 Bekes-lusong FMR, Buyacaoan, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | K
101 | 1-07-03-010 | 21101 | Improvement of FMR (riprap), Antopak, Buyacaoan, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | ok
102 | 1-07-03-010 | 21102 | Improvement of Bekes Gudogodan FMR at Buyacaoan, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
103 | 1-07-03-010 | 21103 | Improvement of Nagawa-Antopak Farm to Market Road, Buyacaoan, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | ok
104 | 1-07-03-010 | 21104 | Construction of Pavement along J204 Cotcot Bolinaca Patugong Walengwaleng Farm to Market Road, Calamagan, Buguias | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
105 | 1-07-03-010 | 21105 | Improvement of Ponopon FMR, Catlubong, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
106 | 1-07-03-010 | 21106 | Improvement of Bekes-Beka FMR, Catlubong, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | K
107 | 1-07-03-010 | 21107 | Improvement of Mankil-et Lebeng FMR, Catlubong, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
108 | 1-07-03-010 | 21108 | Improvement of Modayan-Boca-eg-Kitongan Farm to Market Road, Loo, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
109 | 1-07-03-010 | 21109 | Improvement of Lanas-Pan-ayaoan FMR, Loo, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | ok
110 | 1-07-03-010 | 21110 | Improvement of Lanas Taba-ao Nataeg FMR, Loo, Buguias | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
111 | 1-07-03-010 | 21111 | Improvement of Pusel Ampetang, Legleg Section FMR, Poblacion, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
112 | 1-07-03-010 | 21112 | Improvement of Junction to Alang FMR, Poblacion, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000
113 | 1-07-03-010 | 21113 | Improvement of Inuman Palakad FMR, Poblacion, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
114 | 1-07-03-010 | 21114 | Improvement of JNSR-BTK Bot-oan-Tamangan-Paneg-an FMR (Tacadang, Section) Sebang, Buguias | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
115 | 1-07-03-010 | 21115 | Improvement of Panig-an Tammangan Section FMR, Annadong, Sebang, Buguias | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
116 | 1-07-03-010 | 21116 | Improvement and concreting of JFNR-BTK-Toking-Lingadan-Naliskey-J207 Road, Sebang, Buguias | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
117 | 1-07-03-010 | 21117 | Improvement of Potpotak to Beca FMR, Sebang, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
118 | 1-07-03-010 | 21118 | Improvement of JMFMR PNI-Pasbol Baney-Napuyasan JFMR OCDL (Lay-udan) Sebang, Buguias | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | k
119 | 1-07-03-010 | 21119 | Improvement of Batengan-Paltingan FMR, Adaoay, Kabayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000 | amended in sapp8
120 | 1-07-03-010 | 21120 | Improvement of Adaoay Proper-Pocngol-Abat FMR, Adaoay, Kabayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
121 | 1-07-03-010 | 21121 | Improvement of Dinamili to Dimipayas FMR, Ballay, Kabayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3250000 | 3250000 | OK
122 | 1-07-03-010 | 21122 | Improvement of Talabing-Liang FMR, Ballay, Kabayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | K
123 | 1-07-03-010 | 21123 | Improvement along Minac-Tuidan-Tongotong-Tabayo Ballay, Kabayan | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000 | with pow 2nd qtr
124 | 1-07-03-010 | 21124 | Improvement of Todjacap-Bekes-Balangabang -Singapayew Access Road, Duacan, Kabayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 4000000 | 4000000
125 | 1-07-03-010 | 21125 | Improvement of Wacalan to Madayag Farm to Market Road, Lusod, Kabayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 500000 | 500000 | OK
126 | 1-07-03-010 | 21126 | Improvement of Proper Lusod to Ba-ay Road, Lusod, Kabayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 5000000 | 5000000
127 | 1-07-03-010 | 21127 | Improvement of Kinubkob to Bayabay FMR, Tawangan, Kabayan | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
128 | 1-07-03-010 | 21128 | Improvement of Masala-Sagangasang - Dalumpiit Farm to Market Road Madaymen, Kibungan | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
129 | 1-07-03-010 | 21129 | Improvement / Concreting of God-ang Mancawal Farm to Market Road Access Road Lubo-Sagpat, Lubo, Kibungan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 3000000 | 3000000
130 | 5-02-13-030 | 21130 | Rehabilitation along Peril-Obudan-Capdiaran Road, Pico, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 1200000 |  | 1200000 | OK | SAPP3
131 | 1-07-03-010 | 21131 | Improvement of Road with Drainage Canal (near Alos Residence) , Western Poblacion, La Trinidad | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
132 | 1-07-03-010 | 21132 | Improvement of Kibungan Village Community Road, Puguis, La Trinidad | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000 | k
133 | 1-07-03-010 | 21133 | Improvement of Lamtang FMR, Puguis, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 1500000 | 1500000
134 | 1-07-03-010 | 21134 | Improvement of Pagal Shilan Farm to Market Road, La Trinidad | BIDDING | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 |  | 4000000 | 4000000
135 | 1-07-03-010 | 21135 | Concreting and Completion of Brgy. Road Litopan Talinguroy, Wangal, La Trinidad | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000 | pow onhand 2nd qtr |  | present
136 | 1-07-03-010 | 21136 | Improvement of Nagawaan-Tam-awan Barangay Road, Balili, Mankayan | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 500000 | 500000
137 | 1-07-03-010 | 21137 | Improvement of Buang to Maduto Farm to Market Road Cabiten, Mankayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1700000 | 1700000
138 | 5-02-13-030 | 21138 | Rehabilitation of Busan Barangay Road, Colalo, Mankayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 2000000 |  | 2000000
139 | 1-07-03-010 | 21139 | Improvement of Cabatoan FMR, Colalo, Mankayan | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1500000 | 1500000 | ok
140 | 1-07-03-010 | 21140 | Restoration and Improvement of alternate road at Sitio Palpaltogan, Paco, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
141 | 1-07-03-010 | 21141 | Improvement of Upper Sapid Barangay Road (Sese), Sapid, Mankayan | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
142 | 1-07-03-010 | 21142 | Improvement of Gravel Pit/FMR, Sapid, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
143 | 1-07-03-010 | 21143 | Improvement of Sapid Nursery to Pakda-Suyok FMR, Sapid, Mankayan | SVP | APR 2021 | APR 2021 | APR 2021 | APR 2021 |  | 1000000 | 1000000
144 | 1-07-03-010 | 21144 | Improvement of Inoman-Abbao FMR, Taneg, Mankayan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
145 | 1-07-03-010 | 21145 | Improvement and Opening of Talete Tongshol FMR, Bayabas, Sablan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 1000000 | 1000000
146 | 1-07-03-010 | 21146 | Improvement of Matal-og Kayapa FMR, Poblacion, Sablan | SVP | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 |  | 500000 | 500000
147 | 1-07-03-010 | 21147 | Improvement of Banyol-Lubas FMR, Ansagan, Tuba | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK
148 | 1-07-03-010 | 21148 | Construction of Diversion Road at Taroy Ligay Farm To Market Road (Phase II), Camp 1, Tuba | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 814000 | 814000 | ok
149 | 1-07-03-010 | 21149 | Improvement of Pula, Poblacion Road, Poblacion, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
150 | 1-07-03-010 | 21150 | Improvement of Batangal to Toybongan Barangay Road, Tabaan Norte, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
151 | 1-07-03-010 | 21151 | Improvement of Aguyad-Lebbeng Barangay Road, Tadiangan, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000 | ok
152 | 1-07-03-010 | 21152 | Improvement of Tawalan-Angdil FMR, Taloy Sur, Tuba | BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 |  | 2000000 | 2000000
153 | 1-07-03-010 | 21153 | Improvement of Kaipilan-Dalabi FMR, Twin Peaks, Tuba | SVP | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 1000000 | 1000000 | OK |  | 2021-01-08
154 | 1-07-03-010 | 21154 | Improvement of Twin Peaks-Dengsed Provincial Road, Twin Peaks Section, Tuba | BIDDING | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 |  | 2000000 | 2000000
|  |  | SUB TOTAL | [5 empty] | 4400000 | 138264000 | 142664000
TOTAL PDF CY 2021 | [8 empty] | 4900000 | 267564000 | 272464000
[9 empty] | 0 | 0 | 0
PREPARED BY: | [9 empty] | APPROVED:
| FERDINAND P. CATORES | [9 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat Chairperson | [9 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | LYDIA K. TICDONEN |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC-Vice Chairperson |  |  |  | BAC Member |  | BAC Chairperson
|  | RICHARD S. ANTERO |  | MARIE JENNETTE G. BANGAO |  |  |  | JERRY L. BOCANOG |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  | BAC Chairperson

## SAPP1
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 1
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | TOTAL | MOOE | CO
A. 20 % PROVINCIAL DEVELOP FUND (PDF)
1 | 20021 | Improvement of Les-eng Tacadang Waterworks, Tacadang, Kibungan | Kibungan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 1300000 |  | 1300000 |  | SPPMP No. 1 | 2021-02-02
2 | 20032 | Completion of Multi-Purpose Hall, Dalipey, Bakun | Bakun | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | MAR 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 1/6 | opened Feb.10, 2021 | ok
3 | 20038 | Construction of Drainage Canal from the National Highway going up to the Cruz-Tawang Road at Sitio Atta, Cruz | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 1500000 |  | 1500000 |  | SPPMP No. 1 | opened Feb.10, 2021
4 | 20040 | Construction of Drainage Canal with Cover at Lower Capjaran, KM4, Pico | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 1350000 |  | 1350000 |  | SPPMP No. 1 | 2021-02-02
5 | 20057 | Opening of Yupo-an-Penas FMR, Dalipey | Bakun | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 1500000 |  | 1500000 |  | SPPMP No. 1 | 2021-02-02
6 | 20067 | Improvement of Proper Ekip FMR | Bokod | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 4400000 |  | 4400000 | Clustered to project no.SB3 2019-08 under GF | SPPMP No. 1 | 2021-02-02
7 | 20071 | Opening of Apanan -Dondontog-Lolotab FMR, Amlimay Buguias | Buguias | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 1 | w/ pow
8 | 20102 | Concreting along Sapdaan-Amog-on FMR, Sagpat | Kibungan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1500000 |  | 1500000 |  | SPPMP No. 1 | w/ pow
9 | 20012 | Construction of Health Station, Suyoc-Palasaan, Suyoc, Mankayan (Phase I) | Mankayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 6 | new
10 | 20022 | Completion of Waterworks Project at Sitio Marlboro, Beckel, La Trinidad, Benguet | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 |  | SPPMP No. 6 | new
11 | 20030 | Contruction of Child Development Center, Proper Gaswiling, Kapangan, Benguet | Kapangan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 |  | SPPMP No. 6 |  | sapp4
12 | SB1 2019-37 | Completion of Beling-Belis Barrio School Multi-Purpose Cottage at Beling-Belis, Kapangan, Benguet (Phase II) | Kapangan | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SB NO. 1 CY 2019 - 20 % PDF | 500000 |  | 500000 |  | SPPMP No. 1 | 2021-01-19
13 | SB3 2019-3 | Improvement of Mataliktik FMR, Sinacbat, Bakun | Bakun | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | SB No. 3 PDF 2019 | 2500000 |  | 2500000 |  | SPPMP No. 6 | new
14 | 19032 | Improvement of Kayapa-Bulisay to Beyeng FMR Kayapa, Bakun, Benguet | Bakun | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2019 | 3000000 |  | 3000000 |  | SPPMP No. 6 | new
15 | 17086 | Construction of Daket-Oguban Footbridge, Eddet, Kabayan (additional) | Kabayan | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | SB NO. 1 CY 2017 - 20 % PDF | 1000000 |  | 1000000 | Clustered with item no. 60 under GF 2021 | SPPMP No. 6 | new
16 | 16396 | Completion of Palansa Public Comfort Room, Bila, Bokod, Benguet | Bokod | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2016 | 200000 |  | 200000 | -Realigned from project: Construction of Palansa Public Comfort Room, Bila, Bokod, Benguet | SPPMP No. 2 | opened Feb.10, 2021 | Budget Ordinance No. 20-12
17 | 20078 | Improvement of J204 Bekes-Dontog-Sibungan-Lusong-Magmagaling J207 access road, Buyacaoan, Buguias, Benguet | Buguias | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 | -Realigned from project: Construction of J204 Dontog-Sibungan-Lusong-Magmagaling J207 access road, Buyacaoan, Buguias, Benguet. | SPPMP No. 2 | opened Feb.10, 2021
18 | 20091 | Construction of Canal along Provincial Road (Infront of Mr. Sibayan to First Gate Checkpoint), Virac, Itogon, Benguet | Itogon | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1500000 |  | 1500000 |  | SPPMP No. 6
19 | 20109 | Improvement of Atayan-Balili Provincial Road, Balili, Mankayan, Benguet | Mankayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 10000000 |  | 10000000 |  | SPPMP No. 6
20 | 20095 | Construction of Retaining Wall along Tuidan FMR, Ballay Kabayan, Benguet | Kabayan | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 | -Realigned from project: Construction of Riprap along Tuidan, Ballay, Kabayan, Benguet | SPPMP No. 2 | no pow
21 | 20105 | Opening/Improvement of Upper Bayabas going to Pico Elementary School Access Road, Pico, La Trinidad, Benguet | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | -Realigned from project: Improvement of Upper Bayabas going to Pico Elementary School, Pico, La Trinidad, Benguet | SPPMP No. 2 | no pow
22 | 20065 | Opening of Macbas to Tenglawan FMR (Phase II) Bakun, Benguet | Bakun | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 3 | opened jan. 19
23 | 20060 | Improvement of Alam-am-Gambang FMR, Gambang, Bakun, Benguet | Bakun | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | PDF CY 2020 | 3000000 |  | 3000000 |  | SPPMP No. 3 | PREBID FEB 10, 2021
24 | 20004 | Improvement Along Sipitan -Palidan Provincial Road, Bakun, Benguet | Bakun | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | 20% PDF CY 2020 | 5000000 |  | 5000000 |  | SPPMP No. 3 | PREBID FEB 10, 2021
25 | 20095 | Construction of Retaining Wall Along Tuidan FMR, Ballay, Kabayan | Kabayan | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20 % PDF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 3 | new
26 | a. 16207 | A. Construction of Water Tank at Sitio Payacpac B. Construction of Water Tank at Sitio Payacpac | Tuba | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | a. 20% PDF 2016 b. SB #2-2016 | 200000 |  | 200000 |  | SPPMP No. 3 | new | with ppmp from ppdo | a. 20% PDF 2016 b. GF SB #2-2016
27 | 18082 | Construction of Provincial Fish Hatchery and Grow-out Pond, San Pascual, Tuba | Tuba | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2018 | 1500000 |  | 1500000 | -Realigned from project: Establishment of Fishpond, San Pascual, Tuba, Benguet. -Clustered project (No. 23 &24) | SPPMP No. 4 | pending
28 |  | Construction of Provincial Fish Hatchery and Grow-out Pond, San Pascual, Tuba | Tuba | [5 empty] | 20% PDF CY 2018 | 500000 |  | 500000
29 | 18080 | Installation of Solar Powered Irrigation System and Additional Water Supply Distribution System at Kabayan Demo Farm | Kabayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2018 | 3300000 |  | 3300000 |  | SPPMP No. 6 | REBID | SAPP3
30 | 20014 | Construction of Naubanan to Barangay Daclan Waterworks, Daclan, Bokod, Benguet | Bokod | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | -Realigned from project: Construction of Sodkong Waterworks, Daclan, Bokod, Benguet. | SPPMP No. 4 | delete/defer
31 | GF 2020-015 | Construction of Capitol Entrance Rotunda Sculpture (additional amount) La Trinidad, Benguet | La Trinidad | Small Value Procurement | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF 2015 | 370000 |  | 370000 | -Realigned from project: Improvement of Capitol Grounds. | SPPMP No. 4 | delete/defer
32 | 19003 | Construction of 3 Storey Provincial Health Services Multi-Purpose Building | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2019 | 50000000 |  | 50000000 |  | SPPMP No. 6
33 | 20033 | Construction of Multi-Purpose Stage at Keweng, Tinongdan, Itogon | Itogon | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | SUP AIP-5 CY 2020 | 2000000 |  | 2000000 | -Realigned from project: Enclosure of Multi-purpose Gym with stage at Keweng, Tinongdan, Itogon, Benguet. | SPPMP No. 4 | PREBID FEB 10, 2021
34 | 20117 | Construction of Flood Control Phase II, Bito, Bagong, Sablan, Benguet | Sablan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | -Realigned from project: Opening of Yabyabuan-Sholshol FMR, Bagong, Sablang, Benguet. | SPPMP No. 4 | no pow
35 | 20119 | Opening/Improvement of Kiangan Village to Balding FMR, Camp 3, Tuba, Benguet | Tuba | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2020 | 3000000 |  | 3000000 | -Realigned from project: Construction of Farm-Market Vehicular Bridge from Bued River to Balding, Camp 3, Tuba. | SPPMP No. 4 | delete for reversion
|  | SUB TOTAL | [7 empty] | 116120000 | 0 | 116120000
B. GENERAL FUND (GF)
36 | SB1 2019-31 | Construction of Stage at Kibungan National High School | Kibungan | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SB No. 1-2019 (GF) | 500000 |  | 500000 |  | SPPMP No. 6 | opened Feb 10, 2021
37 | SB3 2019-08 | Improvement of Farm to Market Road, Ekip, Bokod | Bokod | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF 2019 | 1000000 |  | 1000000 | Clustered to project no.20067 under PDF. |  | 2021-02-02
38 | SB3 2019-21 | Construction of Multi-purpose Gym at Upper Bashoy, Kabayan (Phase I) | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 4000000 |  | 4000000 |  | SPPMP No. 1 | 2021-02-02
39 | SB3 2019-41 | Slope Protection and Fencing at Balili National High School, Balili, Mankayan | Mankayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB NO. 3 CY 2019 | 1500000 |  | 1500000 |  | SPPMP No. 1 | 2021-02-02
40 | SB3 2019-45 | Construction of Multi-purpose Building at Banangan, Sablan, Benguet | Sablan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB NO. 3 CY 2019 | 3000000 |  | 3000000 |  | SPPMP No. 1 | 2021-02-02
41 | PGSO-2019-21001 | Construction of Sewage Treatment Plant at Capitol, Poblacion | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF-2019 (PGSO) | 8000000 |  | 8000000 |  | SPPMP No. 1 | 2021-02-02
42 | GF 20035 | Construction of Senior Citizens Multi-purpose Building, Keyang, Gadang, Kapangan | Kapangan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | MAR 2021 | GF CY 2020 | 1500000 |  | 1500000 | amended in sapp8 | SPPMP No. 1 | PREBID FEB 10, 2021
43 | GF 20040 | Improvement of PEO Building, Wangal, La Trinidad | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF CY 2020 | 6000000 |  | 6000000 |  | SPPMP No. 1 | 2021-02-02
44 | GF 2017-005 | Ground Improvement at the Front Elevation of Legislative Building (PWD Access, Landscaping & Viewdeck) Additional | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF CY 2017 | 915000 |  | 915000 | Refer to PDC Res. No. 2020-15 as to funding. Clustered project nos. GF 2017-005 and GF 2017-006 | SPPMP No. 4 | 2021-02-02
45 | GF 2017-006 | Ground Development at Front Elevation of Capitol Building II (PWD Access, Landscaping & Viewdeck) | [6 empty] | GF CY 2017 | 1500000 |  | 1500000 |  | SPPMP No. 1
46 |  | Construction of Upper Tram CDC, Ucab, Itogon, Benguet | Itogon | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | SB No. 1 GF 2017 | 1200000 | 0 | 1200000 |  |  | rebid | with ppmp from ppdo
47 | GF 2018-55 | Construction of School Building at Aduyonan Elementary School, Sitio Aduyonan, Abiagn, Atok, Benguet | Atok | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF 2018 | 1500000 |  | 1500000 | - Realigned from project: Construction of Child Development Center, Abiang, Atok, Benguet. | SPPMP No. 2 | NO POW c/o ppdo | Budget Ordinance No. 20-12
48 | GF 2018-55 | Improvement of Legislative Building,La Trinidad, Benguet | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF 2018 | 5000000 |  | 5000000 |  | SPPMP No. 6
49 | SB3 2019-14 | Improvement /Completion of Composting Facility, Lengaoan, Buguias, Benguet | Buguias | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 500000 |  | 500000 | - Realigned from project: Construction of Composting Facility, Lengaoan, Buguias, Benguet. | SPPMP No. 2 | deferred BUT opened feb 10, 2021 | Budget Ordinance No. 20-12
50 | GF 20058 | Construction of Retaining Wall, Northern Benguet District Hospital, Buguias, Benguet | Buguias | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF SB #3 2019 | 1000000 |  | 1000000 | - Realigned from project: Construction of Retention Wall, NBDH. | SPPMP No. 2 | no pow
51 | GF 20010 | Reconstruction of Datuan Footbridge, Eddet, Kabayan, Benguet | Kabayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF 2020 | 2000000 |  | 2000000 | - Realigned from project: Improvement of Datuan Footbridge, Eddet, Kabayan, Benguet. | SPPMP No. 2 | no pow
52 | GF 2017-10-01 | Construction of a Two-Storey School Building, Tonguey-Nalusbo Barrio School, Madaymen, Kibungan, Benguet | Kibungan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | MAR 2021 | GF 2017 | 1500000 |  | 1500000 |  | SPPMP No. 3 | PREBID FEB 10, 2021 | rebid under 2failed bidding sapp4
53 | GF 2018-20 | Construction of Power House for the 100KVA Generator set donated by DOH & the Reconfiguring of the Electrical Wiring-System of DMDH from A2-Phase to A3-Phase Power System | Bokod | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF 2018 | 1200000 | 0 | 1200000 | - Realigned from project: Improvement of Hospital Building & Annexes, Bokod, Benguet DMMH. | SPPMP No. 4 | ok
54 | GF 2018-53 | Slope Protection at the Back Portion of the Museum Building, Capitol, La Trinidad, Benguet | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF 2018 | 1600000 | 0 | 1600000 | - Realigned from project: Construction of Shaded Walkway. | SPPMP No. 4 | no pow
55 | GF 2019-30 | Road Improvement Going to the Compound of Ambiong Elementary School, Ambiong, La Trinidad, Benguet | La Trinidad | Small Value Procurement | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF 2019 | 200000 | 0 | 200000 | - Realigned from project: Construction of Deepwell & Installation of Water Tank at the Compounf og Ambiong National High School, La Trinidad, Benguet. | SPPMP No. 4 | c/o ppdo
|  | SUB TOTAL | [7 empty] | 43615000 | 0 | 43615000
C. LOCAL DISASTER RISK REDUCTION MANAGEMENT FUND (LDRRMF)
56 | LDRRMF 20010 | Improvement/Rehabilitation of Tublay Gate - Tublay Presidencia Provincial Road, Tubaly, Benguet | Tublay | Public Bidding/ Negotiated Procurement Under Two Failed Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | LDRRMF CY 2020 | 1500000 |  | 1500000 |  | SPPMP No. 6
57 | LDRRMF 20002 | Improvement/Rehabilitation along Sagpat-Sapdaan Provincial Road, Kibungan | Kibungan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | LDRRMF CY 2020 | 1500000 |  | 1500000 | SAPPA4 | SPPMP No. 1 | 2021-02-02
58 | LDRRMF 20012 | Improvement of the Provincial DRRM Building, Wangal, La Trinidad, Benguet | La Trinidad | Small Value Procurement | JAN 2021 | JAN 2021 | MAR 2021 | MAR 2021 | LDRRM Trust Fund | 500000 |  | 500000 |  | SPPMP No. 1 | 2021-01-19
59 | LDRRMF 1519-01 | Improvement along Baguio-Balatoc Provincial Road, Batuang Section | Itogon | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | LDRRM Trust Fund | 2000000 |  | 2000000 |  | SPPMP No. 3 | 2021-02-02 | 2020-10-02
60 | LDRRMF 2019-06 | Construction of Drainage System and Perimeter Fencing at Pond I, Buyagan, La Trinidad, Benguet | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SB NO. 3 CY 2019 LDRRMF | 8000000 |  | 8000000 |  | SPPMP No. 1 | 2021-02-02
61 | LDRRMF 2019-08 | Construction of Drainage Canal System and Protection Wall at the Benguet SPED Center, Wangal, La Trinidad | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | MAR 2021 | SB NO. 3 CY 2018 LDRRMF | 2000000 |  | 2000000 |  | SPPMP No. 1 | PREBID FEB 10, 2021
62 | LDRRMF 2020-01 | Improvement of the Road Cut Section Along Dalicno Barangay Road, Ampucao, Itogon | Itogon | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | LDRRM TF | 6000000 |  | 6000000 |  | SPPMP No. 3 | 2021-02-02 | 20020-383-Aa
63 | 20-15-12 | Construction of Flood Control Along the Asinan Creek to Betel, Poblacion, Buguias, Benguet | Buguias | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | LDRRM TF | 3000000 |  | 3000000 |  | SPPMP No. 5
64 | 20-14-04 | Rehabilitation of Pasbol-Belino Elementary School, Sebang Buguias, Benguet | Buguias | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | LDRRM TF | 1500000 |  | 1500000 |  | SPPMP No. 5 | check origin NEW
65 | 20-14-05 | Improvement of Tuding-Mangga Provincial Road, Tuding, Itogon, Benguet | Itogon | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | LDRRM TF | 1500000 |  | 1500000 |  | SPPMP No. 5
66 | LDRRMF 2019-24 | Rehabilitation of Bedbed -Ambaokok, FMR, Bedbed Mankayan | Mankayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | LDRRMF Trust Fund | 2500000 |  | 2500000 |  | SPPMP No. 6 | check origin NEW
|  | SUB TOTAL | [7 empty] | 30000000 | 0 | 30000000
D. SPECIAL EDUCATION FUND (SEF)
67 |  | Construction of Gymnasium at Nalseb Elementary School Ambassador, Tublay | Tublay | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | MAR 2021 | SEF CY 2020 | 3000000 |  | 3000000 |  | SPPMP No. 1 | PREBID FEB 10, 2021
68 | SEF 20013 | Improvement of Gymnasium at GBDAIS, Balakbak, Kapangan | Kapangan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SEF CY 2020 | 2000000 |  | 2000000 |  | SPPMP No. 1 | 2021-02-02
69 | SEF 20014 | Construction of Canal at Kapangan National High School, Central, Kapangan | Kapangan | Small Value Procurement | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SEF CY 2020 | 1000000 |  | 1000000 |  | SPPMP No. 1 | w/ pow
70 | SEF 2019 10E | Construction of an Open Gymnasium at Bokod Central School, Poblacion | Bokod | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | SEF, SB No. 2 2019 | 4000000 |  | 4000000 |  | SPPMP No. 6 | new
71 | SEF-2019-21003 | Construction of Water Works System with Water Pump of Madaymen National High School, Kibungan | Kibungan | Public Bidding | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 | SEF CY 2019 | 1500000 |  | 1500000 |  | SPPMP No. 1 | w/ pow
72 | SEF-2019-21004 | Construction of Multi-purpose Building Madaymen National High School in Madaymen, Kibungan(additional) | Kibungan | Public Bidding | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 | SEF-SB #2 2019 | 900000 |  | 900000 | Clustered project no. SEF-2019-21004 and SEF-2019-21001 | SPPMP No. 1 | w/ pow
73 | SEF-2018-21001 | Construction of Multi-purpose Building Madaymen National High School in Madaymen, Kibungan | Kibungan | Public Bidding | FEB 2021 | FEB 2021 | FEB 2021 | MAR 2021 | SEF-SB #1 2018 | 1500000 |  | 1500000 |  |  | w/ pow
74 | SEF-2018-21002 | Demolition and Reconstruction of the Alternative Learning School (ALS) in Puguis Elementary School in Puguis, La Trinidad | La Trinidad | Public Bidding | FEB 2021 | FEB 2021 | FEB 2021 | FEB 2021 | SEF CY 2018 | 3278358.62 |  | 3278358.62 |  | SPPMP No. 1 | 2021-02-02
75 | SEF 20006 | Construction of Abatan Elementary School Gymnasium, Abatan, Buguias, Benguet | Buguias | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | SEF CY 2020 | 2000000 |  | 2000000 | Realigned from the Project: Completion of Abatan E/S Gymnasium, Abatan, Buguias, Benguet | SPPMP No. 4 | rebid
|  | SUB TOTAL | [7 empty] | 19178358.62 | 0 | 19178358.62
|  | GRAND TOTAL | [7 empty] | 208913358.62 | 0 | 208913358.62
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC CHAIRPERSON |  | BAC VICE CHAIRPERSON |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC MEMBER |  | BAC MEMBER-ALTERNATE |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
51 | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 | - Realigned from project: Improvement of Pacso Multi-purpose Hall, Pacso, Kabayan, Benguet. | SPPMP No. 2 | awarded JAN. 22

## SAPP2
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 2
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND
1 | GF 2017-005 | Ground Improvement at the Front Elevation of Legislative Building (PWD Access, Landscaping & Viewdeck) Additional | La Trinidad | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF CY 2017 | 915000 |  | 915000 | Clustered Project | SPPMP No. 4 | 2021-02-02
2 | GF 2017-006 | Ground Development at Front Elevation of Capitol Building II (PWD Access, Landscaping & Viewdeck) | [6 empty] | GF CY 2017 | 1500000 |  | 1500000 |  | SPPMP No. 1
3 | GF-PVET (2019) | Establishment of Water Distribution System at San Pascual, Tuba | Tuba | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | GF CY 2019 | 2000000 |  | 2000000 |  | SPPMP No. 6 | REBID | w/ppmp from ppdo
4 | GF 21031 | Improvement of Farm-to-Market Road at Sitio Lamew, Sinacbat, Bakun, Benguet | Bakun | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF CY 2021 | 3000000 |  | 3000000 | Realignment under Budget Ordinance No. 21-02
5 | GF 21093 | Completion of Gymnasium at Upper, Camp, Ampucao, Itogon, Benguet | Itogon | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF CY 2021 | 2500000 |  | 2500000 | Realignment under Budget Ordinance No. 21-02
6 | GF 21064 | Construction of Barangay Hall (Additional Fund), Taneg, Mankayan | Mankayan | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF CY 2021 | 2000000 |  | 2000000 | Realignment under Budget Ordinance No. 21-02
7 |  | Construction of Multi-Purpose Shed at Karao Elementary School, Karao, Bokod | Bokod | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF CY 2020 | 5000000 |  | 5000000 | Realignment under Budget Ordinance No. 21-02
|  | SUB TOTAL | [7 empty] | 16915000 | 0 | 16915000 | 0
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF)
8 | 18080 | Installation of Solar Powered Irrigation System and Additional Water Supply Distribution System at Kabayan Demo Farm | Kabayan | Public Bidding | FEB 2021 | FEB 2021 | MAR 2021 | MAR 2021 | 20% PDF CY 2018 | 3300000 |  | 3300000 |  | SPPMP No. 6 | REBID
9 |  | Road Opening/Improvement of Dumanegdeg-Sayangan-Guinabayan Farm-to-Market Road, Poblacion, Bakun, Benguet | Bakun | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | Realignment under Budget Ordinance No. 21-02
10 |  | Road Opening/Improvement of Pagal-Talingting-Danas Farm-to-Market Road, Shilan, La Trinidad | La Trinidad | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2020 | 3000000 |  | 3000000 | Realignment under Budget Ordinance No. 21-02
11 |  | Road Opening/Improvement at Pipingew (Near Anthony Patinglag's Residence), Lubas, La Trinidad | La Trinidad | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | Realignment under Budget Ordinance No. 21-02
|  | SUB TOTAL | [7 empty] | 10300000 | 0 | 10300000 | 0
|  | GRAND TOTAL | [7 empty] | 27215000 | 0 | 27215000 | 0
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22

## SAPP3
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 3
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
1 | 21130 | Rehabilitation along Peril-Obudan-Capdiaran Road, Pico, La Trinidad | La Trinidad | NEGOTIATED PROCUREMENT UNDER TWO FAILED BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2021 | 1200000 |  | 1200000
2 | 18080 | Installation of Solar Powered Irrigation System and Additional Water Supply Distribution System at Kabayan Demo Farm | Kabayan | NEGOTIATED PROCUREMENT UNDER TWO FAILED BIDDING | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | 20% PDF CY 2018 | 3300000 |  | 3300000 |  | SPPMP No. 6 | REBID
|  | TOTAL | [7 empty] | 4500000 | 0 | 4500000 | 0 |  |  | 0
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member

## SAPP4
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 4
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS |  |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND
1 | GF 2017-10-01 | Construction of a Two Storey School Building, Tonguey-Nalusbo Barrio School, Madaymen | Kibungan | Negotiated Procurement under Two Failed Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | GF 2017 | 1500000 |  | 1500000 | abc corrected at sapp6 SPPMP10 | SPPMP No. 3 | PREBID FEB 10, 2021 | rebid under 2failed bidding sapp4
|  | SUB TOTAL | [7 empty] | 1500000 | 0 | 1500000 | 0 |  |  |  | 0
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF)
2 | 20030 | Contruction of Child Development Center, Proper Gaswiling, Kapangan | Kapangan | Negotiated Procurement under Two Failed Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 | SPPMP 10
|  | SUB TOTAL | [7 empty] | 2000000 | 0 | 2000000 | 0 |  |  |  | 0
C.) LDRRMF TRUST FUND
3 | LDRRMF 20002 | Improvement/Rehabilitation along Sagpat-Sapdaan Provincial Road, Kibungan | Kibungan | Negotiated Procurement under Two Failed Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | LDRRMF CY 2020 | 1500000 |  | 1500000 | SPPMP10
|  | SUB TOTAL | [7 empty] | 1500000 | 0 | 1500000 | 0 |  |  |  | 0
|  | GRAND TOTAL | [7 empty] | 5000000 | 0 | 5000000 | 0 |  |  |  | 0
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22

## SAPP5
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 5
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND
1 | GF 20020 | Construction of Multi-purpose Shed at Karao Elementary School, Karao, Bokod, Benguet | Bokod | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | GF CY 2020 | 5000000 |  | 5000000 |  | SPPMP No. 4 | 2021-02-02 | sppmp7 open May 18
2 | GF 21097-A | Improvement along J207 Bad-ayan - Pugo - Lam-ayan - Sinto - J204 at Bad-ayan Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | SB No.1 GF CY 2021 | 2000000 |  | 2000000 | amended in SAPP6, item no. 27 | SPPMP No. 6 | REBID | sppmp7/8 no pow
3 | GF 21097-B | Improvement along JPR BO - Obanga - Paing - Nakagang - Kebasan - JFMR- BPLS at Amcagwas Section - Bad-ayan - Pugo - Lamayan - Sinto - J204 at Bad-ayan Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | SB No.1 GF CY 2021 | 500000 |  | 500000 | amended in SAPP6, item no. 28 |  |  | sppmp7/8 no pow
4 | GF 21097-C | Improvement along JPR BO - Obanga - Paing - Nakagang - Kebasan - JFMR- BPLS at Paing Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | SB No.1 GF CY 2021 | 500000 |  | 500000 | amended in SAPP6, item no. 29 |  |  | sppmp7/8 no pow
5 | GF 21097-D | Improvement along JPR BO - Obanga - Cayapas - Deckan - Linggew - JFMR NBLDB, Napeyasan Section, Baculongan Sur, Buguias, Benguet |  | Public Bidding/Small Value Procurement | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | SB No.1 GF CY 2021 | 1000000 |  | 1000000 | amended in SAPP6, item no. 30 |  |  | sppmp78 no pow
6 | A.) GF 20048 B.) GF 20049 | Improvement of Legislative Building and Completion of Elevator, Poblacion | La Trinidad | Public Bidding | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | SB No.1 GF CY 2021 | 6000000 |  | 6000000 | amended in SAPP6, item no. 4 |  |  | sppmp7/8 no pow
7 | SB3-019 | Improvement of Bagsakan Area, Cold Chain Project, Wangal, La Trinidad, Benguet | La Trinidad | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | SB No.3 GF 2019 | 2700000 |  | 2700000 |  |  |  | sppmp10/9 open June8
|  | SUB TOTAL | [7 empty] | 19000000 | 0 | 19000000 |  |  |  | 19000000
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF)
8 | 18005 | Improvement along National Road Junction-Diboong-Bangao-Provincial Road, Gusaran, Kabayan, Benguet | Kabayan | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | SB No.1 20% PDF CY 2021 | 5000000 |  | 5000000 | amended in SAPP6, item no. 117 | SPPMP No. 6 | REBID | sppmp7
9 | 20064 | Road Opening/Improvement of Dumanegdeg-Sayangan-Guinabayan FMR, Poblacion, Bakun, Benguet | Bakun | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 |  |  |  | sppmp7
10 | 20106 | Road Opening/Improvement of Pagal-Talingting-Danas FMR Road, Shilan, La Trinidad, Benguet | La Trinidad | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2020 | 3000000 |  | 3000000 |  |  |  | sppmp7 no pow
11 | 21018 | Construction of Dalicno Waterworks, Ampucao, Itogon, Benguet | Itogon | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2021 | 4000000 |  | 4000000 |  |  |  | sppmp7 no pow
12 | 20041 | Construction of Canal with Riprap along Sitio Binanga Norte (Domingo Carpio to Peter Macayba area Down to Solineg Area), Tuding | Itogon | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 |  |  |  | sppmp10/9 open June8
13 | 20104 | Road Opening/ Improvement at Pipingew (near Anthony Patinglag's Residence) | La Trinidad | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2020 | 2000000 |  | 2000000 |  |  |  | sppmp10 | sapp2
14 | 20105 | Opening/ Improvement of Upper Bayabas, going to Pico, Elementary School, Pico, La Trinidad, Benguet | La Trinidad | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | 20% PDF CY 2021 | 2000000 |  | 2000000 | SEE SAPP1 item 21 |  |  | sppmp11 | sapp3
|  | SUB TOTAL | [7 empty] | 20000000 | 0 | 20000000 |  |  |  | 20000000
C.) LDRRMF TRUST FUND
15 | LDRRMF 21-04f | Rehabilitation of Mogao Farm to Market Road, Balili, Mankayan | Mankayan | Public Bidding/ Small Value Procurement | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | LDRRMF Trust Fund | 1000000 |  | 1000000 | AMENDED IN SAPP8 |  |  | sppmp 9 no pow
16 | LDRRMF 21-04l | Improvement of Ground at the Butterfly Sanctuary/Garden in Bulala, Sablan | Sablan | Public Bidding/ Small Value Procurement | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LDRRMF Trust Fund | 300000 |  | 300000 |  |  |  | sppmp 9 no pow
17 | LDRRMF 21-04e | Rehabilitation of Mogao - Pasnaan Farm to Market Road, Balili, Mankayan | Mankayan | Public Bidding/ Small Value Procurement | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | LDRRMF Trust Fund | 1000000 |  | 1000000 |  |  |  | sppmp 9 no pow
18 | LDRRMF 21-04i | Rehabilitation of Bucao-Abucot - Taltalpok FMR, Eddet, Kabayan | Kabayan | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LDRRMF Trust Fund | 3000000 |  | 3000000 |  |  |  | sppmp 9 no pow
19 | LDRRMF 21-04j | Rehabilitation of Jappa-Conet Farm-to-Market Road, Shilan, La Trinidad, Benguet | La Trinidad | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LDRRMF Trust Fund | 3000000 |  | 3000000 |  |  |  | sppmp 9 no pow
20 | LDRRMF 21-04k | Construction of Drainage Canal From Provincial Evacuation Center (TTMF#2) to Motorpool-Housing Road, Junction, Wangal, La Trinidad | La Trinidad | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LDRRMF Trust Fund | 2000000 |  | 2000000 |  |  |  | sppmp 9 no pow
0
|  | SUB TOTAL | [7 empty] | 10300000 | 0 | 10300000 |  |  |  | 10300000
D.) LGSF-DRRAP
21 | LGSF 21-04g | Rehabilitation of JFMR-Pakakayag-Tinongdol Road, Poblacion, Buguias | Buguias | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LGSF-DRRAP FY 2021 | 2000000 |  | 2000000 |  |  |  | sppmp 9 no pow
22 | LGSF 21-04h | Rehabilitation of Lubas-Lumandi FMR, Ansagan, Tuba | Tuba | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LGSF-DRRAP FY 2021 | 2000000 |  | 2000000 |  |  |  | sppmp 9 no pow
23 | LGSF 21-04-01 | Rehabilitation of Multi-purpose Building at Bulala, Bayabas, Sablan | Sablan | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LGSF-DRRAP FY 2021 | 1270985 |  | 1270985 |  |  |  | sppmp 9 no pow
24 | LGSF 21-04-03 | Rehabilitation of J204 Lengaoan-Cada-Bayoyo FMR, Lengaoan, Buguias | Buguias | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LGSF-DRRAP FY 2021 | 3000000 |  | 3000000 |  |  |  | sppmp 9 no pow
25 | LGSF-21001 | Rehabilitation along Besocol-Ballay FMR, Ballay, Kabayan | Kabayan | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | LGSF-DRRAP FY 2021 | 5800000 |  | 5800000 |  |  |  | sppmp10/9 open June8
26 | LGSF 21-04-04 | Rehabilitation along Alapang - Alno - Tuel Provincial Road, Alapang, La Trinidad | La Trinidad | Public Bidding | JUL 2021 | JUL 2021 | AUG 2021 | AUG 2021 | LGSF-DRRAP FY 2021 | 10000000 |  | 10000000 |  |  |  | sppmp 9 no pow
|  | SUB TOTAL | [7 empty] | 24070985 | 0 | 24070985 |  |  |  | 24070985
|  | GRAND TOTAL | [7 empty] | 73370985 | 0 | 73370985 |  |  |  | 73370985
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22

## SAPP6
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 6
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND
1 | SB2 2021-02 | Improvement of Capitol Open Gymnasium (Additional Fund) | La Trinidad | Public Bidding/Small Value Procurement | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 2 GF 2021 | 322000 |  | 322000 |  |  |  | sppmp 10
2 | SB2 2021-03 | Improvement of San Pascual, Elementary School Ground, San Pascual | Tuba | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 2 GF 2021 | 1000000 |  | 1000000 |  |  |  | sppmp 10
3 | SB1-2021-10 | Improvement of Legislative Building and Completion of Elevator, Poblacion | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 GF CY 2021 | 6000000 |  | 6000000 | This amends item no. 6 of SAPP no. 5 |  |  | sppmp7/8 no pow
4 | SB1-2021-11 | Construction of Police Compac (Sub-Station) at Sitio Poyopoy, Taloy Sur, Tuba, Benguet | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000 |  | SPPMP No. 3 | PREBID FEB 10, 2021 | sppmp8
5 | SB1-2021-12 | Installation of Mainpower Lines of the Hospital and its Allied Buildings at Dennis Molintas District Hospital Bokod, Benguet | Bokod | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000 |  | SPPMP No. 3 | PREBID FEB 10, 2021
6 | SB1-2021-13 | Improvement of Bileng Painan FMR, Lengaoan, Buguias | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
7 | SB1-2021-14 | Improvement of Cada Mansingel FMR at Lengaoan, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
8 | SB1-2021-15 | Improvement of Nangkampil Farm to Market Road, Ballay, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
9 | SB1-2021-16 | Construction of Farm to Market Footbridge & Footpath at Dinubangan, Beckel, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
10 | SB1-2021-17 | Improvement of Km.24 to Salidet FMR, Caliking, Atok, Benguet | Atok | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
11 | SB1-2021-18 | Rehabilitation/Repair of Nasuyuan Footbridge, Magmagaling, Buyacaoan, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
12 | SB1-2021-19 | Rehabilitation/Repair of Gusadan Footbridge, Magmagaling, Buyacaoan, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
13 | SB1-2021-20 | Improvement of Nagawaan-Tam-awan Barangay Road, Balili, Mankayan, Benguet | Mankayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
14 | SB1-2021-21 | Construction of Mayan Flood, Control, Ampusongan, Bakun, Benguet (Phase II) | Bakun | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
15 | SB1-2021-22 | Construction/Improvement of Bad-ayan-Pugo-Lam-ayan, Sinto FMR and Crossing Section, Baculongan Norte, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
16 | SB1-2021-23 | Construction of Canal at Daycong Balasigan, Dontog, Dalicno, Ampucao, Benguet | Itogon | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000 |  |  |  | Contraction
17 | SB1-2021-24 | Improvement of Sokong-Telmud FMR, Eddet, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
18 | SB1-2021-25 | Improvement/Construction of Waterwork System at Taloy Norte, Tuba, Benguet | Tuba | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
19 | SB1-2021-26 | Improvement of Champeg-Besang Paco Road, Pacso, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
20 | SB1-2021-27 | Improvement of Lamut to Toplak Farm to Market Road, Tawangan, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
21 | SB1-2021-28 | Construction of Slope Protection Leading to Bagtangan Elementary School, Mogao, Gambang, Bakun, Benguet | Bakun | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
22 | SB1-2021-29 | Construction of Diversion Canal at Obo-o-Namet-a, Poblacion, Bakun, Benguet | Bakun | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
23 | SB1-2021-30 | Improvement of Lanas-Pan-ayaoan Farm to Market Road, Loo, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
24 | SB1-2021-31 | Improvement and Construction of Concrete Pavement at Sadjap, Balili, La Trinidad, Benguet | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
25 | SB1-2021-32 | Construction of Sacyaban-Tigtiging Kaong FB, Baculongan Norte, Buguias (additional fund) | Buguias | Public Bidding/Small Value Procurement | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 650000 |  | 650000
26 | SB1-2021-33 | Improvement along J207 Bad-ayan - Pugo - Lam-ayan - Sinto - J204 at Bad-ayan Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 GF CY 2021 | 2000000 |  | 2000000 | This amends item no. 2 of SAPP No. 5 | SPPMP No. 6 | REBID | sppmp7/8 no pow
27 | SB1-2021-34 | Improvement along JPR BO - Obanga - Paing - Nakagang - Kebasan - JFMR- BPLS at Amcagwas Section - Bad-ayan - Pugo - Lamayan - Sinto - J204 at Bad-ayan Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 GF CY 2021 | 500000 |  | 500000 | This amends item no. 3 of SAPP No. 5 |  |  | sppmp7/8 no pow
28 | SB1-2021-35 | Improvement along JPR BO - Obanga - Paing - Nakagang - Kebasan - JFMR- BPLS at Paing Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 GF CY 2021 | 500000 |  | 500000 | This amends item no. 4 of SAPP No. 5 |  |  | sppmp7/8 no pow
29 | SB1-2021-36 | Improvement along JPPR BO - Obanga - Cayapas - Deckan - Linggew - JFMR NBLDB, Napeyasan Section, Baculongan Sur, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 GF CY 2021 | 1000000 |  | 1000000 | This amends item no. 5 of SAPP No. 5 |  |  | sppmp78 no pow
30 | SB1-2021-37 | Construction of Open Gym at Tapsan Elementary School, Ampucao, Itogon, Benguet | Itogon | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 5500000 |  | 5500000
31 | SB1-2021-38 | Construction of Stage at Luneta Elementary School Loacan, Itogon, Benguet | Itogon | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
32 | SB1-2021-39 | Improvement along Pan-ayaoan-Balaan Farm to Market Road, Loo, Buguias | Buguias | Public Bidding/Small Value Procurement | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
33 | SB1-2021-40 | Construction of Comfort Room at Senior Citizen's Building, Km.46, Bonglo, Paoay, Atok, Benguet | Atok | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
34 | SB1-2021-41 | Improvement along Nagawa and Dacap Road, Ampucao, Itogon, Benguet | Itogon | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
35 | SB1-2021-42 | Improvement along Proper Balat FMR, Tawangan, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 800000 |  | 800000
36 | SB1-2021-43 | Construction of Footpath along Kesbong to Pikao, Kabayan Barrio, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 200000 |  | 200000
37 | SB1-2021-44 | Improvement of Bankey to Katikman FMR, Daclan, Bokod, Benguet | Bokod | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
38 | SB1-2021-45 | Improvement along Tuangan-Bilig FMR, Bagu, Bakun, Benguet | Bakun | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
39 | SB1-2021-46 | Improvement of Community Road at Gayasi, Wangal, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
40 | SB1-2021-47 | Improvement of Kalakay-Mabel Farm to Market Road, Tawangan, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
41 | SB1-2021-48 | Construction of Footbirdge at Sitio Pacac, Tadiangan, Tuba, Benguet | Tuba | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
42 | SB1-2021-49 | Improvement of Lusab Nakidol FMR Catlubong, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
43 | SB1-2021-50 | Improvement of Mankaet - Beleng Motyocna to Naegawa Road, Sebang, Buguias, Benguet | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
44 | SB1-2021-51 | Improvement of Bakbakan - Akikian FMR, Gusaran, Kabayan, Benguet | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
45 | SB1-2021-52 | Improvement of Waterworks at Tangke, Tadiangan, Tuba, Benguet | Tuba | Public Bidding/Small Value Procurement | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | SB No.1 GF CY 2021 | 300000 |  | 300000
46 | SB1-2021-53 | Construction of Multi Purpose Building of Sto. Nino, Tublay Benguet (Phase II) | Tublay | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
47 | SB1-2021-54 | Improvement of Access Road from the National Road Going to Paoad Elementary School, Tublay, Benguet | Tublay | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 400000 |  | 400000
48 | SB1-2021-55 | Construction of Curb and Gutter Canal along Amocao FMR Bayabas, Sablan, Benguet | Sablan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 300000 |  | 300000
49 | SB1-2021-56 | Improvement of Community Road at Upper Central Poblacion, La Trinidad, Benguet (Near Quintos Area) | La Trinidad | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
50 | SB1-2021-57 | Construction of Isolation Facility of Northern Benguet District Hospital (NBDH) at Abatan, Buguias, Benguet | Kabayan | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 15000000 |  | 15000000 | amended in sapp7
51 | SB1-2021-58 | Construction of Storage Building with Comfort Room and Lavatories (Phase I) for Apiary at Techno Demo Farm in Adaoay, Kabayan, Benguet | Kabayan | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
52 | SB1-2021-59 | Opening of Ag-aggat to Lokot via Salidet FMR at Cayapes, Kapangan, Benguet | Kapangan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2500000 |  | 2500000
53 | SB1-2021-60 | Construction of Footbridge at Makidot to Dacaan, Topdac, Atok, Benguet | Atok | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
54 | SB1-2021-61 | Rehabilitation of Domestic Water System in Mamaga, Balili, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 750000 |  | 750000
55 | SB1-2021-62 | Improvement of Pacongan-Tabbor Road at Bulalacao, Mankayan, Benguet | Mankayan | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
56 | SB1-2021-63 | Rehabilitation of Domestic Water Supply in Camanggaan, Tikey, Bokod, Benguet | Bokod | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
57 | SB1-2021-64 | Completion of Liwang View Deck Dalipey, Bakun, Benguet | Bakun | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
58 | SB1-2021-65 | Improvement of Cotcot Barangay Road, Poblacion, Kabayan, Benguet | Kabayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
59 | SB1-2021-66 | Opening of FMR at Sitio Taroy Camp 1 Tuba, Benguet | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
60 | SB1-2021-67 | Completion of Police Outpost in Mamaga Barangay Balili, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
61 | SB1-2021-68 | Construction of Covered Concrete Canal in front of Madayag Shop to Pond 1 Area and Concreting of Unpaved Road, Poblacion, La Trinidad, Benguet | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
62 | SB1-2021-69 | Improvement of Pathway at Capdiaran, Pico, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
63 | SB1-2021-70 | Extension (Upward) of Slope Protection (Grouted Riprap) Below the Residential House of Ms. Morieta C. Balageo Adjacent to Barangay Hall, Ucab, Itogon, Benguet | Itogon | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
64 | SB1-2021-71 | Improvement/Construction of Namoakan Footbridge Badeo, Kibungan, Benguet | Kibungan | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
65 | SB1-2021-72 | Construction of Slope Protection near Barangay Hall (Provincial Road) Virac, Itogon | Itogon | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
66 | SB1-2021-73 | Reconstruction of Mangi Barangay Health Station, Bayabas, Sablan | Sablan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
67 | SB1-2021-74 | Improvement of Sinko-Topinao Road, Poblacion, Tuba | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
68 | SB1-2021-75 | Improvement, Widening, and Construction of Slope Protection, Antamok Norte, Camp 3, Tuba | Tuba | Public Bidding | May 2021 | May 2021 | Jun 2021 | Jun 2021 | SB No. 1 GF 2021 | 2500000 |  | 2500000
69 | SB1-2021-76 | Improvement of Beey- ata FMR, Bangao, Buguias | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
70 | SB1-2021-77 | Road opening of Bineng to Kawa FMR at Bineng, La Trinidad, Benguet | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
71 | SB1-2021-78 | Opening of Tapugo to Ayong FMR Sinacbat, Bakun | Bakun | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 3000000 |  | 3000000
72 | SB1-2021-79 | Ground Development of Kayapa Elementary School, Kayapa, Bakun | Kayapa | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
73 | SB1-2021-80 | Improvement of Lumecneng FMR, Nangalisan, Tuba | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
74 | SB1-2021-81 | Improvement of Payakpak Manking FMR San Pascual, Tuba | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
75 | SB1-2021-82 | Improvement of Municipal Cemetery Road, Poblacion, Bokod | Bokod | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
76 | SB1-2021-83 | Improvement of Giwi- Alas Tiking Balayan FMR Camp 3, Tuba | Tuba | Public Bidding | May 2021 | May 2021 | Jun 2021 | Jun 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
77 | SB1-2021-84 | Construction/Improvement of Pegguena-Magmagaling Domestic Water Works, Buyacaoan, Buguias | Buguias | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
78 | SB1-2021-85 | Construction of Pulag Multi-purpose Building at Gambang, Bakun | Bakun | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
79 | SB1-2021-86 | Improvement of Barangay Hall, Gumatdang, Itogon, Benguet | Itogon | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
80 | SB1-2021-87 | Opening of Pungol FMR Adaoay, Kabayan | Kabayan | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 2500000 |  | 2500000
81 | SB1-2021-88 | Concreting of Sink Hole Phase II Des-ok at Upper Wangal, Housing, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
82 | SB1-2021-89 | Improvement of Pasnaan - Ayosep FMR Balili, Mankayan | Mankayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
83 | SB1-2021-90 | Improvement of Domesic Waterworks GKNWE Ucab, Itogon | Itogon | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
84 | SB1-2021-91 | Construction of Retaining Wall along the Barangay Road going to Sitio Baayan (near Mismisen residence) Ucab, Itogon | Itogon | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
85 | SB1-2021-92 | Improvement/Construction of Barangay Hall at Ambiong, La Trinidad, Benguet | La Trinidad | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
86 | SB1-2021-93 | Construction of Multi-purpose Gym at Sinacbat, Bakun (Phase II) | Bakun | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 3000000 |  | 3000000
87 | SB1-2021-94 | Improvement of J204-Lengaoan-Cada-Bayoyo FMR, Lengaoan, Buguias | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 3000000 |  | 3000000
88 | SB1-2021-95 | Construction of Naubanan to Daclan waterworks Phase II, Daclan, Bokod | Bokod | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
89 | SB1-2021-96 | Improvement of Balakbak Multi-Purpose Hall, Balakbak, Kapangan | Kapangan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
90 | SB1-2021-97 | Construction of Upper Tomay Flood Control, Bahong, La Trinidad, Benguet | La Trinidad | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
91 | SB1-2021-98 | Improvement of Bawempeta Tongdow FMR, Nawal, Bokod | Bokod | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
92 | SB1-2021-99 | Improvement of Loo Lanas Pan-ayaoan Balaon FMR Patang-o Section, Pan-ayaoan, Loo, Buguias | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
93 | SB1-2021-100 | Construction of Animal Quarantine Facility, San Pascual, Tuba | Tuba | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
94 | SB1-2021-101 | Construction of Fire Station, Buguias, Benguet | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 5000000 |  | 5000000
95 | SB1-2021-102 | Construction of Barangay Health Center, Tublay Central , Tublay | Tublay | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 3000000 |  | 3000000 |  |  |  | Cental?
96 | SB1-2021-103 | Improvement along Dinamili Tinaleb Ta-aw FMR, Ballay, Kabayan | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1000000 |  | 1000000
97 | SB1-2021-104 | Construction of Foottrail at Tivang, Dalupirip, Itogon | Itogon | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
98 | SB1-2021-105 | Improvement along Tinaleb FMR, Ballay, Kabayan | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 350000 |  | 350000
99 | SB1-2021-106 | Leveling of Grounds Toybongan Elementary School, Tabaan Norte, Tuba, Benguet | Tuba | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
100 | SB1-2021-107 | Construction/Improvement of Stage Poyopoy Elementary School, Taloy Sur, Tuba | Tuba | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
101 | SB1-2021-108 | Improvement of Bayabas Multi-purpose Building, Bayabas,Sablan | Sablan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
102 | SB1-2021-109 | Improvement of Bekes-Abao FMR Taneg, Mankayan | Mankayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
103 | SB1-2021-110 | Improvement of Road Leading to Municipal Hall at Poblacion, Sablan, Benguet | Sablan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2000000 |  | 2000000
104 | SB1-2021-111 | Improvement/Construction of Lower Coroz to Bacqueque FMR, Ambasador, Tublay, Benguet | Tublay | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000 | amended in sapp8 (ambassador)
105 | SB1-2021-112 | Improvement of Multi-purpose Building (Phase III) Panad West, Poblacion, Mankayan | Mankayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 2500000 |  | 2500000
106 | SB1-2021-113 | Opening of Baayan to Sabi-an FMR, Taneg, Mankayan | Mankayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000
107 | SB1-2021-114 | Construction of Footbridge along Sitio Upper Tojacap-Barao Creek, Duacan, Kabayan | Kabayan | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
108 | SB1-2021-115 | Construction of Pathway with Drainage Canal, Tabio, Mankayan | Mankayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
109 | SB1-2021-116 | Improvement of Existing Cold Chain Building (Phase 2) | La Trinidad | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 3500000 |  | 3500000
110 | SB1-2021-117 | Improvement of Flooring at Capitol Main Building, Poblacion, La Trindad, Benguet | La Trinidad | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 1100000 |  | 1100000
111 | SB1-2021-118 | Construction of Stage (Additional Fund) at Wangal, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 700000 |  | 700000
112 | SB1-2021-119 | Construction of Storage Room (Additional fund) Wangal Sports Center, Wangal, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No. 1 GF 2021 | 300000 |  | 300000
113 | SB1-2021-120 | Improvement of DILG Office Building, Poblacion, La Trinidad, Benguet | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No. 1 GF 2021 | 500000 |  | 500000
|  | SUB TOTAL | [7 empty] | 162372000 | 0 | 162372000 | 0 |  |  | 162372000
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF)
114 | SB1-2021-01 | Construction of Flood Control Phase II, Bito, Bagong, Sablan, Benguet | Sablan | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | SB No.1 20% PDF 2021 | 2000000 |  | 2000000 |  | SPPMP No. 4 | no pow
115 | SB1-2021-02 | Construction of Vehicular Bridge Balding Camp 3, Tuba, Benguet | Tuba | Public Bidding | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021 | SB No.1 20% PDF 2021 | 3000000 |  | 3000000
116 | SB1-2021-03 | Improvement along National Road Junction-Diboong-Bangao Provincial Road, Gusaran, Kabayan, Benguet | Kabayan | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | SB No.1 20% PDF 2021 | 5000000 |  | 5000000 | This amends item no. 8 of SAPP no. 5
117 | SB1-2021-04 | Improvement of Mankingaw - Sil-ak FMR at Balili, Mankayan | Tuba | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 3000000 |  | 3000000
118 | SB1-2021-05 | Improvement/Construction of Naltet Water Works System and Sanitation, Maduto Cabiten, Mankayan | Mankayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 2000000 |  | 2000000
119 | SB1-2021-06 | Improvement of Domestic Water Works Tinekey to Lower Poblacion, Sablan | Sablan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 2000000 |  | 2000000
120 | SB1-2021-07 | Improvement of Palintaang - Balintag FMR, Baculongan Sur, Buguias | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 2000000 |  | 2000000
121 | SB1-2021-08 | Construction of Ud-udan Domestic Water Works Ampucao, Itogon | Itogon | Public Bidding/ Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 600000 |  | 600000
122 | SB1-2021-09 | Improvement of Existing Potato Seed Production Nursery, Wangal, La Trinidad | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.1 20% PDF 2021 | 3000000 |  | 3000000
123 | 17007 | Construction of New Kapangan District Hospital (KDH) Building (Phase I) Located at Central Kapangan | Kapangan | Negotiated Procurement-Emergency Cases | May 2021 | May 2021 | June 2021 | June 2021 | 20% PDF CY 2017 | 10000000 |  | 10000000 | amended in sapp7 |  |  | SPPMP 10
124 | 20006 | Improvement along Yagyagan-Ampusa Provincial Road, Tuba | Tuba | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | 20% PDF CY 2020 | 5000000 |  | 5000000 |  |  |  | SPPMP 10
125 | SB2-2021-01 | Improvement of Lupog to Kamanpantew Farm to Market Road, Palina, Kibungan, Benguet | Kibungan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | SB No.2 20% PDF 2021 | 1000000 |  | 1000000 |  |  |  | SPPMP 10
SUB TOTAL | [9 empty] | 38600000 | 0 | 38600000 | 0 |  |  | 38600000
C.) LDRRMF
126 | LDRRMF SB1-2021-121 | Construction of Flood Control Dapiting, Alapang, La Trinidad, Benguet | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | LDRRMF General Fund | 1100000 |  | 1100000 |  |  |  | SPPMP 8
128 | DOH-21-02; | Construction of Temporary Treatment and Monitoring Facility (TTMF) | Buguias | Negotiated Procurement-Emergency Cases | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021 | DOH Fund | 10000000 |  | 10000000 | amended in sapp7 |  |  | CLUSTERED
129 | DOH-21-01; | Construction of Sewage Treatment Facility (STP). | Buguias | Negotiated Procurement-Emergency Cases | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021 | DOH Fund | 1300000 |  | 1300000 | amended in sapp7
0
SUB TOTAL | [9 empty] | 12400000 | 0 | 12400000 | 0 |  |  | 12400000
D.) LGSF-DRRAP
|  | SUB TOTAL | [7 empty] | 0 | 0 | 0 | 0 |  |  | 0
GRAND TOTAL | [9 empty] | 213372000 | 0 | 213372000 | 0 |  |  | 213372000
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
10 |  | A. Construction of Sacyaban-Tigtiging Kaong Footbridge, Baculongan Norte, Buguias; B. Construction of Sacyaban-Tigtiging Kaong FB, Baculongan Norte, Buguias (additional fund) | Buguias | Public Bidding | MAY 2021 | MAY 2021 | JUN 2021 | JUN 2021 | A. GF CY 2017; B. SB No.1 CY 2021 GF | 650,000.00 +650,000.00= 1,300,000.00 |  | 650,000.00 +650,000.00= 1,300,000.00
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22
127 | LDRRMF1-2018 | Completion of Slope Protection & Improvement of Ground at the Ewa-Bokes Elementary School, Sagpat, Kibungan, Benguet | Kibungan | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | LDRRMF Trust Fund | 1500000 |  | 1500000 |  |  |  | SPPMP 10 with note of defer from budget

## SAPP7
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 7
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND (GF)
1 | SB1-2021-57 | Construction of Isolation Facility of Northern Benguet District Hospital (NBDH) at Abatan, Buguias, Benguet | Buguias | Negotiated Procurement-Emergency Cases | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 15000000 |  | 15000000 | This amends item no. 50 in SAPP No. 6
SUB TOTAL | [9 empty] | 15000000 | 0 | 15000000 | 0 |  |  | 15000000
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF)
2 | 17007 | Construction of New Kapangan District Hospital (KDH) Building (Phase I) Located at Central Kapangan | Kapangan | Negotiated Procurement-Emergency Cases | May 2021 | May 2021 | June 2021 | June 2021 | 20% PDF CY 2017 | 10000000 |  | 10000000 | This amends item no. 123 in SAPP No. 6 |  |  | SPPMP 10
SUB TOTAL | [9 empty] | 10000000 | 0 | 10000000 | 0 |  |  | 10000000
C.) DEPARTMENT OF HEALTH (DOH) FUND
3 | DOH-21-02 | Construction of a Temporary Treatment and Monitoring Facility (TTMF) | Buguias | Negotiated Procurement-Emergency Cases | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021 | DOH Fund | 10000000 |  | 10000000 | This amends item no. 128 in SAPP No. 6 |  |  | CLUSTERED
4 | DOH-21-01 | Repair and Improvement of Northern Benguet District Hospital (NBDH) (Construction of Sewage Treatment Facility). | Buguias | Negotiated Procurement-Emergency Cases | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021 | DOH Fund | 3500000 |  | 3500000 | This amends item no. 129 in SAPP No. 6
0
|  | SUB TOTAL | [7 empty] | 13500000 | 0 | 13500000 |  |  |  | 13500000
|  | GRAND TOTAL | [7 empty] | 38500000 | 0 | 38500000 |  |  |  | 38500000
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22

## SAPP8
Republic of the Philippines
BENGUET PROVINCIAL GOVERNMENT
SUPPLEMENTAL ANNUAL PROCUREMENT PLAN FOR FY 2021
SUPPLEMENTAL APP NO. 8
NO. | PROJ. NO. | PROCUREMENT PROGRAMS / PROJECTS | PMO/ END USER/ LOCATION | MODE OF PROCUREMENT | SCHEDULE FOR EACH PROCUREMENT ACTIVITY |  |  |  | SOURCE OF FUNDS | ESTIMATED BUDGET (PhP) |  |  | REMARKS
[5 empty] | ADS/POST OF IB/REI | SUB/ OPEN OF BIDS | NOTICE OF AWARD | CONTRACT SIGNING |  | CO | MOOE | TOTAL
A.) GENERAL FUND (GF)
1 | 2021-22 | Completion of Senior Citizen's Multi-purpose Building, Keyang, Gadang, Kapangan | Kapangan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2021 | 1500000 |  | 1500000 | SPPMP12 | SPPMP No. 1 | PREBID FEB 10, 2021 | Sppmp12 | This amends item no. 42 in SAPP No.1
2 | 2021-21 | Construction of Gate and Improvement of Pathway Going to Towing Falls, Poblacion, Sablan | Sablan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2021 | 500000 |  | 500000 | SPPMP12 |  |  | ppmp12
3 | 2021-25 | Improvement of Various Roads (Cawa and Motorpool Extension) at Wangal, La Trinidad, Benguet | La Trinidad | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2021 | 3000000 |  | 3000000 | SPPMP12 |  |  | ppmp12
4 | GF 21101 | Construction of Covered Walk Way Shed at the Entrance of Swamp Road to Frontage of Valley Hotel, Betag, La Trinidad | La Trinidad | Public Bidding | APR 2021 | APR 2021 | MAY 2021 | MAY 2021 | GF CY 2021 | 1500000 |  | 1500000 | This amends item no. 101 in APP 20%PDF 2021 |  | 1500000
5 | SB1-2021-111 | Improvement/Construction of Lower Coroz to Bacqueque FMR, Ambassador, Tublay, Benguet | Tublay | Public Bidding | May 2021 | May 2021 | June 2021 | June 2021 | SB No. 1 GF 2021 | 1500000 |  | 1500000 | This amends item no. 104 in SAPP No. 6
6 | GF 21050 | Opening/Improvement of Bocaeg-Togtogyon FMR, Loo, Buguias | Buguias | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2021 | 1000000 |  | 1000000 | This amends item no. 50 in APP GF 2021
| GF 21036 | Concreting of Barangay Road, Camangaan to Balakbak, Tikey, Bokod | Bokod | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2021 |  |  | 0 | This amends item no. 36 in APP GF 2021
7 | GF 20055 | Extension of Motorpool Shed Support Unit, Wangal, La Trinidad | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2020 | 700000 |  | 700000 | SPPMP14 |  |  | ppmp14
8 |  | Construction of Storage Room | La Trinidad | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | GF CY 2020 | 1000000 |  | 1000000 | SPPMP14 |  |  | ppmp14
|  | SUB TOTAL | [7 empty] | 10700000 | 0 | 10700000 | 0
B.) 20 % PROVINCIAL DEVELOPMENT FUND (PDF) | [10 empty] | 0
9 | 21119 | Opening/Improvement of Batengan-Paltingan FMR, Adaoay, Kabayan | Kabayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | 20% PDF CY 2021 | 1000000 |  | 1000000 | This amends item no. 119 in APP 20%PDF 2021
10 | SB3-2019-29 | Construciton of Kaling-Bashoy-Ranger Station FMR, Kabayan, Benguet | Kabayan | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | 20% PDF CY 2019 | 3000000 |  | 3000000 | SPPMP13 |  |  | ppmp13
11 | 2021-20 | Opening and Improvement along Colog to Takayan-Nagawa-Nabuo Farm to Market Road, Gambang, Bakun | Bakun | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | 20% PDF CY 2020 | 3000000 |  | 3000000 | SPPMP12 |  |  | ppmp12
12 | 21060 | Construction of Retaining Wall along Pukitan Road, Paco, Mankayan | Mankayan | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | 20% PDF CY 2021 | 1000000 |  | 1000000 | This amends item no. 60 in APP 20%PDF 2021
|  | SUB TOTAL | [7 empty] | 8000000 | 0 | 8000000 | 0
C.) LGSF-DRRAP
13 | LGSF 21-04g | Rehabilitation of JFMR-Pakakayang-Tinongdol Road, Poblacion, Buguias | Buguias | Public Bidding | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | LGSF-DRRAP FY 2021 | 2000000 |  | 2000000 | This amends item no. 21 in SAPP5/SPPMP9 |  |  | sppmp9
0
|  | SUB TOTAL | [7 empty] | 2000000 | 0 | 2000000
D.) LDRRM-TF
14 | LDRRMF 21-04f | Rehabilitation of Mogao-Dimoyog Farm-to-Market Road, Balili, Mankayan | Mankayan | Public Bidding/Small Value Procurement | JUNE 2021 | JUNE 2021 | JUNE 2021 | JUNE 2021 | LDRRMF-TF | 1000000 |  | 1000000 | This amends item no. 15 in SAPP5/SPPMP9 |  |  | ppmp ok
15 | LDRRMF 18-71221 | Rehabilitation of Tublay School Home Industries (Annex) Ground, Tublay Central, Tublay, Benguet | Tublay | Public Bidding/Small Value Procurement | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021 | LDRRMF-TF CY 2018 | 1000000 |  | 1000000 | SPPMP12 |  |  | ppmp12
0
|  | SUB TOTAL | [7 empty] | 2000000 | 0 | 2000000
|  | GRAND TOTAL | [7 empty] | 22700000 | 0 | 22700000
PREPARED BY: | [9 empty] | APPROVED:
| BEATRICE S. SERRANO | [8 empty] | MELCHOR D. DICLAS, M.D.
| BAC Secretariat | [8 empty] | Provincial Governor
RECOMMENDED BY:
|  | SUNNY G. SACLA |  | BRIAN A. CAMHIT |  |  |  | RICHARD S. ANTERO |  |  |  | FRANCIS N. DITAN
|  | BAC Chairperson |  | BAC Vice Chairperson |  |  |  | BAC Member |  |  |  | BAC Member
|  | LYDIA K. TICDONEN |  | JENNETTE MARIE G. BANGAO |  |  |  | JERRY L. BOCANOG |  |  |  | ELEAZAR B. CARIAS
|  | BAC Member |  | BAC Member-Alternate |  |  |  | BAC Member |  |  |  | BAC Member
#REF! | GF 20034 | Improvement of Dampeg-Mankew Farm to Market Road (FMR), Pacso, Kabayan, Benguet | Kabayan | Public Bidding | JAN 2021 | JAN 2021 | FEB 2021 | FEB 2021 | GF SB #3 2019 | 2000000 |  | 2000000 |  | SPPMP No. 2 | awarded JAN. 22

## Sheet1
Republic of the Philippines
PROVINCE OF BENGUET
La Trinidad, Benguet
OFFICE OF THE PROVINCIAL BUDGET OFFICER
SUMMARY OF UNOBLIGATED CONTINUING CAPITAL OUTLAY FOR CY 2020
INFRASTRACTURE PROJECTS
(General Fund, 20% PDF and SEF)
As of October 12,2020
YEAR | NO. | FUNCTION/ PROGRAMS/PROJECTS | LOCATION | AMOUNT
A. GENERAL FUND
2015 | 3 | Construction of Public Comfort Room at Bangho Junction | Tublay | 700000
|  | Sub-Total (CY2015 -3 projects) |  | 1500000
2016 | 2 | Construction of Bridge at Stonehill, Balili (additional) | La Trinidad | 2285000
|  | Sub-Total (CY2016 -2 projects) |  | 2385000
2017 | 4 | Construction of PDRRM Office and Emergency Operation Center | La Trinidad | 700000
2017 | 5 | Improvement along Bguio-Balatoc-Itogon Provincial Road (sinkhole), Virac | Itogon | 3300000
2017 | 6 | Construction of Sacyaban - Tigtiging-Kaong Footbridge, Baculongan Norte | Buguias | 650000
2017 | 7 | Perimeter Fencing of Maliclico Watershed Spring, Bakun | Bakun | 100000
2017 | 8 | Construction of two Storey Industrial Arts Building (phase I) at Adaoay National | Kabayan | 360000
2017 | 9 | Improvement of Caucalan- Bekes Domestic Water System, Taloy Sur | Tuba | 1500000
2017 | 10 | Construction of Upper Tram CDC, Ucab | Itogon | 1200000
2017 | 11 | Constyruction of 3x3x10 watertank at Paswek, Puguis La Trinidad | La Trinidad | 105000
2017 | 12 | Construction of two-storey Industrial Arts Building (phase II), Adaoay NHS | Kabayan | 2500000
2017 | 13 | Completion of Barangay Health Station birthing facility, Napsong, Madaymen, Kibungan | Kibungan | 300000
2017 | 14 | Completion of Yangyang comfort room, Ambuaclao | Bokod | 500000
2017 | 15 | Construction of Senior Citizen's Adibay Center Poblacion | Kabayan | 500000
2017 | 16 | Construction of two-storey schiil building, Tongey,Nalusbo Bario School, Madaymen | Kibungan | 1500000
2017 | 17 | Improvement of Pokkong-Pasdong Proper Inuman FMR, Pasdong | Atok | 800000
2017 | 18 | Upgrading of Provincial Jail Electric System Additional | La Trinidad | 300000
|  | Sub-Total (CY2017 -18 projects) |  | 14315000
2018 | 1 | Improvement of Waterworks System at Capitol Main Building- Legislative Building and Annexes (Phase 1) | La Trinidad | 1500000
2018 | 2 | Improvement of Legislative Building | La Trinidad | 5000000
2018 | 3 | Construction of Septic Vault, Capitol | La Trinidad | 300000
2018 | 4 | Construction of Child Development Center, Abiang | Atok | 1500000
2018 | 5 | Construction of Drainage Canal System and Protection Wall at Benguet SPED Center Wangal | La Trinidad | 2000000
2018 | 6 | Construction of Multi-Purpose Building,Cattubo | Atok | 1500000
2018 | 7 | Construction of Shed (gym) at Dalicno Elementary School, Ampucao | Itogon | 1000000
2018 | 8 | Construction of Shaded Walkway connecting Registry of Deeds Building and Capitol Main Building | La Trinidad | 1600000
2018 | 9 | Construction of Annex Building ( Capitol) PhaseIII | La Trinidad | 57000000
2018 | 10 | Completion of PEOBuilding ( Office Extension & Motorpool Vehicle and Heavy Equipment Garage & Repair Shop) | La Trinidad | 8000000
2018 | 11 | Improvement of Torre Elementary School Ground, Camp 3 | Tuba | 250000
2018 | 12 | Improvement of Ligay Elemetary School Ground, Camp 1 | Tuba | 250000
2018 | 13 | Installation of Cold Chain Main Power Line and Accessories, Benguet Cold | La Trinidad | 700000
2018 |  | Chain, Wangal
2018 | 14 | Construction of Composting Facility, Bulala Agri-Eco Farm, Bayabas | Sablan | 1000000
2018 | 15 | Improvement Hospital Building and Annexes, DMDH | Bokod | 1200000
|  | Sub-Total (CY 2018-15projects) |  | 82800000
2019 | 1 | Construction of Annex Building ( Capitol) Phase IV | La Trinidad | 40000000
2019 | 2 | Construction of Sewage Treatment Plant, Capitol | La Trinidad | 8000000
2019 | 3 | Improvement of Water Work System of Capitol Main Bulding, Legislative | La Trinidad | 2000000
2019 |  | Building & Annexes (additional)
2019 | 4 | Construction of Drainage Canal at the Benguet Sports Center, Wangal | La Trinidad | 3000000
2019 | 5 | Construction of Deepwell & Installation of Water Tank, Ambiong NHS | La Trinidad | 200000
2019 | 6 | Fencing of Michael G. Andel E/S at Kamog | Sablan | 500000
2019 | 7 | Construction of Stage at Kibungan NHS, Poblacion | Kibungan | 500000
2019 | 8 | Construction of Shed(gym) at Dalicno Elementary School, Ampucao, | Itogon | 80000
2019 |  | (additional)
2019 | 9 | Extension of Bineng Waterworks System, Bineng (Additional) | La Trinidad | 178000
2019 | 10 | Slope Protection and Fencing at Balili National HighSchool, Balili | Mankayan | 1500000
2019 | 11 | Construction of Drainage Sytem and Perimeter Fencing at Pond I, Buyagan | La Trinidad | 8000000
2019 | 12 | Improvement of Road along Block 7, Phase II of Provincial Housing Project, | La Trinidad | 2000000
2019 |  | Wangal |  |  |  | 110349.32
2019 | 13 | Improvement of Administrative Building Phase I, Located at the Northern | Buguias | 1000000 |  | 95349.32
2019 |  | Benguet District Hospitals Bekes, Buyacaoan
2019 | 14 | Construction of PCL-LNB Mulit-Purpose Building (Phase III), Wangal | La Trinidad | 6000000
2019 | 15 | Opening and Construction of Concrete Pavement ast Wangal Housing | La Trinidad | 3000000
2019 | 16 | Improvement of Farm to Market Road, Ekip | Bokod | 1000000
2019 | 17 | Construction of Muliti-Purpose Gym at Upper Bashoy (Phase I) | Kabayan | 4000000
2019 | 18 | Construction of Multi-Purpose Building, Banangan, Sablan | Sablan | 3000000
2019 | 19 | Construction of Compsting Facility, Lengaoan | Buguias | 500000
2019 | 20 | Establishment oof Water Distribution System at San Pascual | Tuba | 2000000
2019 | 21 | Establishment of Bagsakan Area, Benguet Cold Chain Porject Wangal | La Trinidad | 2700000 | S4
2019 | 22 | Construction of a 4 storey Building, Phase II, ADH | Atok | 20000000
|  | Sub-Total (CY 2019-22 projects) |  | 109158000
|  | TOTAL (General Fund- 60 Projects) |  | 213573000
B. 20% PROVINCIAL DEVELOPMENT FUND
2014 | 1 | Construction of Piggery Building | c/o PVET | 1600000
|  | Sub-Total (CY 2014-1 Project) |  | 1600000
2015 | 1 | Construction of a Multi-Purpose Building (Phase I) | c/o PVET | 1200000
|  | Sub-Total (CY 2015 - 1 Project) |  | 1200000
2016 | 1 | Construction of Two-Storey Industrial Arts Building (Phase I) at Adoay National | Kabayan | 1000000
2016 |  | Highschool, Located at Adaoay
|  | Sub-Total (CY 2016 - 2 Projects |  | 1100000
2017 | 1 | Construction of Palansa Public Comfort Rooms, Bila | Bokod | 200000
2017 | 2 | Construction of New Kapangan District Hospital (KDH) Building (Phase I) located at Central Kapangan | Kapangan | 10000000
2017
2017 | 3 | Construction of Gate and Guard House and Signage (San Pascual) | PVET | 1000000
2017 | 4 | Construction of Gym at Poblacion, Kibungan Central School | Kibungan | 500000
2017 | 5 | Construction of Rain Water Tank for Bokod Natiional High School, Ambangeg, | Bokod | 100000
2017 |  | Daclan Campus, Daclan
2017 | 6 | Perimeter Fencing and Ground Improvement of Nawal Day Care Center, Nawal | Bokod | 300000
2017 | 7 | Completion of Sagpat-Sablang foothpath Concreting, Sagpat | Kibungan | 200000
2017 | 8 | Construction of Water System at Sitio Bocao, Cuba | Kapangan | 250000
2017 | 9 | Construction of Water Reservior, at Sitio Bocao, Cuba | Kapangan | 250000
2017 | 10 | Construction of Multi-Purpose Building, Pito | Bokod | 500000
2017 | 11 | Construction of Tirepath along Sawingan to Bua Barangay Road, Naguey | Atok | 500000
2017 | 12 | Construction of Sawili-Boliweg FMR, Poblacion | Sablan | 500000
2017 | 13 | Opeining of Taroy- FMR and Construction of Waiting Shed at Taroy, Camp 1 | Tuba | 500000
2017 | 14 | Improvement of Torre-Mangga FMR Located at Camp 3 | Tuba | 500000
2017 | 15 | Construction of Daket-Oguban Footbridge, Eddet (additional) | Kabayan | 1000000
2017 | 16 | Opening/Construction of Ampusa-Nangalisan Road, Nangalisan, Tuba | Tuba | 1500000
|  | Sub-Total (CY 2017 - 16 Projects) |  | 17800000
2018 | 1 | Completion of Barangay Health Center, Eddet | Kabayan | 2500000
2018 | 2 | Completion of Barangay Abatan Health Station and Child Development Center | Buguias | 2000000
2018 |  | Building, Abatan
2018 | 3 | Construction of Water Works System, Caew, Bulalacao | Mankayan | 500000
2018 | 4 | Installation of Solar Powered Irrigation System and Additional Water Supply | Kabayan | 3300000
2018 |  | distribution system at Kabayan demo Farm
2018 | 5 | Establishment of Fishpond, San Pascual | Tuba | 2000000
2018 | 6 | Construction of a 4 storey Hospital Building (Phase I), ADH | Atok | 16600000
|  | Sub-Total (CY 2018 - 6 Projects) |  | 26900000
2019 | 1 | Construction of 3 Storey Provincial Health Services Multi-Purpose Building | La Trinidad | 50.000.000.00
2019 | 2 | Construction of Waterworks at Tawangan | Kabayan | 500000
2019 | 3 | Completion of Gym, Ambassador | Tublay | 1500000
2019 | 4 | Completion of Gym, Tinongdan Proper, Tinongdan | Itogon | 1500000
2019 | 5 | Improvement along Bolo-Tocdo FMR, Poblacion | Buguias | 2000000
2019 | 6 | Improvement of Gagahaw-Kimpit FMR, Alinmay | Buguias | 1000000
2019 | 7 | Improvement of Kayapa-Bulisay to Beyeng FMR, Kayapa | Bakun | 3000000
2019 | 8 | Construction of Beleng Belis Barrio School Multi-Purpose Cottage at Beleng- | Kapangan | 500000
2019 |  | Belis
2019 | 9 | Completion of Multi-Purpose Building with Water Tank and Ground | Atok | 800000
2019 |  | Improvement, Pasong
2019 | 10 | Construciton of Kaling-Bashoy-Ranger Station FMR | Kabayan | 3000000
2019
2019 | 11 | Improvement of Mataliktik FMR, Sinacbat | Bakun | 2500000
|  | Sub-Total (CY 2019-11 Projects) |  | 66300000
|  | TOTAL (20% Provincial Development Fund - 37 Projects) |  | 114900000
C. SPECIAL EDUCATION FUND
2018 | 1 | Improvement of Ambiong Elementary School Perimeter Fencing, Ambiong | La Trinidad | 500000
2018 | 2 | Demolition and Reconstruction of Alternative Learnind School (ALS) in Puguis | La Trinidad | 3278358.62
2018 | 3 | Ground Improvement for Senior high School of Tabio National High School at | Mankayan | 3500000
2018 |  | Lepanto
2018 | 4 | Construction of Multi-Purpose Building for Madaymen National Highs School | Kibungan | 1500000
2018 |  | in Madaymen
|  | Sub-Total (CY 2018- 4 Projects) |  | 8778358.62
2019 | 1 | Completino of 1 Storey Bulding for Asokong- Pacso E/S | Kabayan | 800000
2019 | 2 | Construction of School Building at Ampontoc Elementary School, Colalo | Mankayan | 1000000
2019 | 3 | Construction of a Four Seater Water Sealed Comfort Room for Saddle | Kibungan | 1000000
2019 |  | Elementary School in Sagpat
2019 | 4 | Construction of School Building for Saguitlang E/S in Saguitlang | Tuba | 4200000
2019 | 5 | Construction of Water Works System with Water Pump for Madaymen NHS | Kibungan | 1500000
2019 | 6 | Construction of additional Comfort Rooms Tabio NHS in Tabio | Mankayan | 250000
2019 | 7 | Construction of Catwalk Shed at Emilio Javier Memorial NHS in Camp 4 | Tuba | 300000
2019 | 8 | Construction of Open Gymnasium at Kayapa Elementary School | Bakun | 6000000
2019 | 9 | Construction of an Open Gymnasium at Bangao Elementary School, Bangao | Buguias | 6000000
2019 | 10 | Construction of Water Works System for Ampucao Elem.School in Ampucao | Itogon | 300000
2019 | 11 | Construction of an Open Gymnasium at Sagubo Elementary School | Kapangan | 6000000
2019 | 12 | Construction of an Open Gymnasium at Bokod Central School, Poblacion | Bokod | 4000000
2019 | 13 | Construction of Gymnasium of Loo National High School | Buguias | 6000000
2019 | 14 | Construction of Multi-Purpose Building for Madaymen for Madaymen | Kibungan | 900000
2019 |  | National High School (additional)
|  | Sub-Total (CY 2019-14 projects) |  | 38250000
|  | TOTAL (Special Education Fund - 18 Projects) |  | 47028358.62
|  | GRAND TOTAL (115 PROJECTS) |  | 375501358.62
NO. |  | FUNCTION/ PROGRAMS/PROJECTS | LOCATION | AMOUNT
A. GENERAL FUND
1 |  | Construction of Footbridge at Taytay, Cadian, Topdac | Atok | 800000
2 |  | Construction of Footbridge at Makidol to Dacaan, Topdac | Atok | 600000
3 |  | Construction of Decves to Afat Footbridge, Poblacion | Itogon | 300000
4 |  | Improvement of Datuan Footbridge, Eddet | Kabayan | 2000000
5 |  | Construction of Bolo Footbridge, Sitio Bolo, Poblacion | Bokod | 800000
6 |  | Improvement of Road along Phase II, Block IV, Housing, Wangal | La Trinidad | 3080000
7 |  | Construction of Pathway Shed, Camp 6 | Tuba | 1000000
8 |  | Construction of Waiting Shed along Sitio Coplo, Bayabas | Sablan | 200000
9 |  | Construction of Barangay Hall for Brgy. Taneg | Mankayan | 1000000
10 |  | Construction of Gym at Karao Elementary School, Karao | Bokod | 5000000
11 |  | Construciton of Multi-Purpose Gym at Palali Elementary School, Poblacion | Sablan | 5000000
12 |  | Fencing of Longlong Elementary School, Puguis | La Trinidad | 1500000
13 |  | Construction of Balili National High School Gymnasium Phase I, Balili | Mankayan | 2000000
14 |  | Improvement of Classroom Building, Ayosep Elementary School, Balili | Mankayan | 500000
15 |  | Installation of Hand Railings along the Critical Sections of the Aloo-Eli Pathway, | Bokod | 350000
Sitio Bangao, Ambuklao
16 |  | Improvement of Ambangeg to Naybaliw Foot Trail, Daclan, Bokod | Bokod | 500000
17 |  | Fencing and Improvement of Public Comfort Room at Acop, Caponga | Tublay | 1000000
18 |  | Improvement of Tourism Information Center, Poblacion | Itogon | 675000
19 |  | Construction of CICL and VAWC Refugee Center, Duacan | Kabayan | 1000000
20 |  | Improvement of Pacso Multi-Purpose Barangay Hall, Pacso | Kabayan | 2000000
21 |  | Construction of Senior Citizens Multi-Purpose Building, Keyang, Gadang | Kapangan | 1500000
22 |  | Concreting of Sink Hole at Zone 2, Des-ok, Provincial Housing, Wangal | La Trinidad | 500000
23 |  | Enclosure of Multi-Purpose Gym, Poblacion | Sablan | 3000000
24 |  | Construction of two-storey Multi-Purpose Building/Women's Center, Madaymen | Kibungan | 3000000
25 |  | Completion of the Buguias Public Market, Abatan | Buguias | 5000000
26 |  | Improvement of PEO Building, Wangal | La Trinidad | 6000000
27 |  | Drilling and Installation of Deep Well Water Source System at DMDH, Bokod | Bokod | 1000000
28 |  | Construction of Benguet Provincial Jail Kitchen with Dining Hall | La Trinidad | 1500000
29 |  | Repair of Ambangeg Waterworks System, Daclan | Bokod | 500000
A. GENERAL FUND
30 |  | Repair and Restoration (rehab) of Retaining Wall and Conrete Fence of La | La Trinidad | 1421000
Trinidad Central School
31 |  | Repair of Records and Administrative Building NBDH | Buguias | 1000000
32 |  | Rehabilitation of Two Storey Waiting Shed at Junction of the National Road and | Itogon | 1500000
Provincial Road, Antamok
33 |  | Painting and Lighting of the Legeslative Building | La Trinidad | 4000000
34 |  | Painting of Legislative Building(interior) | La Trinidad | 2000000
35 |  | Construction of Parking Area and Driveway with Slope Protection at the back of | La Trinidad | 5000000
the Legislative (Phase I)
36 |  | Installation of the Waterworks System at the Legislative Building | La Trinidad | 2000000
37 |  | Improvement of the Capitol Open Gymnasium | La Trinidad | 1000000
38 |  | Construction of Storage Room | La Trinidad | 1000000
39 |  | Completion of the Barangay Hall with Tourism Information Center at Barangay | Kibungan | 700000
Tacadang
40 |  | Installation of Hand Railings going to Mt. Kabunian | Bakun | 400000
41 |  | Fencing within the Benguet-Kochi Sisterhood Park, Paoay (Phase III) | Atok | 1000000
42 |  | Perimeter Fencing at Bahay PAGASA, Wangal | La Trinidad | 1500000
43 |  | Construction of Drainage Canal at Bahay PAGASA, Wangal | La Trinidad | 300000
44 |  | Construction of Slope Protection (Various section) Eco Farm, Bulala | Sablan | 3000000
45 |  | Construction of a Waste Storage Facility at Kapangan District Hospital | Kapangan | 1500000
46 |  | Upgrading of Electrical System to Three Phase at NBDH | Buguias | 2000000
47 |  | Construction of Retention Wall, NBDH | Buguias | 1000000
48 |  | Improvement of NBDH Building | Buguias | 1000000
49 |  | Improvement/ Rehabilitation along Jose Mencio Provincial Road | Atok | 4000000
50 |  | Improvement/ Rehabilitation along Sagpat-Sapdaan Provincial Road | Kibungan | 1500000
51 |  | Improvement/ Rehabilitation along Datakan-Labueg-Lomon Provincial Road | Kapangan | 1500000
52 |  | Improvement/ Rehabilitation along Lomon-Sagubo- Provincial Road | Kapangan | 2000000
53 |  | Improvement/ Rehabilitation along La Trinidad-Capitol-Bineng Prov'l Road | La Trinidad | 2000000
54 |  | Improvement/ Rehabilitation Tublay Gate-Tublay Presidencia Prov'l Road | Tublay | 1500000
55 |  | Improvement/ Rehabilitation along Halsema-Madaymen Provincial Road | Kibungan | 3500000
56 |  | Electrical Connection of Evacuation Center to Main Line Power Supply | La Trinidad | 600000
|  | TOTAL (General Fund- 56 Projects) |  | 99226000
B. 20% PROVINCIAL DEVELOPMENT FUND
1 |  | Improvement along Sipitan-Palidan Provincial Road | Bakun | 5000000
2 |  | Improvement along Yagyagan-Ampusa Provincial Road | Tuba | 5000000
3 |  | Improvement along Antamok Tram-Ucab Provincial Road | Itogon | 2000000
B. 20% PROVINCIAL DEVELOPMENT FUND
4 |  | Improvement along Lomon - Paykek Provincial Road | Kapangan | 5000000
5 |  | Construction of Health Station, Suyoc-Palasana (phase 1) | Palasaan | 1000000
6 |  | Improvement of Bila Health Station-Coros-Salishet-Bajombong Waterworks | Bokod | 1000000
7 |  | Concstruction of Sodkong- Daklan Waterworks | Daclan, Bokod | 2000000
8 |  | Improvement of Togtogyon Waterworkks | Loo, Buguias | 1000000
9 |  | Construction of Waterworks System from Pikaw Springs Farm to Tumal | Kabayan Barrio | 1000000
10 |  | Construction of Kamanpantew to Lupog DWS | Palina, | 1000000
11 |  | Improvement of Les-eng Tacadang Waterworks | Tacadang | 1300000
12 |  | Completion of Waterworks Project at Sitio Marlboro | Beckel, La | 2000000
13 |  | Improvement if POSDO 1&2 Domestic Waterworks | Tabio | 2000000
14 |  | Construction of Sacbitan- Bengkagan-Balluay Waterworks | Sablan | 1000000
15 |  | Construction of Lower Lasilas Waterworks System (pumping) | Nangalisan | 100000
16 |  | Construciton of Dalabi Waterworks System | Twin Peaks | 500000
17 |  | Construction of Child Development Center, Proper Gaswiling | Gaswiling | 20000000
18 |  | Completion of San Roque Child Development Center | Paco | 1500000
19 |  | Completion of Multi-Purpose Hall, Dalipey | Bakun | 1000000
20 |  | Enclosure of Multi-Purpose Gym with Stage at Keweng, Tinongdan | Itogon | 2000000
21 |  | Completion and Extension of Balili Multi-Purpose Building at Sayucong | Central Balili | 2000000
22 |  | Construction of Multi-Purpose Building at Powerhouse, Camp 6, Camp 4 | Tuiba | 500000
23 |  | Ground Improvement of Municipal Evacuation and Crisis Center, | Itogon | 3000000
Keystone, Ucab
24 |  | Construction of Drainage Canal from the National Highway going up to the Cruz- | La Trinidad | 1500000
Tawang Road at Sitio Atta, Cruz
25 |  | Construction of Drainage along Lubas Road at Sebseb | La Trinidad | 1500000
26 |  | Consttruction of Drainage Canal with Cover at Lower Capjaran, Km4, Pico | La Trinidad | 1350000
27 |  | Construction of Canal with riprap along Sitio Binanga Norte (Domingo Carpio to | Itogon | 2000000 | SAPP4
Peter Macayba area Down to Solineg Area), Tuding
28 |  | Construction of Box Culvert at Central Upper Ambiong (near Juanito's Residence, | La Trinidad | 500000
Ambiong
29 |  | Improvement of Box Culvert at Central Ambiong, Pitdawan | La Trinidad | 700000
30 |  | Improvement of Eroded road Portion Besside Philex Mines Elementary School, | Tuiba | 1000000
Pacdal, Camp 3
31 |  | Construction of Box Culvert at Punas Creek, Andolor | Tabaan Sur | 1000000
32 |  | Construciton of Municiapal Market (Phase II) Provincial Counterpart, Lomon, | Kapangan | 3000000
Paykek
33 |  | Improvement of Riverside Sawmill Access Road, Ampusongan | Bakun | 600000
34 |  | Opening of Yupo-an-Penas FMR, Dalipey | Bakun | 1500000 |  |  | -44160.76
35 |  | Improvement of Alam-am - Gambang FMR, Gambang | Bakun | 3000000 |  |  | 14
41
|  | B. 20% PROVINCIAL DEVELOPMENT FUND |  |  |  |  | 2768.87
36 |  | Improvement of Alam-am - Kilong FMR, Gambang | Bakun | 1000000 |  |  | 7500
37 |  | Opening of Colog- Panakiyan-Bagtangan FMR, Gambang | Bakun | 3000000
38 |  | Opening of Bulisay Agay-ay to Tamangan FMR, Kayapa | Bakun | 2000000
39 |  | Road Opening of Dada-Beyeng-Guinabayan FMR, Poblacion | Bakun | 2000000 |  |  | -33836.89
40 |  | Opening of Macbas to Tenglawan FMR (pahse II), Sinacbat | Bakun | 100000
41 |  | Improvement of Proper Ekip FMR, Ekip | Bokod | 4400000
42 |  | Improvement of Geweng to Porspek FMR at Anoples, Pito | Bokod | 2000000
43 |  | Improvement of JFMR-NMS Baso Road, Amgalayguey | Buguias | 1500000
44 |  | Opening of Apanan-Dondontog - Lolotab FMR, Alinmay | Buguias | 1000000
45 |  | Imrpovement of Pugo FMR, Baculongan Norte | Buguias | 1000000
46 |  | Construction of Concrete Pavement along J204 Bekes-Dontog-Sibugan | Buguias | 1000000
47 |  | Improvement of Ambanglo-Masoyosoy-Catlubong FMR, Catlubong | Buguias | 5000000
48 |  | Improvement of CT5-73 Daldal-Akipan-Lengaoan JFMR (Akipan Section) Lengaoan | Buguias | 1000000
49 |  | Improvement of JFMR73 STP- Posel-Kayang-Ampetang Road, Poblacion | Buguias | 2000000
50 |  | Improvement of Paneg-an-Tamangan FMR (Camanlanga Section) Sebang | Buguias | 1500000
51 |  | Improvement of Simpa FMR, Ampucao | Itogon | 2000000
52 |  | Improvement of Doteng Loacan Municipal Road, Loacan | Itogon | 2000000
53 |  | Construction of Canal along Provincial Road (infront of Mr. Sibayan to First Gate | Itogon | 1500000
Checkpoint), Virac
54 |  | Concreting of Pavement along Upper Adaoay FMR | Kabayan | 500000
55 |  | Improvement along Anchokey FMR (Otbong Portion), Anchokey | Kabayan | 1000000
56 |  | Construction of Riprap along Tudian FMR, Ballay | Kabayan | 1000000
57 |  | Improvement of Kaling to Sangal - Bashoy FMR | Kabayan | 2500000
58 |  | Improvement along Proper Lusod to Awing Access Road, Lusod | Kabayan | 5000000
59 |  | Road Opening at Bolo to Pudong Barangay Hall, Pudong | Kapangan | 2000000
60 |  | Improvement (Pavement) of Ubod FMR, Taba-ao | Kapangan | 500000
61 |  | Concreting along Sapdaan-Amog-on FMR, Sagpat | Kibungan | 1500000
62 |  | Improvement of the Raod Intersection at Upper Riverside, Ambiong | La Trinidad | 700000
63 |  | Road Opening at Pipingew (near Anthony Patinfals residence) Lubas | La Trinidad | 2000000 | s4
64 |  | Improvement of Upper Bayabas going to Pico Elementary School | La Trinidad | 2000000
65 |  | Improvement of Pagal- Damas FMR, Shilan | La Trinidad | 3000000
66 |  | Improvement of Atayan-Balili Provincial Road, Balili | Mankayan | 10000000
67 |  | Rehabilitation of Six (6) sources of Potable Water and Pipeplines, Poblacion | Kabayan | 2000000
68 |  | Opening or Yabyabuan-Sholshol Farm to Market Road, Bagong | Sablan | 2000000
69 |  | Construction of Farm to Market Vehicular Bridge for Bued River to Balding, | Tuba | 3000000
Camp 3
70 |  | Improvement of Malanac-Shekdan Road, Daclan | Tublay | 1000000
|  | TOTAL (20% Provincial Development Fund -70 Projects) |  | 165150000
C. SPECIAL EDUCATION FUND
1 |  | Construction of Sidewalk with Railings along Tinaleb Elementary School, Ballay | Kabayan | 800000
2 |  | Constrution of Catwalk Shed at Dio-alan Elementary School, Bagu | Bakun | 600000
3 |  | Construction of a Permanent Fence of Alicay-Segundo Elementary School at | Bakun | 500000
Dalingoan, Sinacbat
4 |  | Completion of Abatan Elementary School Gymnasium, Buguias | Buguias | 2000000
5 |  | Construction of Grouted Riprap Between Natubleng Elementary School and | Buguias | 2000000
Sinipsip National High School, Natubleng Extension
6 |  | Improvement of Baguio Gold Elementary School, Tuding | Itogon | 2000000
7 |  | Construction of Gymnasium at Nalseb Elementary School, Ambassador | Tublay | 3000000
TOTAL (Special Education Fund - 7 Projects)
GRAND TOTAL (131 PROJECTS)
7 | 21-01-02 | Improvement of Halsema - Pasanan- Pactil Farm-to-Market Road, Ambassador, Tublay, Benguet | Tublay |  | Public Bidding | JULY 2021 | JULY 2021 | AUG 2021 | AUG 2021 | GF CY 2020 | 2000000 | 2000000 | Deleted not funded in SB No.1