## PMR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | BENGUET PROVINCIAL GOVERNMENT Procurement Monitoring Report as of June 30, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
Atok
SB1-2021-17 | Improvement of KM. 24 to Salidet FMR, Caliking, Atok, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 | 01/27/2022 | 01/27/2022 | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 498971.9 |  | 498971.9 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/02/2021 | 12/02/2021 | 12/02/2021
DOH-21-03 | A) Repair and Improvement of Atok District Hospital | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/16/2022 | 03/16/2022 | 80.00CD |  | A) T.F HFEP of DOH-CAR | 1350000 |  | 1350000 | 3495205.41 |  | 3495205.41 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
DOH-21-03 | B) Repair and Improvement of Atok District District Hospital | [33 empty] | 187.00CD |  | B) HFEP of DOH-CAR | 2150000 |  | 2150000
2022085 | Construction of Concrete Pavement Along Lolita's Store to Sacla's Residence, Bosleng, Paoay, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 | 03/28/2022 | 03/29/2022 | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999170.49 |  | 999170.49 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/28/2022 | 01/28/2022 | 01/28/2022
2022083 | Improvement of KM 22 Bilis FMR (Piloy Section), Caliking, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/18/2022 | 02/18/2022 | 06/01/2022 | 06/08/2022 | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999300 |  | 999300 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/04/2022 | 02/04/2022 | 02/04/2022
2022086 | Construction of Concrete Pavement along Paoay Proper Road in Between Ernesto Pocsi's and Anton Boda's Residence, Paoay, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 | 06/27/2022 | 06/27/2022 | 38.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999051.87 |  | 999051.87 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/11/2022 | 03/11/2022 | 03/11/2022
GF 22004 | Improvement of Jose Mencio Provincial Road (Beside the Pual Assembly of God Church-Pagc), Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 07/05/2022 | 07/07/2022 | 35.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997017.12 |  | 997017.12 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
2022082 | Improvement of Guiweng to Andiongan Barangay Road,Boy-Otan Section,Abiang,Atok | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/24/2022 | 05/24/2022 | 07/05/2022 | 07/07/2022 | 65.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997064.28 |  | 1997064.28 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
2022088 | Improvement / Pavement of Patapat Farm to Market Road, Topdac, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 |  | 11/10/2022 | 42.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998624.26 |  | 998624.26 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022089 | Improvement/Pavement of Tamocmoc Farm to Market Road, Topdac,Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 |  | 10/14/2022 | 52.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998641.12 |  | 998641.12 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022071 | Construction of Riprap to Support Barangay Road Boneng, Naguey, Atok | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 07/29/2022 | 07/29/2022 | 09/06/2022 | 09/08/2022 | 74.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997466.1 |  | 1997466.1 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022084 | Improvement of Loakan-Ampaloc FMR, Cattubo,Atok | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/23/2022 | 08/23/2022 | 09/12/2022 | 09/12/2022 | 70.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2998484.47 |  | 2998484.47 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
LDRRMF 22-13 | Rehabilitation/Improvement along Tulodan-Sayangan Provincial Road, Atok, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/23/2022 | 08/23/2022 | 09/12/2022 | 09/15/2022 | 56.00 CD |  | 70% PDRRMF CY 2022 | 3000000 |  | 3000000 | 2998666.07 |  | 2998666.07 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
LDRRMF 22-10 | Rehabilitation/Improvement along Mencio Provincial Road, Atok, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 09/12/2022 | 09/12/2022 | 81.00 CD |  | LDRRMF CY 2022 | 4000000 |  | 4000000 | 3996520.45 |  | 3996520.45 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
GF 22003 | Construction of Composting Facility, Lower Abiang, Abiang, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 09/06/2022 | 09/06/2022 |  | 10/20/2022 | 48.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499800 |  | 499800 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022
LGSF 2021-002 | Rehabilitation / Improvement of Wasan Farm-to-Market Road at Poblacion, Atok | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 |  | 10/11/2022 | 68.00 CD |  | LGSF-FALGU FY 2021 | 5000000 |  | 5000000 | 4996372.6 |  | 4996372.6 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
SB1-2022-09 | Construction of Comfort Rooms for the Senior Citizen's Building at Sayangan, Paoay, Atok, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 |  | 10/17/2022 | 31.00 CD |  | SB No. 1 GF 2022 | 261300 |  | 261300 | 261000 |  | 261000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022 |  |  | This is to amend item no. 9 of SAPP14 to update project timeline.
Bakun
SB1-2021-79 | Ground Development of Kayapa Elementary School, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 02/11/2022 | 02/14/2022 | 76.00 CD |  | SB NO.1 CY 2021 GF | 1100000 |  | 1100000 | 1099499.71 |  | 1099499.71 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SB1-2021-58 | Completion of Liwang View Deck, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/22/2022 | 03/24/2022 | 56.00 CD |  | SB NO. 1 (GF 2021) | 1100000 |  | 1100000 | 1090094.79 |  | 1090094.79 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
GF 22013 | Improvement along Sookan-Gambang FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/18/2022 | 02/18/2022 | 05/20/2022 | 05/20/2022 | 40.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997555 |  | 997555 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/04/2022 | 02/04/2022 | 02/04/2022
GF 22012 | Improvement of Copcopit FMR Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/18/2022 | 02/18/2022 | 05/20/2022 | 05/20/2022 | 26.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499500 |  | 499500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
21039 | A) Construction of Mayan Flood Control, Ampusongan, Bakun; | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  | 04/18/2022 | 118.00CD |  | A) 20% PDF CY 2021 | 1000000 |  | 1000000 | 2496243.34 |  | 2496243.34 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022 |  |  | Clustered with project no. SB1-2021-21 under SB1 GF 2021
SB1-2021-21 | B) Construction of Mayan Flood Control, Ampusongan, Bakun Phase II | [35 empty] | B) SB NO.1 CY 2021 GF | 1500000 |  | 1500000
2022072 | Improvement/Construction of Slope Protection at Sitio Datacan, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/01/2022 | 03/01/2022 | 05/17/2022 | 05/18/2022 | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997996.66 |  | 997996.66 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
GF 22019 | Improvement of Alam-am to Nasayotean FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 | 08/01/2022 | 08/01/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998731.42 |  | 998731.42 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
GF 22011 | Improvement of FMR at Tuangan to Belig, Bagu, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 | 04/18/2022 | 04/21/2022 | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999300 |  | 999300 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
2022098 | Improvement of Kayapa-Lingab Farm to Market Road, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/22/2022 | 03/22/2022 | 06/29/2022 | 07/01/2022 | 72.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999299.94 |  | 1999299.94 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
LDRRMF 22-18 | Rehabilitation of Sipitan-Lup-ot Road (Liwang Section), Dalipey, Bakun, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 | 07/07/2022 | 07/07/2022 | 48.00 CD |  | LDRRMF CY 2022 | 1500000 |  | 1500000 | 1499499.46 |  | 1499499.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22009 | Construction of Gym/Multi-Purpose Shed Palidan Integrated School, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 | 07/05/2022 | 07/05/2022 | 119.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999530.31 |  | 2999530.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22010 | Improvement of Nalusbo Paoay-Nalbo Farm to Market Road, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 | 06/29/2022 | 07/01/2022 | 83.00 CD |  | GF CY 2022 | 5000000 |  | 5000000 | 4999499.51 |  | 4999499.51 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22016 | Improvement of Bolbolo Road,Gambang,Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 07/05/2022 | 07/06/2022 | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999499.52 |  | 999499.52 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/07/2022 | 03/07/2022 | 03/07/2022
2022095 | Improvement of Liwang Tubaang Farm to Market Road, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 | 07/05/2022 | 07/05/2022 | 54.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999700 |  | 999700 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/11/2022 | 03/11/2022 | 03/11/2022
2022054 | Construction of Longboy Flood Control (Phase II), Longboy, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  | 06/08/2022 | 64.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000.01 |  | 1999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/21/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22006 | Completion of Gym Bagu Elementary School, Tanap, Bagu, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/12/2022 | 04/12/2022 | 06/09/2022 | 06/10/2022 | 140.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999137.53 |  | 2999137.53 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022096 | Opening of Long-Ayan to Copcopit Farm to Market Road, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 30.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 22014 | Opening of Gambang Batanes-Nagawa FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  | 06/08/2022 | 24.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022093 | Improvement along Ay-ay to Cabutotan (Bec-O Section), Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 64.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000.01 |  | 1999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
2022097 | Improvement of Sookan Sayet Farm to Market Road, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 | 06/23/2022 | 06/23/2022 | 56.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998459.48 |  | 1998459.48 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
2022053 | Construction of Nacanga to Gusol Flood Control, Nakanga, Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 06/22/2022 | 06/22/2022 | 70.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22018 | Improvement of Tuwadan to Balawa FMR, Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/08/2022 | 07/11/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22015 | Improvement of Damoco-Pugongan Fmr, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 09/06/2022 | 09/09/2022 | 20.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499499.67 |  | 499499.67 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
GF 22007 | Completion of Sinacbat Elementary School Gym, Sinacbat, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 07/28/2022 | 08/02/2022 | 140.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999558.72 |  | 2999558.72 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 22017 | Improvement of Municipal Road (Near Contada's Residence), Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 10/11/2022 | 10/11/2022 | 30.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997791.22 |  | 997791.22 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22008 | Improvement of Bas-angan to Mangaan Farm to Market Road, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 10/03/2022 | 10/04/2022 | 61.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999499.32 |  | 2999499.32 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022091 | Improvement of Nangabayo to Demeg Farm to Market Road, Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 09/08/2022 | 09/09/2022 | 49.00 CD |  | 20% PDF CY 2022 | 1500000 |  | 1500000 | 1499999 |  | 1499999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022092 | Opening of Malikliko to Tebaang Farm to Market Road, Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 09/12/2022 | 09/12/2022 | 41.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022090 | Improvement of Tuadan-Banawes Farm to Market Road, Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 09/08/2022 | 09/09/2022 | 64.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
SB1-2021-85 | Construction of Pulag Multi-purpose Building at Gambang, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/27/2022 | 09/27/2022 | 12/13/2022 | 12/15/2022 | 121.00 CD |  | SB No. 1 GF 2021 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
Bokod
A. 20014; B. SB1-2021-95 | Construction of Naubunan to Barangay Daklan Waterworks, Daklan; B. Construction of Naubanan to Daclan Waterworks Phase II Daclan, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 | 02/02/2022 | 02/04/2022 | 143.00 CD |  | A. 20% PDF CY 2020; B. SB No.1 GF CY 2021 | 4000000 |  | 4000000 | 3997097.52 |  | 3997097.52 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022006 | Improvement along Daclan-Camangaan-Tickey-Bonagan Provincial Road, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 | 05/16/2022 | 05/16/2022 | 51.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998674.78 |  | 4998674.78 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
2022014 | Improvement of Binado-Kiweng and Palansa-Aponan-Acnip Provincial Road, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 | 06/21/2022 | 06/30/2022 | 62.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2998000 |  | 2998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 21083 | Improvement of Barangay Covered Court, Bila, Bokod, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/24/2022 | 05/24/2022 | 06/21/2022 | 06/23/2022 | 115.00 CD |  | GF CY 2021 | 1500000 |  | 1500000 | 1499880.74 |  | 1499880.74 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
2022102 | Improvement of Palansa Farm to Market Road, Bila, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/16/2022 | 65.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999086.94 |  | 1999086.94 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
2022107 | Improvement of Balakbak to Liboong Barangay Road, Tikey, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/01/2022 | 08/01/2022 | 71.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
2022055 | Construction of Flood Mitigating Structures within Agno River Basin, along Sitio Barot, Ambuclao, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 08/09/2022 | 08/09/2022 | 09/14/2022 | 09/19/2022 | 89.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2999000 |  | 2999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
LDRRMF 22-15 | Rehabilitation/Improvement along Daclan-Bonagan Provincial Road, Bokod, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/30/2022 | 08/30/2022 | 09/16/2022 | 09/20/2022 | 79.00 CD |  | LDRRMF CY 2022 | 2000000 |  | 2000000 | 1999246.75 |  | 1999246.75 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022056 | Construction of Flood Control Ikip Proper (Turning Point), Ekip, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/30/2022 | 08/30/2022 |  | 10/07/2022 | 95.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2999000 |  | 2999000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022105 | Improvement of Pakak-Akbot Farm to Market Road, Pito, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 | 11/28/2022 | 11/29/2022 | 54.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997112.64 |  | 1997112.64 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
2022103 | A) Improvement of Wakal Farm to Market Road, Nawal, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/06/2022 | 09/06/2022 | 10/25/2022 | 10/25/2022 | 98.00CD |  | A) 20% PDF CY 2022 | 2000000 |  | 2000000 | 4997483.44 |  | 4997483.44 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
2022104 | B) Improvement of Wakal to Nawal Access Road, Nawal, Bokod | [33 empty] | 0.00CD |  | B) 20% PDF CY 2022 | 3000000 |  | 3000000
Buguias
SB1-2021-76 | Improvement of Beey - Ata FMR, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/21/2022 | 03/21/2022 | 72.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1495879.72 |  | 1495879.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
SB1-2021-84 | Construction/ Improvement of Pegguena - Magmagaling Domestic Water Works, Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/03/2022 | 03/03/2022 | 70.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1497844.3 |  | 1497844.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
GF 21079 | Construction of Catlubong Multi-Purpose Building, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 01/28/2022 | 08/16/2022 | 132.00 CD |  | GF CY 2021 | 4000000 |  | 4000000 | 3994726.53 |  | 3994726.53 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
SB1-2021-39 | Improvement along Pan-ayaoan - Balaan Farm to Market Road, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 |  | 05/24/2022 | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 499574.22 |  | 499574.22 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/15/2021 | 12/15/2021 | 12/15/2021
GF - 22046 | Improvement of JFMR GNT - Nalam-an - Napugu-an Road, Nalam-an, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  | 03/28/2022 | 33.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998135.82 |  | 998135.82 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/28/2022 | 01/28/2022 | 01/28/2022
GF 22045 | Improvement of Impogong - Pasbol Farm-To-Market, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 | 04/21/2022 | 04/26/2022 | 57.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999236.47 |  | 999236.47 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/17/2022 | 02/17/2022 | 02/17/2022
2022109 | Improvement of JFMR-CTS 23-Peggueyna Amgaleyguey Road (Pegguena Section), Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 | 06/07/2022 | 06/07/2022 | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999775.77 |  | 999775.77 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/17/2022 | 02/17/2022 | 02/17/2022
GF 22049 | Improvement of JFMR BTA - Landingan - Bengbeng - Bauknit Road, Junction, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 | 05/12/2022 | 05/16/2022 | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996517.64 |  | 996517.64 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/17/2022 | 02/17/2022 | 02/17/2022
GF 22036 | Improvement of JFMR LP - Lusab - Ammanong Road, Lusab, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  | 04/18/2022 | 49.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1996919.12 |  | 1996919.12 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
2022136 | Improvement of JFMR NT-Natalag-Mabila Road, Sebang | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 | 05/02/2022 | 05/05/2022 | 50.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995287.6 |  | 1995287.6 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
GF 22029 | Improvement of JFMR LCP-Pugo-Lengat Road, Lengat, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 06/22/2022 | 07/04/2022 | 29.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499759.43 |  | 499759.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
2022137 | Improvement of JSNR BTK - Toking - Lingadan - Naliskey - J207 Road, Lingadan, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 04/06/2022 | 04/06/2022 | 56.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998899.89 |  | 998899.89 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
GF 22048 | Improvement of J204 Katadtada Road at Sitio Km.73, Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 05/13/2022 | 05/16/2022 | 35.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999990.68 |  | 999990.68 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
2022108 | Improvement of J204-Polis-Akiki-Dilan Road (Polis Section), Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 06/07/2022 |  | 41.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999989.43 |  | 999989.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
GF 22040 | Improvement of JFMR - LLPB - Lanas - Pusong Road, Pusong, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/02/2022 | N/A | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/15/2022 | 03/15/2022 | 05/11/2022 | 05/11/2022 | 48.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996504.5 |  | 996504.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/01/2022 | 03/01/2022 | 03/01/2022
21112 | Improvement of Junction to Alang FMR, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 |  | 08/31/2022 | 53.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1445977.32 |  | 1445977.32 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/21/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022133 | Improvement of J207-Wallayan-Naybo-Abbatan-JFMR BLN Road Along Tanggawan Section, Tanggawan, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 07/01/2022 | 07/07/2022 | 45.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 996095.36 |  | 996095.36 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/07/2022 | 03/07/2022 | 03/07/2022
GF 22051 | Improvement of JFMR OCDL - Lamagan - Cudal - Pugo - JFMR BPLS Road, Cudal, Baculongan Norte | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 07/20/2022 | 07/20/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 995635.39 |  | 995635.39 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/07/2022 | 03/07/2022 | 03/07/2022
2022058 | Construction of Dagdag Magubgubang Flood Control, Loo, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 | 07/04/2022 | 07/08/2022 | 84.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995652.47 |  | 1995652.47 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/21/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22038 | A) Improvement along J204 - Cotcot - Bolinaca - Patugong - Walengweng JFMR BPLS Road (Bannaken Section), Daligdig, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 85.00CD |  | A) GF CY 2022 | 1000000 |  | 1000000 | 2994882.59 |  | 2994882.59 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022120 | B) Improvement of J204-Cotcot-Bolinaca-Patugong-Walengweng-JFMR BPLS Road along Baunaken Section, Daligdig, Bangao, Buguias | [35 empty] | B) 20% PDF CY 2022 | 2000000 |  | 2000000
GF 22052 | Improvement of Water Supply System @ Northern Benguet District Hospital | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 06/10/2022 | 06/14/2022 | 23.00 CD |  | GF CY 2022 | 300000 |  | 300000 | 299999 |  | 299999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
2022122 | Improvement of J204 Bekes-Tagpaya Road (Tagpaya Section), Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 07/05/2022 | 07/05/2022 | 49.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999152.11 |  | 999152.11 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
GF 22031 | Improvement of JSNR BTK - Bot-oan - Tammangan - Panig-An - JFMR OCDL Road, Bayen, Sebeng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 34.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997148.46 |  | 997148.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
2022134 | Improvement of J207-Toking-Alumit Road, Tuking, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 | 06/17/2022 | 06/21/2022 | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999294.3 |  | 999294.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22047 | Improvement of JFMR BLN - Bekes - Palakad - Inuman- JMR WNA Road, Elengan, Poblacion,Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 | 07/01/2022 | 07/07/2022 | 39.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996671.09 |  | 996671.09 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22032 | Improvement of JFMR LLPB - Lanas - Taba-ao - Sumilalaw JFMR BPLS Road (Lanas and Togtogyon Section), Lanas, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
2022116 | Improvement of JFMR OCDL Lammagan-Cudal Pugo JFMR BPLS Road along Cudal Section, Baculongan Sur, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 05/04/2022 | 05/04/2022 | 07/04/2022 | 07/08/2022 | 49.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995339.3 |  | 1995339.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022135 | Improvement of JSNR BTK - Bot-Oan - Tammangan - Panig-an - JFMR OCDL Road (Dugoan Section), Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 07/26/2022 | 08/17/2022 | 71.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3993952.87 |  | 3993952.87 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
2022139 | Improvement of JFMR BTP - Gungal - Nalam-an - Tammangan - JFMR BTP Road, Gangal, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 06/21/2022 | 06/21/2022 | 48.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1994900.77 |  | 1994900.77 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22043 | Improvement of Naleskey - Lingadan Road, Naliskey, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 06/27/2022 | 06/27/2022 | 62.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1998320.09 |  | 1998320.09 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
SB1-2021-101 | Construction of Fire Station, Buguias, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 07/04/2022 | 07/08/2022 | 149.00 CD |  | SB No. 1 GF 2021 | 5000000 |  | 5000000 | 4995002.33 |  | 4995002.33 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22035 | Improvement of JPR BO - Obanga - Paing - Nacagang - Kebsan - JFMR BPLS Road (Nacagang Section), Nacagang, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/04/2022 | 05/04/2022 |  |  | 30.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22042 | Improvement of Tonglo - Lulutab FMR, Bodobod, Amlimay, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/17/2022 | 05/17/2022 | 06/27/2022 | 06/28/2022 | 50.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1997941.98 |  | 1997941.98 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
2022057 | Construction of Sebseb Creek Flood Control, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/31/2022 | 05/31/2022 | 07/04/2022 | 07/08/2022 | 40.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999999.9 |  | 999999.9 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22030 | Improvement of J207-Modayan-Becaeg-Kitongan JFMR BPLS Road, Ludeg, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/05/2022 | 07/05/2022 | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998974.66 |  | 998974.66 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
2022115 | Improvement of J207 - Sebseb - Beling Road (Sebseb Section), Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/21/2022 | 07/25/2022 | 46.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999900.7 |  | 999900.7 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22110 | Construction of Loading Platform, Bineng, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/05/2022 | 07/07/2022 | 63.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 497902.44 |  | 497902.44 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22034 | Improvement of JFMR BPLS-Napolowan-Bangsalan-Linggew-BPI-JFMR BPLS Road, Bangsalan, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/24/2022 | 04/05/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 05/24/2022 | 05/24/2022 | 07/13/2022 | 07/14/2022 | 40.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1996486.18 |  | 1996486.18 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/28/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022
2022121 | Improvement of J204 Bekes Lusong Road (Lusong Section), Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 07/01/2022 | 07/07/2022 | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998696.62 |  | 998696.62 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22050 | Improvement of JSNR BTK - Bot-oan - Lebeng - Nakidol Road, Nakidol, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 11/17/2022 | 11/29/2022 | 30.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997791.7 |  | 997791.7 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
2022123 | Improvement of J207-Magmagaling-Lusong-Sibugan-Dontog-Bekes-J204 Road, Papasok, Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 07/01/2022 | 07/07/2022 | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22044 | Improvement of J204 Bekkes Dontog Sibugan Section Access Road, Sibugan, Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/28/2022 | 06/30/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22037 | Improvement Along JFMR De - Daligdig - Manbayo Road, Daligdig, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 07/13/2022 | 07/14/2022 | 41.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997217.74 |  | 997217.74 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
2022117 | Improvement of JFMR OCDL Bungian - Mong-o- Road (Mong-o Section), Baculongan Sur, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/28/2022 | 06/30/2022 | 39.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22022 | Improvement of Barangay Hall, Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 07/21/2022 | 07/25/2022 | 70.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999435.62 |  | 999435.62 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22041 | Improvement of J204 - Taptap - Colliding - JFMR LC Road, Colliding, Natubleng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 11/17/2022 | 11/29/2022 | 25.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499269.93 |  | 499269.93 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022059 | Construction of Flood Control along J204-Frosty Hill-Upper Patkiaw-JFMR AUP Road, Nan-agto, Natubleng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 11/17/2022 | 11/29/2022 | 28.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 499208.4 |  | 499208.4 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022124 | Improvement of J204-Cotcot-Bolinaca-Patugong-Walengweng-JFMR BPLS, Dagayadeg, Calamagan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/10/2022 | 08/16/2022 | 37.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
2022118 | Improvement of Paing-Beleng Section Along Jprbo-Obanga Paing Nakagang-Kebasan JFMR-BPLS, Baculongan Sur, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/10/2022 | 08/16/2022 | 68.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
SB1-2021-94 | A) Improvement of J204 - Lengaoan - Cada - Bayoyo FMR, Lengaoan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-04-26 | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/09/2022 | 08/15/2022 | 111.00CD |  | A) SB No. 1 CY 2021 | 3000000 |  | 3000000 | 5990553.11 |  | 5990553.11 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
LGSF 21-04-02 | B) Rehabilitation of J204 - Lengaoan - Cada - Bayoyo FMR, Lengaoan, Buguias | [33 empty] | 0.00CD |  | B) LGSF-DDRAP FY 2021 | 3000000 |  | 3000000
2022112 | Opening of JFMR GTK-Tangwawan-Sapid-Mogao Road (Sapid-Mogao Section), Amlimay, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/14/2022 | 07/14/2022 | 09/16/2022 | 09/22/2022 | 15.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998298.79 |  | 998298.79 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
2022131 | Improvement of Apanberang ABB-Upper Patkiaw - JFMR ACC NN, Natubleng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/14/2022 | 07/14/2022 |  | 10/12/2022 | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999037.63 |  | 999037.63 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
2022110 | Improvement of J207-Guieong-Bangbangayen-Paynag Road (Guieong Section), Amlimay, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 |  | 08/31/2022 | 39.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997987.08 |  | 997987.08 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022 |  |  | This is to update item no. 110 of APP 2021-20% PDF
2022126 | Improvement along JFMR-Dangpa-Daldal-Akipan-Lengaoan-JFMR LB Road (Akipan Section), Lengaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/12/2022 | 07/12/2022 | 08/08/2022 | 08/15/2022 | 52.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999570.76 |  | 999570.76 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
GF 22025 | Improvement of JFMR BTP-Lamagan-Ibisan JFMR Road, Bacquit, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/09/2022 | 08/09/2022 | 09/08/2022 | 09/12/2022 | 33.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999500 |  | 1999500 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022125 | Improvement of JFMR BLN-Bekes-Palakan-Inuman-JNR WNA Road, Dontog, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 09/28/2022 | 10/05/2022 | 32.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1994987.41 |  | 1994987.41 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022111 | Opening of JFMR CTS73-Tonglo-Tulibeng Road (Tonglo-Tulibeng Section), Amlimay, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/12/2022 | 08/12/2022 | 09/05/2022 | 09/09/2022 | 22.00 CD |  | 20% PDF CY 2022 | 1500000 |  | 1500000 | 1497494.52 |  | 1497494.52 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
SB1-2021-57 | A) Construction of a (Covid 19) Isolation Building Facility | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-05-31 | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/12/2022 | 08/12/2022 | 09/05/2022 | 09/09/2022 | 266.00CD |  | A) SN Aboitiz Power-Benguet, Inc. (CSR Fund) | 3222869.49 |  | 3222869.49 | 12948422.09 |  | 12948422.09 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022 |  |  | This amends item no. 10 of SAPP5 to update project title/ABC.
SB1-2021-57 | B) Construction of an Isolation Facility of Northern Benguet District Hospital, Abatan , Buguias, Benguet (Additional) (Phase II) | [33 empty] | 0.00CD |  | B) San Roque Power Corporation - EF (ER-194 Fund) | 5248961.05 |  | 5248961.05
SB1-2021-57 | C) Construction of an Isolation Facility of Northern Benguet District Hospital, Abatan, Buguias, Benguet (Phase II) (Additional) | [33 empty] | 0.00CD |  | C) SN Aboitiz Power - Benguet, Inc. (ER-194 Funds) | 4485542.3 |  | 4485542.3
2022138 | Improvement of JSNR BTK-Pasbol-Naigawa-Impugong-J207 Road, Nataynan, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/23/2022 | 08/23/2022 | 11/08/2022 | 11/11/2022 | 43.00 CD |  | 20% PDF CY 2022 | 1500000 |  | 1500000 | 1499999 |  | 1499999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
GF20058 | A) Construction of Retaining Wall, NBDH | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/23/2022 | 08/23/2022 | 11/10/2022 | 11/14/2022 | 73.00CD |  | A) GF CY 2020 | 1000000 |  | 1000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
GF 22053 | B) Construction of Retaining Wall, NBDH, Buguias - Additional | [33 empty] | 0.00CD |  | B) GF CY 2022 | 1000000 |  | 1000000
GF 22026 | Improvement of JFMR MTP-Taaw-Motyocna-Naigawa Road, Bileng, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 09/09/2022 | 09/09/2022 | 69.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999200 |  | 2999200 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022007 | Improvement along Bad-ayan-Manhuyuhuy Provincial Road, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/30/2022 | 08/30/2022 | 10/06/2022 | 10/07/2022 | 106.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4999000 |  | 4999000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022127 | Improvement along JFMR-Dangpa-Daldal-Akipan-Lengaoan-JFMR LB Road (Daldal Section), Lengaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 07/14/2022 | N/A | 07/19/2022 | 07/19/2022 | 07/19/2022 | 07/19/2022 | 08/09/2022 | 08/09/2022 |  | 11/17/2022 | 59.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999187.08 |  | 999187.08 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 07/14/2022 | 07/14/2022 | 07/14/2022
2022130 | Improvement of JFMR ACC NN - Calipongpong - Atras Abante Botingew Road, Natubleng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 | 11/17/2022 | 11/17/2022 | 38.00 CD |  | 20% PDF CY 2022 |  |  |  | 999110.54 |  | 999110.54 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022 |  |  | This amends item no. 130 of APP 2022-20% PDF to update project timeline.
2022114 | Improvement of J207 - Bad-ayan - Pugo - Lam-ayan - Sinto - J204 Road (Lam-Ayan Section), Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 | 12/05/2022 | 12/16/2022 | 31.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998763.42 |  | 998763.42 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022 |  |  | This amend item no.114 in APP 2022-20% PDF to update project timeline
2022113 | Improvement of J207-Bana-ao - Mogao-Tattawa-Gagahaw-Guieong-J207 Road, Nagewgewengan, Amlimay, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  |  | 43.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997346.97 |  | 1997346.97 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
2022040 | Improvement of J207-Abatan Elementary School Road, Abatan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 | 11/10/2022 | 11/14/2022 | 61.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999969.69 |  | 1999969.69 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
2022128 | Improvement of J207 - Loo - Lanas - Pan-ayaoan - Balaan - JFMR BPLS Road (Entrance BSU), Loo, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/27/2022 | 09/27/2022 | 11/11/2022 | 11/14/2022 | 132.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3999969.69 |  | 3999969.69 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
LGSF 2021-003 | Rehabilitation / Improvement of Kasa - Toy-ob - Farm-to-Market Road, Lengaoan, Buguias, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/27/2022 | 09/27/2022 |  | 11/14/2022 | 82.00 CD |  | LGSF-FALGU FY 2021 | 5000000 |  | 5000000 | 4999999 |  | 4999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
LGSF 2021-004 | Rehabilitation / Improvement of Daldal -Labay Farm-to-Market Road, Lengaoan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 |  | 10/12/2022 | 92.00 CD |  | LGSF-FALGU FY 2021 | 5000000 |  | 5000000 | 4995107.57 |  | 4995107.57 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
SB1-2022-02 | Rehabilitation/ Repair of Gusadan Footbridge, Magmagaling, Buyacaoan, Buguias, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 |  | 11/04/2022 | 39.00 CD |  | SB No. 1 GF 2022 | 1000000 | 1000000 |  | 999197.77 | 999197.77 |  | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022 |  |  | SPPMP No. 11
2022129 | Improvement of JFMR ACC NN Nagawa-Lower Patkiaw Road, Proper Patkiao, Natubleng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/18/2022 | N/A | 08/23/2022 | 08/23/2022 | 08/23/2022 | 08/23/2022 | 09/20/2022 | 09/20/2022 |  | 12/05/2022 | 26.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999674.78 |  | 999674.78 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/17/2022 | 08/17/2022 | 08/17/2022 |  |  | This amends item no. 129 of APP 2022- 20% PDF to update project timeline.
Itogon
SB3-2021-06 | Improvement of Laboratory Building at Itogon District Hospital, Tinongdan, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 | 02/04/2022 |  | 34.00 CD |  | SB NO. 3 CY 2021 GF | 522000 |  | 522000 | 521545.24 |  | 521545.24 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/02/2021 | 12/02/2021 | 12/02/2021
GF 21073 | Improvement of Multi-Purpose Building at Cruz, Ampucao, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/16/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 | 01/31/2022 | 01/31/2022 | 129.00 CD |  | GF CY 2021 | 700000 |  | 700000 | 698000 |  | 698000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/15/2021 | 12/15/2021 | 12/15/2021
SB3-2021-08 | Construction of RHU Comfort Room (Back of RHU) Gumatdang, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/06/2022 | N/A | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 03/09/2022 | 03/09/2022 | 112.00 CD |  | SB NO. 3 CY 2021 GF | 1000000 |  | 1000000 | 996517.43 |  | 996517.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/07/2022 | 01/07/2022 | 01/07/2022
21018 | Improvement of Dalicno Waterworks, Ampucao, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  | 04/07/2022 | 126.00 CD |  | 20% PDF CY 2021 |  |  |  | 3998401.1 |  | 3998401.1 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
GF - 22065 | Improvement of Tocmo Brgy. Road, Loacan, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  | 03/22/2022 | 58.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 994325.5 |  | 994325.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/28/2022 | 01/28/2022 | 01/28/2022
SB3-2021-10 | Improvement of Drainage Canal at Bakong, Loacan, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  | 04/07/2022 | 84.00 CD |  | SB NO. 3 CY 2021 GF | 1500000 |  | 1500000 | 1498410.4 |  | 1498410.4 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
SB1-2021-72 | Construction of Slope Protection near Barangay Hall (Provincial Road), Virac, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  | 04/08/2022 | 80.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1497644.31 |  | 1497644.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
21001 | Upgrading of Hospital Water System at Itogon District Hospital | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 65.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1497377.58 |  | 1497377.58 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
SB1-2021-37 | Construction of Open Gym at Tapsan Elementary School, Ampucao, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 | 06/20/2022 | 06/21/2022 | 238.00 CD |  | SB NO.1 CY 2021 GF | 5500000 |  | 5500000 | 5499762.84 |  | 5499762.84 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22062 | Improvement of FMR at Peday to Orengao, Loakan, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/12/2022 | 04/12/2022 | 06/03/2022 | 06/07/2022 | 81.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1980500.93 |  | 1980500.93 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022144 | Improvement of Calhorr Road Kias Virac,Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 50.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 996151.15 |  | 996151.15 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
2022142 | Opening and Improvement of Road From Simpa to Poblacion, Poblacion, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/13/2022 | 06/17/2022 | 69.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997969.88 |  | 1997969.88 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/07/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
SB3-2021-11 | Construction of Satellite Market, Ampucao, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/20/2022 | 06/21/2022 | 140.00 CD |  | SB No. 3 GF CY 2021 | 3000000 |  | 3000000 | 2999545.91 |  | 2999545.91 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
2022004 | Improvement along Kias-Padcal-Philex Provincial Road, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/27/2022 | 06/28/2022 | 97.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998628.65 |  | 4998628.65 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22060 | Improvement of Bangen-Narva Road, Virac, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/24/2022 | 04/05/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 05/24/2022 | 05/24/2022 | 06/24/2022 | 06/24/2022 | 73.00 CD |  | GF CY 2022 | 2500000 |  | 2500000 | 2497511.58 |  | 2497511.58 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/28/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022
2022076 | Rehabilitation of Tongshol Irrigation System, Poblacion, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 |  |  | 58.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997334.45 |  | 997334.45 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
2022060 | Improvement of Canal/Drainage System (Main Canal), Kias, Virac, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 06/27/2022 | 06/27/2022 | 08/22/2022 | 08/22/2022 | 66.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998992.6 |  | 1998992.6 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 21047 | Construction of Municipal Multi-Purpose Stage at Keweng, Tinongdan, Itogon (Phase II) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 |  | 08/30/2022 | 49.00 CD |  | GF 2021 | 1000000 |  | 1000000 | 999102.82 |  | 999102.82 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
GF 22061 | Improvement/Construction of Multi-Purpose Building, Naiba, Tuding, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 07/29/2022 | 07/29/2022 | 09/06/2022 | 09/12/2022 | 82.00 CD |  | GF CY 2022 | 1500000 |  | 1500000 | 1495630.82 |  | 1495630.82 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022021 | Construction of Barangay Health Station, Tuding, Itogon (Phase I) | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/30/2022 | 08/30/2022 | 09/14/2022 | 09/19/2022 | 90.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1996259.62 |  | 1996259.62 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022 |  |  | This amends
SB1-2021-86 | Improvement of Barangay Hall, Gumatdang, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/30/2022 | 08/30/2022 | 09/27/2022 | 09/27/2022 | 140.00 CD |  | SB No. 1 GF 2021 | 1500000 |  | 1500000 | 1493598.37 |  | 1493598.37 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
GF 22066 | Improvement of Barangay Road at Hartwell, Ampucao, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 07/14/2022 | N/A | 07/19/2022 | 07/19/2022 | 07/19/2022 | 07/19/2022 | 08/09/2022 | 08/09/2022 | 09/12/2022 | 09/12/2022 | 45.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999500 |  | 999500 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 07/14/2022 | 07/14/2022 | 07/14/2022
GF 22063 | Construction of Multi-Purpose Building at Bontoc Village, Virac, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/17/2022 | 189.00 CD |  | GF CY 2022 | 2500000 |  | 2500000 | 2499569.05 |  | 2499569.05 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
GF 22067 | Improvement of Pasiday-Tocod-Danglay FMR, Ampucao, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 |  | 10/14/2022 | 50.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2996951.28 |  | 2996951.28 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
Kabayan
SB1-2021-65 | Improvement of Cotcot Barangay Road, Poblacion, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/04/2022 | 01/04/2022 | 02/08/2022 | 02/09/2022 | 77.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1997582.65 |  | 1997582.65 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SB1-2021-87 | Opening and Improvement of Pongol - Binaljan - Abat- FMR, Adaoay, Kabayan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/26/2022 | 01/26/2022 | 03/24/2022 | 03/25/2022 | 118.00 CD |  | SB NO.1 CY 2021 GF | 2500000 |  | 2500000 | 2496775.44 |  | 2496775.44 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SB1-2021-24 | Improvement of Sokong - Telmud FMR, Eddet, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 | 02/10/2022 | 02/10/2022 | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 499558.79 |  | 499558.79 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/02/2021 | 12/02/2021 | 12/02/2021
GF 21082 | Improvement of Senior Citizen's Building, Poblacion, Kabayan | [19 empty] | PLGU-Benguet | No | Negotiated | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/26/2022 | 01/26/2022 |  |  | 140.00 CD |  | GF CY 2021 | 1500000 |  | 1500000 | 1498009.16 |  | 1498009.16 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/02/2021 | 12/02/2021 | 12/02/2021
SB3-2021-09 | Construction of Drainage Canal along Todjacap - Bekes - Balangabang - Singapayew Access Road Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/09/2022 | 75.00 CD |  | SB NO. 3 CY 2021 GF | 1000000 |  | 1000000 | 998000 |  | 998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/15/2021 | 12/15/2021 | 12/15/2021
GF 22077 | Improvement of Patakan, Tinaleb FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/07/2022 | 03/07/2022 | 05/23/2022 | 05/26/2022 | 40.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998998 |  | 998998 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/04/2022 | 02/04/2022 | 02/04/2022
2022149 | Improvement of Lacaan Bito Farm to Market Road, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 04/01/2022 | 04/01/2022 | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999615.26 |  | 999615.26 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
2022037 | Completion of Child Development Center, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/25/2022 | N/A | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/07/2022 | 03/07/2022 | 06/17/2022 | 06/17/2022 | 56.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999327.08 |  | 999327.08 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/24/2022 | 02/24/2022 | 02/24/2022
GF 22080 | Construction of Concrete Canal-Upper Dimapayas Junction FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 | 06/27/2022 | 06/30/2022 | 40.00 CD |  | GF CY 2022 | 1500000 |  | 1500000 | 1498500 |  | 1498500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022147 | Improvement along Bato-An Farm to Market Road, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 | 06/27/2022 | 06/30/2022 | 48.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998000 |  | 1998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022005 | Improvement along National Junction-Diboong-Bangao Provincial Road, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 | 06/27/2022 | 06/30/2022 | 59.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4997500 |  | 4997500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/21/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022061 | Improvement/Concreting of Drainage Canal at Bekes Balangabang Farm to Market Road, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 | 06/28/2022 | 06/28/2022 | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998087.5 |  | 998087.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/11/2022 | 03/11/2022 | 03/11/2022
GF 22075 | Improvement of Bumagat-Mongol FMR, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 | 06/01/2022 | 06/08/2022 | 63.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22078 | Construction of Concrete Canal at Tabayo, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 | 08/01/2022 | 08/10/2022 | 48.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1993567 |  | 1993567 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022150 | Improvement Along Bumagat Farm to Market Road Batan Proper, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 | 06/14/2022 | 06/20/2022 | 61.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995442.3 |  | 1995442.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22081 | Improvement along Bagto-Gawa-Akikian FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/24/2022 | 05/24/2022 | 08/01/2022 | 08/11/2022 | 64.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1997933.29 |  | 1997933.29 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
GF 22073 | Improvement of Children in Conflict with Law Refuge Center, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 06/17/2022 | 06/17/2022 | 63.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499539.52 |  | 499539.52 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22086 | Improvement of Dimapayas FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/25/2022 | 07/28/2022 | 38.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998000 |  | 998000 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22087 | Improvement of Ballay Proper Liang FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 06/15/2022 | 06/20/2022 | 32.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998000 |  | 998000 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22074 | A) Improvement of Proper Lusod to Awing Access Road, Lusod, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-03-23 | 03/24/2022 | 04/05/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 04/19/2022 | 05/17/2022 | 05/17/2022 | 07/25/2022 | 07/28/2022 | 68.00CD |  | A) GF CY 2022 | 3000000 |  | 3000000 | 5997500 |  | 5997500 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/28/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022
GF 22079 | B) Improvement of Proper Lusod to Awing Access Road (Awing Section), Lusod, Kabayan | [35 empty] | B) GF CY 2022 | 3000000 |  | 3000000
2022148 | Improvement of Kiweng Otbong Farm to Market Road, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/24/2022 | 06/30/2022 | 44.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999498.18 |  | 999498.18 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22082 | Improvement along Bagto-Gongo-Bakanganga FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 06/27/2022 | 06/27/2022 | 08/01/2022 | 08/11/2022 | 64.00 CD |  | GF CY 2022 | 2500000 |  | 2500000 | 2497500 |  | 2497500 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
2022151 | Improvement of Apanberang to Patkiaw Farm to Market Road, Pacso, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 | 08/01/2022 | 08/01/2022 | 36.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999600 |  | 999600 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
SB1-2021-114 | Construction of Footbridge along Sitio Upper Tojacap-Barao Creek, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 12/19/2022 | 12/19/2022 | 49.00 CD |  | SB No. 1 GF 2021 | 500000 |  | 500000 | 499293.85 |  | 499293.85 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22072 | Improvement of Barangay Hall, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 12/19/2022 | 12/19/2022 | 91.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999568.14 |  | 999568.14 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22085 | Improvement of Binalyan-Toplac Fmr,Tawangan,Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 09/14/2022 | 09/19/2022 | 39.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998000 |  | 998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
2022022 | Improvement of Babadak Barangay Health Station, Bashoy, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/24/2022 | 119.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1996000 |  | 1996000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
2022077 | Riprapping and Construction of Drying Shed at Mongoto, Pacso, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 09/20/2022 | 09/20/2022 |  | 10/17/2022 | 42.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999700 |  | 999700 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022
GF 22076 | Improvement of Proper to Nakilo FMR, Tawangan, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 |  | 10/24/2022 | 40.00 CD |  | GF CY 2022 | 1500000 |  | 1500000 | 1498500 |  | 1498500 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
LGRCB-22-0003988 | Improvement of Besocol-Ballay Farm-to-Market-Road at Barangay Ballay, Municipality of Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/27/2022 | 09/27/2022 |  | 10/14/2022 | 207.00 CD |  | LGSF-FALGU FY 2022 | 20000000 |  | 20000000 | 19998000 |  | 19998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
GF 22088 | Improvement of Bocao-Abucot-Teltelpok FMR, Eddet, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/18/2022 | N/A | 08/23/2022 | 08/23/2022 | 08/23/2022 | 08/23/2022 | 09/20/2022 | 09/20/2022 | 11/17/2022 | 11/24/2022 | 44.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998000 |  | 998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/17/2022 | 08/17/2022 | 08/17/2022 |  |  | This amends item no. 88 of APP 2022-GF to update project timeline.
SB1-2022-54 | Construction of Abat-Padingad Farm to Market Road Batan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 |  | 11/04/2022 | 16.00 CD |  | SB No. 1 GF 2022 | 1000000 |  | 1000000 | 998014.26 |  | 998014.26 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022 |  |  | SPPMP No. 11
GF 22083 | Improvement of Babalak to Toliling Road, Bashoy, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 | 11/17/2022 | 11/24/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998000 |  | 998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022
2022145 | Improvement of Batengan - Paltingan Farm to Market Road, Adaoay, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 |  |  | 39.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998964.86 |  | 998964.86 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022 |  |  | This amend item no.145 of APP 2022-20% PDF to update project title.
2022044 | Reconstruction of Kimangeb Footbridge, Gusaran, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 | 12/07/2022 | 12/09/2022 | 62.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999800 |  | 999800 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022
Kapangan
21035 | Construction of Barangay Multi-Purpose Building, Taba-ao, Kapangan (phase II) | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 | 03/04/2022 | 03/10/2022 | 148.00 CD |  | 20% PDF CY 2021 | 3000000 |  | 3000000 | 2999481.21 |  | 2999481.21 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21086 | Construction of 2 Units Slab Footbridge and Foot Trail with Hand Railings, Basisil and Paayosan, Pudong, Kapangan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 03/14/2022 | 03/15/2022 | 112.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 994091.64 |  | 994091.64 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/15/2021 | 12/15/2021 | 12/15/2021
SB1-2021-96 | Improvement of Balakbak Multi-Purpose Hall, Balakbak, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/23/2022 | 02/23/2022 | 05/04/2022 | 05/06/2022 | 77.00 CD |  | SB #1 2021 GF | 1500000 |  | 1500000 | 1497334.57 |  | 1497334.57 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
GF 21091 | Improvement of Multi-Purpose Hall & Ground Development, Central, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 | 05/04/2022 | 05/06/2022 | 123.00 CD |  | GF CY 2021 | 1500000 |  | 1500000 | 1497489.46 |  | 1497489.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
20053 | Improvement of Kapangan Public Market Building Annex C, Lomon, Paykek, Kapangan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  | 05/04/2022 | 266.00 CD |  | 20% PDF CY 2020 | 3000000 |  | 3000000 | 2992299.54 |  | 2992299.54 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
LDRRMF 22-11 | Rehabilitation/ Improvement along Lomon-Sagubo Provinical Road, Kapangan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 |  | 07/04/2022 | 63.00 CD |  | LDRRMF CY 2022 | 2000000 |  | 2000000 | 1999099.05 |  | 1999099.05 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022008 | Improvement along Lomon-Paykek Provincial Road, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/03/2022 | 06/07/2022 | 120.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3997297.97 |  | 3997297.97 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
2022013 | Improvement along Lomon-Sagubo Provincial Road, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 09/06/2022 | 09/06/2022 | 61.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4995151.35 |  | 4995151.35 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22102 | Completion of Building at Kapangan District Hospital, Central Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 07/01/2022 | 07/01/2022 | 392.00 CD |  | GF CY 2022 | 10000000 |  | 10000000 | 9994617.32 |  | 9994617.32 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
2022010 | Improvement along Cadtay-Pudong Provincial Road, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/17/2022 | 05/17/2022 | 06/27/2022 | 06/30/2022 | 81.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1992782.18 |  | 1992782.18 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
2022157 | Improvement of Road going to Barangay Hall, Pudong, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/11/2022 | 08/17/2022 | 47.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1994606.8 |  | 1994606.8 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 22096 | Construction of Pongayan Barrio School Covered Court (Shed), Pongayan, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 09/14/2022 | 09/19/2022 | 133.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999999 |  | 2999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
GF 22090 | Improvement of Municipal Building (Annex), Lomon, Paykek, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/09/2022 | 08/09/2022 | 10/06/2022 | 10/11/2022 | 218.40 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2988623 |  | 2988623 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
LDRRMF 21016 | Improvement and or Rehabilitation of Kapangan Provincial Road, Labueg Area, Labueg, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 09/15/2022 | 09/15/2022 | 62.00 CD |  | LDRRMF-TF CY 2021 | 3000000 |  | 3000000 | 2994537.51 |  | 2994537.51 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022153 | Improvement along Barangay Central Road (Sagubo Junction) to Dagao, Cayapes, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/12/2022 | 08/12/2022 | 09/14/2022 | 09/19/2022 | 47.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022156 | Improvement of Barangay Road at Cabilisan, Pudong, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/12/2022 | 08/12/2022 | 09/15/2022 | 09/15/2022 | 50.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1992681.67 |  | 1992681.67 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022154 | Opening of Farm to Market Road, Aagat to Locot (Phase II), Cayapes, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/06/2022 | 09/06/2022 | 11/09/2022 | 11/10/2022 | 47.00 CD |  | 20% PDF CY 2022 | 2500000 |  | 2500000 | 2499499.88 |  | 2499499.88 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
GF 22098 | Construction of Two Comfort Room at Multi-Purpose Building, Landing, Sagubo, Kapangan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/18/2022 | N/A | 08/23/2022 | 08/23/2022 | 08/23/2022 | 08/23/2022 | 09/20/2022 | 09/20/2022 |  | 10/18/2022 | 63.97 CD |  | GF CY 2022 | 500000 |  | 500000 | 499893.72 |  | 499893.72 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/17/2022 | 08/17/2022 | 08/17/2022
Kibungan
SEF 2018-21001 | A) Construction of Multi-Purpose Building for Madaymen National High School in Madaymen, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 02/21/2022 | 03/01/2022 | 198.98CD |  | A) SEF-SB N0. 1 CY 2018 | 1500000 |  | 1500000 | 2399336.22 |  | 2399336.22 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SEF 2019-21004 | B) Construction of Multi-Purpose Building for Madaymen National High School, Kibungan, Benguet (ADDITIONAL) | [35 empty] | B) SEF-SB N0. 2 CY 2019 | 900000 | 900000
GF 22104 | Improvement of Pakpakitan - Taliboy-oc - Lamut Farm to Market Road,Madaymen,Kibungan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 05/23/2022 | 05/26/2022 | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999.7 |  | 999999.7 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
2022012 | Improvement along Halsema-Madaymen Provincial Road, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 | 07/18/2022 | 07/19/2022 | 130.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998000 |  | 4998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022160 | Opening of Beyeng to Almasi Farm to Market Road, Palina, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 | 06/24/2022 | 06/24/2022 | 117.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4999000.01 |  | 4999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022159 | Improvement of Riverside-Tagpaya-Kuadsil Access Road, Madaymen, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 04/12/2022 | 04/12/2022 | 06/01/2022 | 06/08/2022 | 71.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2999000 |  | 2999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
GF 22103 | Improvement of Masaybo-Panayag Farm to Market Road, Sagpat, Kibungan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 07/26/2022 | 08/01/2022 | 25.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499061.28 |  | 499061.28 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
LDRRMF 22-06 | Construction of Slope Protection along Riverside-Colili Road (Bobocco Section), Kibungan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 08/01/2022 | 08/02/2022 | 61.00 CD |  | LDRRMF CY 2022 | 1500000 |  | 1500000 | 1499500 |  | 1499500 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 22105 | Improvement of Deccan - Alsoka - Tangadan Farm to Market/ Access Road, Sagpat, Kibungan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 08/09/2022 | 08/09/2022 |  | 10/14/2022 | 32.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999937.5 |  | 999937.5 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022 |  |  | This amends item no. 105 of APP 2022- GF to update project title.
2022017 | Construction of Multi-purpose Gymnasium, Napsong, Madaymen, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 | 11/14/2022 | 11/18/2022 | 88.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2999000 |  | 2999000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
2022028 | Repair of Takip-Tamog-o Domestic Water System, Poblacion, Kibungan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 |  | 12/06/2022 | 41.00 CD |  | 20% PDF CY 2022 | 1000000 | 1000000 |  | 999887.96 | 999887.96 |  | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022 |  |  | This amends item no. 28 of APP 2022-20% PDF to update project timeline.
La Trinidad
2021-25 | Improvement of Various Road (Cawa and Motorpool - Extension) at Wangal, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 02/21/2022 | 02/21/2022 | 166.00 CD |  | SB NO. 3 CY 2019 GF | 3000000 |  | 3000000 | 2996803.83 |  | 2996803.83 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SB1-2021-77 | Road Opening and Improvement of Bineng to Kawa Farm to Market Road, Bineng, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/14/2022 | 01/14/2022 | 02/22/2022 | 03/01/2022 | 72.00 CD |  | SB NO.1 CY 2021 GF | 1100000 |  | 1100000 | 1097000 |  | 1097000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
SB1-2021-16 | Construction of Farm to Market Footbridge & Footpath at Dinubangan, Beckel, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 | 04/01/2022 | 04/04/2022 | 70.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 498662.76 |  | 498662.76 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/15/2021 | 12/15/2021 | 12/15/2021
SB3-2021-05 | Construction of Benguet Provincial Jail Kitchen with Dining Hall (Additional Amount) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/06/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 |  | 03/02/2022 | 47.00 CD |  | SB NO. 3 CY 2021 GF | 300000 |  | 300000 | 299663.39 |  | 299663.39 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/07/2022 | 01/07/2022 | 01/07/2022
20106 | Road Opening/ Improvement of Pagal - Talingting - Danas Farm to Market Road, Shilan, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 | 05/05/2022 | 05/06/2022 | 139.00 CD |  | 20% PDF CY 2020 | 3000000 |  | 3000000 | 2998525.09 |  | 2998525.09 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
LGSF-21-04-04 | Rehabilitation along Alapang - Alno - Tuel Provincial Road, Alapang, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 1970-01-01 | 01/18/2022 | 01/26/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 224.00 CD |  | LGSF-DRRAP FY 2021- TRUST FUND | 10000000 |  | 10000000 | 9859648.19 |  | 9859648.19 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/24/2022 | 02/04/2022 | 02/04/2022 | 02/04/2022 |  |  | REBID- FAILED (Aug. 24, 2021)
GF 21032 | Improvement of Road at Windy Hill (Cenon Garcia Area), Poblacion, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 | 04/25/2022 | 04/27/2022 | 40.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 999399.72 |  | 999399.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
21054 | Improvement of Drainage Canal, Siadto Malinias Luspian Cores Area, Poblacion, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 | 05/23/2022 | 05/26/2022 | 65.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1499999.72 |  | 1499999.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
2022009 | Improvement along Alno-Tuel-Balway Provincial Road, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 | 09/05/2022 | 09/07/2022 | 118.00 CD |  | 20% PDF CY 2022 | 8000000 |  | 8000000 | 7987830.92 |  | 7987830.92 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
2022062 | Construction of Drainage Canal at Akes to Benguet National HS Annex, Alno, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/02/2022 | N/A | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/15/2022 | 03/15/2022 | 05/23/2022 | 05/27/2022 | 60.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998977.02 |  | 998977.02 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22120 | Improvement of Balucas Community Road, Shilan, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 09/05/2022 | 09/07/2022 | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998933.49 |  | 998933.49 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/07/2022 | 03/07/2022 | 03/07/2022
GF 22127 | Improvement of Puguis - Buyagan - Poblacion PR Junction (Rotonda) - LTO - Motorpool, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-02-18 | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 49.00 CD |  | GF CY 2022 | 10000000 |  | 10000000 | 9990430.31 |  | 9990430.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 22126 | Improvement of Alapang - Alno - Tuel Provincial Road, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-02-18 | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 | 05/31/2022 | 06/02/2022 | 120.00 CD |  | GF CY 2022 | 10000000 |  | 10000000 | 9997717.4 |  | 9997717.4 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 22111 | Completion of the Perimeter Fence at La Trinidad National High School, Lubas, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 06/21/2022 | 06/22/2022 | 37.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 496846.55 |  | 496846.55 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
GF 22112 | Completion of Barangay Hall Extension of Barangay Balili,La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 06/10/2022 | 06/13/2022 | 47.00 CD |  | GF CY 2022 | 700000 |  | 700000 | 698509.14 |  | 698509.14 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
2022067 | Construction of Flood Control from Sitio Dapiting Towards Sitio Proper, Alapang, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 05/31/2022 | 05/31/2022 | 07/04/2022 | 07/04/2022 | 86.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997905.12 |  | 1997905.12 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/21/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
GF 22124 | Improvement/ Construction of Flood Control at Dong-oy River, Bahong, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/07/2022 | 06/07/2022 | 84.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1998805.16 |  | 1998805.16 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22116 | Improvement along Motorpool-Wangal Extension Barangay Road, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 | 06/17/2022 | 06/17/2022 | 63.00 CD |  | GF CY 2022 | 2600000 |  | 2600000 | 2594808.71 |  | 2594808.71 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/07/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 21115 | Ground Improvement of Trade Fair Area at Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  | 05/30/2022 | 84.00 CD |  | GF 2021 | 5000000 |  | 5000000 | 4994310.03 |  | 4994310.03 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22117 | Construction of School Building at Puguis National High School, Longlong, Puguis,La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/04/2022 | 05/04/2022 | 09/05/2022 | 09/07/2022 | 268.00 CD |  | GF CY 2022 | 6000000 |  | 6000000 | 5991252.43 |  | 5991252.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
2022163 | Improvement of Oliweg Road, Cruz, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/17/2022 | 05/17/2022 | 08/01/2022 | 08/03/2022 | 77.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1994499.31 |  | 1994499.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
GF 22108 | Improvement of Road at Sitio Nayono, Bineng, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 07/01/2022 | 07/04/2022 | 43.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998837.61 |  | 998837.61 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
2022164 | Opening and Construction of Road at Pine Breeze Shamolog, Pico, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 10/06/2022 | 10/07/2022 | 45.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998767.87 |  | 1998767.87 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
2022066 | Construction of Drainage Canal along Betag Swamp Road near Pedazo's Area to Toyong Creek in Zone 3, Betag, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 | 09/20/2022 | 09/21/2022 | 51.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999500 |  | 999500 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
2022050 | Improvement of Pathway with Drainage at Tabangaoen, Balili, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 | 09/12/2022 | 09/16/2022 | 58.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 499443.98 |  | 499443.98 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
GF 2018-53 | Slope Protection at the Back Portion of Museum Building, Capitol | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 07/29/2022 | 07/29/2022 | 09/05/2022 | 09/06/2022 | 56.00 CD |  | GF 2018 | 1600000 |  | 1600000 | 1594465.85 |  | 1594465.85 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
GF 22113 | Improvement of Barangay Tawang Multi-Purpose Gymnasium, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/30/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 09/12/2022 | 09/14/2022 | 31.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 498477.53 |  | 498477.53 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
2022049 | Improvement of Pathway with Drainage at Mamaga, Balili, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 09/12/2022 | 09/14/2022 | 56.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 498745.82 |  | 498745.82 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
SB1-2021-92 | Improvement/Construction of Barangay Hall at Ambiong, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 |  |  | 164.00 CD |  | SB No. 1 GF 2021 | 2000000 |  | 2000000 | 1995450.2 |  | 1995450.2 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022165 | Improvement of Talingguroy to Bekyeg Farm to Market Road, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/23/2022 | 08/23/2022 | 11/08/2022 | 11/11/2022 | 53.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999999 |  | 1999999 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
2022064 | Improvement of Drainage Canal Ubbog, Ambiong, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 07/14/2022 | N/A | 07/19/2022 | 07/19/2022 | 07/19/2022 | 07/19/2022 | 08/09/2022 | 08/09/2022 |  | 09/20/2022 | 51.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 496994.73 |  | 496994.73 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 07/14/2022 | 07/14/2022 | 07/14/2022
2022063 | Improvement of Drainage Canal at Central Ambiong, La Trinidad (Near Jim Cris Dagdag Area) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 07/14/2022 | N/A | 07/19/2022 | 07/19/2022 | 07/19/2022 | 07/19/2022 | 08/09/2022 | 08/09/2022 | 09/15/2022 | 09/20/2022 | 44.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 496933.8 |  | 496933.8 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 07/14/2022 | 07/14/2022 | 07/14/2022 |  |  | This amends item no. 63 of APP 2022- 20% PDF to project title and update timeline.
GF 22114 | Improvement of Footpath, Sadag, Bahong, La Trinidad (From Marcos Residence to Pacdal River & Antonio’s Residence) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 |  | 10/20/2022 | 51.00 CD |  | GF CY 2022 |  |  |  | 299684.45 |  | 299684.45 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022 |  |  | This amends item no. 144 of APP 2022-GF to update project title and timeline,
SB1-2022-66 | Construction of Covered Walkway along Swamp Road in Betag, La Trinidad, Benguet (Phase II) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 | 09/15/2022 | 09/15/2022 | 73.18 CD |  | SB #1 - 20% PDF CY 2022 | 500000 |  | 500000 | 499544.88 |  | 499544.88 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022 |  |  | SPPMP No. 11
LDRRMF 21015 | Construction of Drainage Canal to Minimize Landslide at Sitio Ubbog, Ambiong, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/07/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/21/2022 | 85.00 CD |  | LDRRMF-TF CY 2021 | 2000000 |  | 2000000 | 1998000 |  | 1998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
GF 22107 | Road Improvement/Concreting at Block 1,2 & 3, Phase 1, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/14/2022 | 80.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2998000 |  | 2998000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
SB1-2021-10 | Improvement of Legislative Building and Completion of Elevator, Poblacion, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-07-05 | 07/06/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/18/2022 | 350.00 CD |  | SB No. 1 GF 2021 | 6000000 |  | 6000000 | 5999576.16 |  | 5999576.16 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
LDRRMF 21012 | Rehabilitation of Drainage Canal and Fencing of the Wangal Sports Complex, Wangal, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 |  | 10/19/2022 | 117.00 CD |  | LDRRMF-TF CY 2021 | 2000000 |  | 2000000 | 1994875.64 |  | 1994875.64 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022 |  |  | This amends item no. 3 of SAPP9 to update project title and timeline.
2022065 | Improvement of Road with Drainage at Duheb, Bahong, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/18/2022 | N/A | 08/23/2022 | 08/23/2022 | 08/23/2022 | 08/23/2022 | 09/20/2022 | 09/20/2022 |  | 10/17/2022 | 25.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 499800 |  | 499800 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/17/2022 | 08/17/2022 | 08/17/2022
2022081 | Improvement of Eb-eban Outlet of the Dinog Underground Creek, Bahong, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 | 10/28/2022 | 11/02/2022 | 38.00 CD |  | 20% PDF CY 2022 | 500000 |  | 500000 | 499321.68 |  | 499321.68 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022
SB1-2022-43 | Slope Protection at Guadayan, Puguis La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 | 11/29/2022 | 12/01/2022 | 47.00 CD |  | SB No. 1 GF 2022 | 500000 |  | 500000 | 498322.12 |  | 498322.12 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022 |  |  | SPPMP No. 11
SB1-2022-07 | Construction of Concrete Pavement at BAPTC, Betag, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 09/01/2022 | N/A | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/06/2022 | 09/27/2022 | 09/27/2022 |  | 10/20/2022 | 41.00 CD |  | SB No. 1 GF 2022 | 1000000 |  | 1000000 | 995918.09 |  | 995918.09 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/31/2022 | 08/31/2022 | 08/31/2022 |  |  | SPPMP No. 11
Mankayan
GF 22132 | Improvement of Bato-Liwang FMR, Bato, Tabio, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/15/2022 | 03/15/2022 | 05/20/2022 | 05/20/2022 | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999200 |  | 999200 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/04/2022 | 02/04/2022 | 02/04/2022
2022069 | Continuation & Improvement of the Main Canal of the following: Sitios-Sesecan Upper/Lower Labaan-Dalumpinas-Mabilig, Tabio, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/23/2022 | 03/23/2022 | 06/22/2022 | 06/22/2022 | 94.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995179.82 |  | 1995179.82 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
2022173 | Construction of Makilikil Farm to Market Road, Makilikil, Cabiten, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 | 04/27/2022 |  | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998505.07 |  | 998505.07 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/21/2022 | 02/21/2022 | 02/21/2022
GF 22138 | Improvement Along Dimuyog - Pashaan Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/25/2022 | N/A | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/07/2022 | 03/07/2022 | 05/31/2022 | 05/31/2022 | 53.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998729.17 |  | 998729.17 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/24/2022 | 02/24/2022 | 02/24/2022
2022171 | Opening and Improvement of Lamut FMR, Caew, Bulalacao, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 | 06/22/2022 | 06/22/2022 | 117.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3994666.46 |  | 3994666.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
2022172 | Improvement of Akmet Farm to Market Road,Akmet,Bulalacao, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 | 07/26/2022 | 07/26/2022 | 31.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998116.9 |  | 998116.9 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/11/2022 | 03/11/2022 | 03/11/2022
2022167 | Improvement of Nalikob-Agaki Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  | 05/31/2022 | 57.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995141.07 |  | 1995141.07 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/16/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022
2022168 | Improvement of Paykek Farm to Market Road, Paykek & Am-am, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 | 05/30/2022 | 05/31/2022 | 60.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995051.43 |  | 1995051.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 20020 | A) Construction of Barangay Hall for Brgy. Taneg Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 | 06/14/2022 | 06/17/2022 | 140.00CD |  | A) GF CY 2020 | 1000000 |  | 1000000 | 2998548.96 |  | 2998548.96 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 21064 | B) Construction of Barangay Hall (Additional Fund), Taneg, Mankayan | [35 empty] | B) GF CY 2021 | 2000000 |  | 2000000
2022166 | Improvement of Dagadag-Solin Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 84.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995249.37 |  | 1995249.37 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/01/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 22133 | Improvememnt of Daycong - Tam-awan Farm to Market Road, Tam-awan, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 10/10/2022 | 10/10/2022 | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999080.54 |  | 999080.54 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/15/2022 | 03/15/2022 | 03/15/2022
2022169 | Improvement of Ambaokok-Degway Road Pavement, Bedbed, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 | 06/21/2022 | 06/23/2022 | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998862.75 |  | 998862.75 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22140 | Improvement of Tam-awan Balili Barangay Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/24/2022 | 05/24/2022 | 06/22/2022 | 06/22/2022 | 82.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2995304.27 |  | 2995304.27 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
2022178 | Improvement of Central Palasaan Farm To Market Road, Palasaan, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/24/2022 | 05/24/2022 | 06/23/2022 | 06/24/2022 | 63.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998464.8 |  | 1998464.8 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
GF 22134 | Improvement of School Facility (Ground Roofing) at Mankayan Central School, Panad East, Poblacion, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/31/2022 | 05/31/2022 | 07/07/2022 | 07/07/2022 | 36.00 CD |  | GF CY 2022 | 700000 |  | 700000 | 698717.46 |  | 698717.46 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22142 | Construction of Slope Protection at Ayosep Primary School, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 06/21/2022 | 06/22/2022 | 50.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996361.14 |  | 996361.14 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
2022031 | Rehabilitation of Maduto-Pekaw Waterworks, Maduto, Cabiten, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 06/21/2022 | 06/22/2022 | 59.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998827.19 |  | 998827.19 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22001 | Rehabilitation /Repair of Tagumbao Multi-Purpose Building, Sapid, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/28/2022 | 06/30/2022 | 54.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499221.64 |  | 499221.64 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22136 | Canalization and Riprapping along Upper Lamdagan FMR, Paco, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/21/2022 | 06/23/2022 | 56.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999087.99 |  | 999087.99 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
2022177 | Improvement/Concreting Paco Proper Road, Paco, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/17/2022 | 05/17/2022 | 06/21/2022 | 06/23/2022 | 70.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999038.02 |  | 999038.02 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22139 | Improvement of Colong Copcopit FMR, Ca-ew, Bulalacao, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/28/2022 | N/A | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/31/2022 | 05/31/2022 | 07/28/2022 | 08/02/2022 | 34.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 494217.24 |  | 494217.24 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/27/2022 | 04/27/2022 | 04/27/2022
GF 22143 | Improvement of Conacon-Nagawaan FMR, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/28/2022 | N/A | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/31/2022 | 05/31/2022 | 07/07/2022 | 07/07/2022 | 40.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 498170.76 |  | 498170.76 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/27/2022 | 04/27/2022 | 04/27/2022
GF 22141 | Construction of Slope Protection and Road Protection at Palatong Elementary School, Tabio, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/28/2022 | N/A | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/04/2022 | 06/14/2022 | 06/14/2022 | 10/10/2022 | 10/10/2022 | 17.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 498424.16 |  | 498424.16 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/27/2022 | 04/27/2022 | 04/27/2022
GF 22137 | Improvement along Bonie Salingay FMR, Colalo, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/28/2022 | N/A | 05/04/2022 | 05/04/2022 | 05/04/2022 | 05/04/2022 | 06/14/2022 | 06/14/2022 | 09/23/2022 | 09/23/2022 | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997261.73 |  | 997261.73 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/27/2022 | 04/27/2022 | 04/27/2022
GF 22129 | Construction of Slope Protection of Pacda Tabak FMR at Suyoc/ Palasaan, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 07/28/2022 | 07/28/2022 | 30.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499000 |  | 499000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022074 | Improvement of Pacda Tabbak Farm to Market Road (Roadside Riprapping), Pacda, Palasaan, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 07/28/2022 | 07/28/2022 | 51.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999000 |  | 999000 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022032 | Rehabilitation of Takab Proper, Bedbed Domestic Water Source, Tacab, Bedbed, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 07/28/2022 | 07/29/2022 | 21.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 996465.73 |  | 996465.73 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
2022038 | Ground Improvement Cabacab Elementary School, Cabacab, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 07/05/2022 | 07/05/2022 | 09/15/2022 | 09/20/2022 | 83.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998111.49 |  | 1998111.49 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 22135 | Construction of Nursery Drainage Canal, Sapid, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 | 08/18/2022 | 08/18/2022 | 29.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499439.45 |  | 499439.45 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
GF 22131 | Construction of Drainage Canal, Sayapot, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 |  | 10/20/2022 | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998915.75 |  | 998915.75 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
GF 22128 | Completion of Mankayan National High School Dorm, Poblacion, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 07/29/2022 | 07/29/2022 | 08/18/2022 | 08/18/2022 | 133.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1996887.91 |  | 1996887.91 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022174 | Improvement of Ampontoc Farm to Market Road/Construction of Pavement & Canal, Ampontoc, Colalo, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 07/29/2022 | 07/29/2022 | 09/12/2022 | 09/15/2022 | 50.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999383.38 |  | 1999383.38 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
Sablan
SB1-2021-06 | Improvement of Domestic Water Works Tinekey to Lower Poblacion, Sablan | [19 empty] | PLGU-Benguet | No | Negotiated | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/14/2022 | 01/14/2022 | 02/09/2022 | 02/09/2022 | 138.00 CD |  | SB No. 1 -20% PDF CY 2021 | 2000000 |  | 2000000 | 1999958.7 |  | 1999958.7 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 12/02/2021 | 12/02/2021 | 12/02/2021
SB1-2021-110 | Improvement of Road Leading to Municipal Hall at Poblacion, Sablan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 02/28/2022 | 02/28/2022 |  |  | 70.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1979961.44 |  | 1979961.44 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
GF 21108 | Installation of Pipelines, Faucet and other Accessories at Agro-Eco Farm, Bulala, Bayabas, Sablan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  | 03/21/2022 | 54.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 999912.29 |  | 999912.29 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/28/2022 | 01/28/2022 | 01/28/2022
LDRRMF 22-14 | Rehabilitation/Improvement along Monglo-Bayabas Provincial Road | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/22/2022 | 03/22/2022 | 07/21/2022 | 07/21/2022 | 56.00 CD |  | LDRRMF CY 2022 | 2000000 |  | 2000000 | 1998011.93 |  | 1998011.93 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/08/2022 | 02/16/2022 | 02/16/2022 | 02/16/2022
GF 22145 | Construction of Gym, Ampaguey Elementary School, Balluay, Sablan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 119.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2998825.88 |  | 2998825.88 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 21114 | Construction of Gate and Improvement of Pathway Going to Towing Falls, Poblacion, Sablan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 07/29/2022 | 08/01/2022 | 41.00 CD |  | GF CY 2021 | 500000 |  | 500000 | 499725.58 |  | 499725.58 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
GF 22148 | Improvement/Construction of Waterworks System Bayabas - Bulala, Bayabas, Sablan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 08/18/2022 | 08/19/2022 | 35.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999983.04 |  | 999983.04 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22002 | Rehabilitation of Multi-Purpose Building Pavilion Phase II at Benguet Agri-Eco Farm, Bayabas, Sablan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 08/12/2022 | 08/12/2022 | 09/12/2022 | 09/12/2022 | 81.20 CD |  | GF CY 2022 | 1500000 |  | 1500000 | 1499960.94 |  | 1499960.94 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022 |  |  | This amends item no. 2 of APP 2022-GF.
Tuba
21016 | Construction of Rural Health Unit, Phase II, Poblacion, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/04/2022 | 01/04/2022 | 02/28/2022 | 03/07/2022 | 182.00 CD |  | 20% PDF CY 2021 | 4000000 |  | 4000000 | 3999565.27 |  | 3999565.27 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
SB1-2021-100 | Construction of a Storage Building with Comfort Room & Lavatories Phase II at San Pascual, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/14/2022 | 01/14/2022 |  |  | 154.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1998222.57 |  | 1998222.57 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 12/02/2021 | 12/15/2021 | 12/15/2021 | 12/15/2021
SB1-2021-11 | Construction of Police Compac (Sub-Station) at Sitio Poyopoy, Taloy Sur, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 154.00 CD |  | SB NO. 1 (GF 2021) | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
2022180 | Improvement of Liwliw FMR,Camp 4,Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/18/2022 | 02/18/2022 | 06/28/2022 | 06/30/2022 | 38.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997976.56 |  | 997976.56 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 02/08/2022 | 02/08/2022 | 02/08/2022
2022003 | Improvement along Camp 1 Indaoac - Twin Peaks Provincial Road | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/18/2022 | 01/26/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/01/2022 | 03/01/2022 |  | 04/19/2022 | 35.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4994596.33 |  | 4994596.33 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/24/2022 | 02/04/2022 | 02/04/2022 | 02/04/2022
2022011 | Improvement along Poyopoy-Begis Provincial Road, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 | 07/07/2022 | 07/08/2022 | 112.00 CD |  | 20% PDF CY 2022 | 6000000 |  | 6000000 | 5997775.23 |  | 5997775.23 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/07/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022
GF 21084 | A) Construction of Belis Gymnasium, Taloy Norte, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 05/04/2022 | 05/04/2022 | 07/07/2022 | 07/08/2022 | 168.00CD |  | A) GF CY 2021 | 3000000 |  | 3000000 | 5997678.92 |  | 5997678.92 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 02/24/2022 | 03/09/2022 | 03/09/2022 | 03/09/2022
GF 22168 | B) Construction of Covered Court/Gym Phase II - Belis Taloy Norte Elementary School, Taloy Norte, Tuba | [35 empty] | B) GF CY 2022 | 3000000 |  | 3000000
2022183 | Improvement of Balangabang To Keyte Farm To Market Road,Tabaan Norte, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/17/2022 | 05/17/2022 | 06/10/2022 | 06/10/2022 | 34.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2995972.35 |  | 2995972.35 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/11/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022
GF 22157 | Improvement of Lopitac - Laclac - Farm to Market Road, Ansagan, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/15/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 04/05/2022 | 05/17/2022 | 05/17/2022 | 06/22/2022 | 06/22/2022 | 42.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1995000 |  | 1995000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/15/2022 | 03/28/2022 | 03/28/2022 | 03/28/2022
GF 22167 | Completion of Tadiangan IP Building, Tadiangan, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/06/2022 | N/A | 04/12/2022 | 04/12/2022 | 04/12/2022 | 04/12/2022 | 05/17/2022 | 05/17/2022 | 08/11/2022 | 08/15/2022 | 86.27 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997225.62 |  | 997225.62 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/06/2022 | 04/06/2022 | 04/06/2022
GF 22164 | Improvement of Indaoac - Pasiday Farm to Market Road, Tabaan Sur, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 04/22/2022 | N/A | 04/26/2022 | 04/26/2022 | 04/26/2022 | 04/26/2022 | 05/31/2022 | 05/31/2022 | 07/11/2022 | 07/12/2022 | 50.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999061.86 |  | 999061.86 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 04/20/2022 | 04/20/2022 | 04/20/2022
GF 22166 | Improvement of Sipitan Hydro No.2 Barangay Road, Tadiangan, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/16/2022 | 59.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999013.96 |  | 1999013.96 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 22159 | Construction of Waterworks System at Waterfalls (Kalipayon-Nagrealan), Camp One, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/16/2022 | 36.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 498432.66 |  | 498432.66 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
17017 | Construction of Gate and Guard House and Signage,San Pascual | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/16/2022 | 65.00 CD |  | 20% PDF CY 2017 | 1000000 |  | 1000000 | 999121.4 |  | 999121.4 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
GF 22173 | Road Improvement of Bocboc Village, Camp 4, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/05/2022 | 07/05/2022 | 09/05/2022 | 09/08/2022 | 58.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999715.83 |  | 999715.83 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
2022075 | Construction of Retaining Wall with Parapet at Sitio Kaipilan, Camp 3, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/09/2022 | N/A | 06/14/2022 | 06/14/2022 | 06/14/2022 | 06/14/2022 | 07/12/2022 | 07/12/2022 | 09/05/2022 | 09/08/2022 | 42.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999545.16 |  | 999545.16 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/08/2022 | 06/08/2022 | 06/08/2022
GF 22170 | Improvement of Kaipilan to Dalabis Farm to Market Road, Twin Peaks, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 07/29/2022 | 07/29/2022 | 09/05/2022 | 09/08/2022 | 72.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999620.57 |  | 1999620.57 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
GF 22174 | Improvement of Alang to Ligay FMR, Camp 1, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/01/2022 | 06/14/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 06/28/2022 | 07/29/2022 | 07/29/2022 |  | 08/24/2022 | 82.00 CD |  | GF CY 2022 | 2500000 |  | 2500000 | 2487602.76 |  | 2487602.76 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/08/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
2022179 | Improvement along Colocol-Agpay Farm to Market Road, Camp 3,Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 |  | 10/14/2022 | 48.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999920.15 |  | 999920.15 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22165 | Improvement of Drainage Canal System Near the Multipurpose Hall, Taleb, Tabaan Sur, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/29/2022 | N/A | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/05/2022 | 07/29/2022 | 07/29/2022 | 09/12/2022 | 09/15/2022 | 39.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999857.77 |  | 999857.77 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/30/2022 | 06/30/2022 | 06/30/2022
GF 22163 | Improvement and Widening at the Binombong Area along Nabjeng - Toybongan Barangay Road, Tabaan Norte, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 09/23/2022 | 09/28/2022 | 57.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999101.73 |  | 1999101.73 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
GF 22158 | Improvement of Dongon - Ataki Farm to Market Road, Camp 1, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 06/16/2022 | 06/28/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 07/12/2022 | 08/12/2022 | 08/12/2022 | 10/05/2022 | 10/10/2022 | 70.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1994710.61 |  | 1994710.61 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/22/2022 | 07/06/2022 | 07/06/2022 | 07/06/2022
GF 22160 | Improvement of Public Market, Philex Mines, Camp 3, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 | 10/17/2022 | 10/24/2022 | 44.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999589.8 |  | 999589.8 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022
GF 22169 | Improvement of Shontog - Beling Farm to Market Road, Taloy Sur, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/30/2022 | 08/30/2022 |  | 10/17/2022 | 51.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999800 |  | 999800 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022
2022019 | Completion of Multipurpose Gym, Nangalisan, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/21/2022 | 07/29/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 08/12/2022 | 09/20/2022 | 09/20/2022 | 10/24/2022 | 10/25/2022 | 119.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2998356.23 |  | 2998356.23 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/22/2022 | 08/02/2022 | 08/02/2022 | 08/02/2022
2022184 | Improvement of Poyopoy-Paltugan Farm To Market Road, Taloy Sur, Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 | 11/28/2022 | 12/01/2022 | 51.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999800 |  | 999800 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022
Tublay
GF 21102 | Construction of Baayan Multi-Purpose Building, Baayan, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 | 02/04/2022 | 02/16/2022 | 91.00 CD |  | GF 2021 | 2000000 |  | 2000000 | 1998993.23 |  | 1998993.23 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
19019 | Completion of Gym, Ambassador, Tublay, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 02/08/2022 | 02/10/2022 | 104.89 CD |  | 20% PDF CY 2019 | 1500000 |  | 1500000 | 1497765.43 |  | 1497765.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 11/26/2021 | 11/26/2021 | 11/26/2021
21036 | Improvement of Municipal Evacuation Center/ Municipal Gymnasium of Tublay at Caponga, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 77.00 CD |  | 20% PDF 2021 |  |  |  | 2994137.28 |  | 2994137.28 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/07/2022 | 01/24/2022 | 01/24/2022 | 01/24/2022
GF 22184 | Improvement of Tuhok - Bulsi Farm to Market Road, Tuel, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/06/2022 | 05/17/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 05/31/2022 | 06/27/2022 | 06/27/2022 |  | 08/10/2022 | 41.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1998870.85 |  | 1998870.85 | Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 05/11/2022 | 05/23/2022 | 05/23/2022 | 05/23/2022
GF 21042 | Construction of Riprap at the Barangay Health Clinic premises, Basil, Tublay | [19 empty] | PLGU-Benguet | No | SVP | N/A | 06/02/2022 | N/A | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 08/05/2022 | 08/09/2022 | 45.00 CD |  | GF CY 2021 | 800000 |  | 800000 | 798949.11 |  | 798949.11 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 06/02/2022 | 06/02/2022 | 06/02/2022
SB1-2021-102 | Construction of Barangay Health Center, Tublay Central , Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 05/27/2022 | 06/07/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 06/27/2022 | 08/12/2022 | 08/12/2022 | 09/09/2022 | 09/20/2022 | 91.00 CD |  | SB No. 1 GF 2021 | 3000000 |  | 3000000 | 2995331.41 |  | 2995331.41 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 06/02/2022 | 06/22/2022 | 06/22/2022 | 06/22/2022
GF 22178 | Improvement of Gongel - Lower Belong Farm to Market Road, Ambassador, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 07/07/2022 | 07/14/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 07/29/2022 | 09/20/2022 | 09/20/2022 |  | 10/20/2022 | 58.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1997876.53 |  | 1997876.53 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 07/08/2022 | 07/22/2022 | 07/22/2022 | 07/22/2022
GF 22181 | Construction of Asob Waterworks System with Water Pump, Baayan, Tublay | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/03/2022 | N/A | 08/09/2022 | 08/09/2022 | 08/09/2022 | 08/09/2022 | 09/06/2022 | 09/06/2022 |  | 10/20/2022 | 77.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 983682.77 |  | 983682.77 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/02/2022 | 08/02/2022 | 08/02/2022
GF 22180 | Improvement of Ground Barangay Hall, Ambongdolan, Tublay | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 |  | 10/19/2022 | 68.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 977760.94 |  | 977760.94 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022 |  |  | This amends item no. 180 of APP 2022-GF to update project timeline.
GF 22179 | Improvement of Teytey Farm to Market Road, Ambongdolan, Tublay | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/11/2022 | N/A | 08/16/2022 | 08/16/2022 | 08/16/2022 | 08/16/2022 | 09/20/2022 | 09/20/2022 |  | 10/18/2022 | 73.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997178.09 |  | 997178.09 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/11/2022 | 08/11/2022 | 08/11/2022 |  |  | This amends item no. 179 of APP 2022-GF to update project timeline.
SEF 22017 | Demolition of Collapsed Gymnasium at Tublay Central School, Central, Tublay | [19 empty] | PLGU-Benguet | No | SVP | N/A | 08/18/2022 | N/A | 08/23/2022 | 08/23/2022 | 08/23/2022 | 08/23/2022 | 09/20/2022 | 09/20/2022 |  | 10/17/2022 | 34.00 CD |  | SEF CY 2022 | 700000 |  | 700000 | 699600 |  | 699600 | Ms. Marie Geneline G. Banisa , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 08/17/2022 | 08/17/2022 | 08/17/2022 |  |  | This amends item no. 8 of SAPP2 to update project timeline.
[38 empty] | 664840672.84 | 2900000 | 661940672.84 | 672192470.37 | 1999085.73 | 670193384.64
Total Alloted Budget of Procurement Activities | [37 empty] | 664840672.84
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 672192470.37
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | -7351797.53
0N-GOING PROCUREMENT ACTIVITIES
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement