## PMR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | BENGUET PROVINCIAL GOVERNMENT Procurement Monitoring Report as of June 30, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
Atok
SB1-2021-17 | Improvement of KM. 24 to Salidet FMR, Caliking, Atok, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 |  |  | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 498971.9 |  | 498971.9 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
DOH-21-03 | A) Repair and Improvement of Atok District Hospital | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 80.00CD |  | A) T.F HFEP of DOH-CAR | 1350000 |  | 1350000 | 3495205.41 |  | 3495205.41 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
DOH-21-03 | B) Repair and Improvement of Atok District District Hospital | [33 empty] | 187.00CD |  | B) HFEP of DOH-CAR | 2150000 |  | 2150000
2022085 | Construction of Concrete Pavement Along Lolita's Store to Sacla's Residence, Bosleng, Paoay, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  |  | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999170.49 |  | 999170.49 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022083 | Improvement of KM 22 Bilis FMR (Piloy Section), Caliking, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/18/2022 | 02/18/2022 |  |  | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999300 |  | 999300 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022086 | Construction of Concrete Pavement along Paoay Proper Road in Between Ernesto Pocsi's and Anton Boda's Residence, Paoay, Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 |  |  | 38.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999051.87 |  | 999051.87 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/08/2022 | 03/08/2022 | 03/08/2022
GF 22004 | Improvement of Jose Mencio Provincial Road (Beside the Pual Assembly of God Church-Pagc), Atok | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 35.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997017.12 |  | 997017.12 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Bakun
SB1-2021-79 | Ground Development of Kayapa Elementary School, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 02/14/2022 |  | 76.00 CD |  | SB NO.1 CY 2021 GF | 1100000 |  | 1100000 | 1099499.71 |  | 1099499.71 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-58 | Completion of Liwang View Deck, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 56.00 CD |  | SB NO. 1 (GF 2021) | 1100000 |  | 1100000 | 1090094.79 |  | 1090094.79 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22013 | Improvement along Sookan-Gambang FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/18/2022 | 02/18/2022 |  |  | 40.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997555 |  | 997555 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22012 | Improvement of Copcopit FMR Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/18/2022 | 02/18/2022 |  |  | 26.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499500 |  | 499500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
21039 | A) Construction of Mayan Flood Control, Ampusongan, Bakun; | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 118.00CD |  | A) 20% PDF CY 2021 | 1000000 |  | 1000000 | 2496243.34 |  | 2496243.34 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022 | [5 empty] | Clustered with project no. SB1-2021-21 under SB1 GF 2021
SB1-2021-21 | B) Construction of Mayan Flood Control, Ampusongan, Bakun Phase II | [35 empty] | B) SB NO.1 CY 2021 GF | 1500000 |  | 1500000
2022072 | Improvement/Construction of Slope Protection at Sitio Datacan, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/01/2022 | 03/01/2022 |  |  | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997996.66 |  | 997996.66 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22019 | Improvement of Alam-am to Nasayotean FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 |  |  | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998731.42 |  | 998731.42 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22011 | Improvement of FMR at Tuangan to Belig, Bagu, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999300 |  | 999300 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022098 | Improvement of Kayapa-Lingab Farm to Market Road, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/22/2022 | 03/22/2022 |  |  | 72.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999299.94 |  | 1999299.94 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
LDRRMF 22-18 | Rehabilitation of Sipitan-Lup-ot Road (Liwang Section), Dalipey, Bakun, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 48.00 CD |  | LDRRMF CY 2022 | 1500000 |  | 1500000 | 1499499.46 |  | 1499499.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22009 | Construction of Gym/Multi-Purpose Shed Palidan Integrated School, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 |  |  | 119.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999530.31 |  | 2999530.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22010 | Improvement of Nalusbo Paoay-Nalbo Farm to Market Road, Kayapa, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 |  |  | 83.00 CD |  | GF CY 2022 | 5000000 |  | 5000000 | 4999499.51 |  | 4999499.51 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22016 | Improvement of Bolbolo Road,Gambang,Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999499.52 |  | 999499.52 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022095 | Improvement of Liwang Tubaang Farm to Market Road, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 |  |  | 54.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999700 |  | 999700 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/08/2022 | 03/08/2022 | 03/08/2022
2022054 | Construction of Longboy Flood Control (Phase II), Longboy, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  |  | 64.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000.01 |  | 1999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22006 | Completion of Gym Bagu Elementary School, Tanap, Bagu, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/12/2022 | 04/12/2022 |  |  | 140.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2999137.53 |  | 2999137.53 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022096 | Opening of Long-Ayan to Copcopit Farm to Market Road, Dalipey, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 30.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22014 | Opening of Gambang Batanes-Nagawa FMR, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 24.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022093 | Improvement along Ay-ay to Cabutotan (Bec-O Section), Ampusongan, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 64.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1999000.01 |  | 1999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022097 | Improvement of Sookan Sayet Farm to Market Road, Gambang, Bakun | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 56.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998459.48 |  | 1998459.48 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Bokod
A. 20014; B. SB1-2021-95 | Construction of Naubunan to Barangay Daklan Waterworks, Daklan; B. Construction of Naubanan to Daclan Waterworks Phase II Daclan, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 |  |  | 143.00 CD |  | A. 20% PDF CY 2020; B. SB No.1 GF CY 2021 | 4000000 |  | 4000000 | 3997097.52 |  | 3997097.52 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022006 | Improvement along Daclan-Camangaan-Tickey-Bonagan Provincial Road, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  |  | 51.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998674.78 |  | 4998674.78 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022014 | Improvement of Binado-Kiweng and Palansa-Aponan-Acnip Provincial Road, Bokod | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 62.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2998000 |  | 2998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Buguias
SB1-2021-39 | Improvement along Pan-ayaoan - Balaan Farm to Market Road, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 |  |  | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 499574.22 |  | 499574.22 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-76 | Improvement of Beey - Ata FMR, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 72.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1495879.72 |  | 1495879.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-84 | Construction/ Improvement of Pegguena - Magmagaling Domestic Water Works, Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 70.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1497844.3 |  | 1497844.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21079 | Construction of Catlubong Multi-Purpose Building, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 | 01/28/2022 |  | 132.00 CD |  | GF CY 2021 | 4000000 |  | 4000000 | 3994726.53 |  | 3994726.53 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF - 22046 | Improvement of JFMR GNT - Nalam-an - Napugu-an Road, Nalam-an, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  |  | 33.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998135.82 |  | 998135.82 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22045 | Improvement of Impogong - Pasbol Farm-To-Market, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 |  |  | 57.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999236.47 |  | 999236.47 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022109 | Improvement of JFMR-CTS 23-Peggueyna Amgaleyguey Road (Pegguena Section), Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 |  |  | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999775.77 |  | 999775.77 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22049 | Improvement of JFMR BTA - Landingan - Bengbeng - Bauknit Road, Junction, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/15/2022 | N/A | 02/18/2022 | 02/18/2022 | 02/18/2022 | 02/18/2022 | 03/07/2022 | 03/07/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996517.64 |  | 996517.64 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22036 | Improvement of JFMR LP - Lusab - Ammanong Road, Lusab, Catlubong, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  |  | 49.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1996919.12 |  | 1996919.12 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022136 | Improvement of JFMR NT-Natalag-Mabila Road, Sebang | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  |  | 50.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995287.6 |  | 1995287.6 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22029 | Improvement of JFMR LCP-Pugo-Lengat Road, Lengat, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 29.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 499759.43 |  | 499759.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022137 | Improvement of JSNR BTK - Toking - Lingadan - Naliskey - J207 Road, Lingadan, Sebang, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 56.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998899.89 |  | 998899.89 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22048 | Improvement of J204 Katadtada Road at Sitio Km.73, Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 35.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999990.68 |  | 999990.68 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022108 | Improvement of J204-Polis-Akiki-Dilan Road (Polis Section), Amgaleyguey, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 41.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999989.43 |  | 999989.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22040 | Improvement of JFMR - LLPB - Lanas - Pusong Road, Pusong, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/02/2022 | N/A | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/15/2022 | 03/15/2022 |  |  | 48.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996504.5 |  | 996504.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
21112 | Improvement of Junction to Alang FMR, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 53.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1445977.32 |  | 1445977.32 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022133 | Improvement of J207-Wallayan-Naybo-Abbatan-JFMR BLN Road Along Tanggawan Section, Tanggawan, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 |  |  | 45.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 996095.36 |  | 996095.36 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22051 | Improvement of JFMR OCDL - Lamagan - Cudal - Pugo - JFMR BPLS Road, Cudal, Baculongan Norte | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 |  |  | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 995635.39 |  | 995635.39 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022058 | Construction of Dagdag Magubgubang Flood Control, Loo, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  |  | 84.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995652.47 |  | 1995652.47 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22038 | A) Improvement along J204 - Cotcot - Bolinaca - Patugong - Walengweng JFMR BPLS Road (Bannaken Section), Daligdig, Bangao, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 85.00CD |  | A) GF CY 2022 | 1000000 |  | 1000000 | 2994882.59 |  | 2994882.59 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022120 | B) Improvement of J204-Cotcot-Bolinaca-Patugong-Walengweng-JFMR BPLS Road along Baunaken Section, Daligdig, Bangao, Buguias | [35 empty] | B) 20% PDF CY 2022 | 2000000 |  | 2000000
GF 22152 | Improvement of Water Supply System @ Northern Benguet District Hospital | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 23.00 CD |  | GF CY 2022 | 300000 |  | 300000 | 299999 |  | 299999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022122 | Improvement of J204 Bekes-Tagpaya Road (Tagpaya Section), Buyacaoan, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 49.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999152.11 |  | 999152.11 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22031 | Improvement of JSNR BTK - Bot-oan - Tammangan - Panig-An - JFMR OCDL Road, Bayen, Sebeng, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 34.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 997148.46 |  | 997148.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022134 | Improvement of J207-Toking-Alumit Road, Tuking, Poblacion, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999294.3 |  | 999294.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22047 | Improvement of JFMR BLN - Bekes - Palakad - Inuman- JMR WNA Road, Elengan, Poblacion,Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 39.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 996671.09 |  | 996671.09 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22032 | Improvement of JFMR LLPB - Lanas - Taba-ao - Sumilalaw JFMR BPLS Road (Lanas and Togtogyon Section), Lanas, Loo, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022116 | Improvement of JFMR OCDL Lammagan-Cudal Pugo JFMR BPLS Road along Cudal Section, Baculongan Sur, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 05/04/2022 | 05/04/2022 |  |  | 49.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995339.3 |  | 1995339.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022135 | Improvement of JSNR BTK - Bot-Oan - Tammangan - Panig-an - JFMR OCDL Road (Dugoan Section), Sebang, Buguias | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 71.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3993952.87 |  | 3993952.87 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22035 | Improvement of JPR BO - Obanga - Paing - Nacagang - Kebsan - JFMR BPLS Road (Nacagang Section), Nacagang, Baculongan Norte, Buguias | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/04/2022 | 05/04/2022 |  |  | 30.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999 |  | 999999 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Itogon
SB3-2021-06 | Improvement of Laboratory Building at Itogon District Hospital, Tinongdan, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 | 01/12/2022 |  | 34.00 CD |  | SB NO. 3 CY 2021 GF | 522000 |  | 522000 | 521545.24 |  | 521545.24 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21073 | Improvement of Multi-Purpose Building at Cruz, Ampucao, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/16/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 |  |  | 129.00 CD |  | GF CY 2021 | 700000 |  | 700000 | 698000 |  | 698000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB3-2021-08 | Construction of RHU Comfort Room (Back of RHU) Gumatdang, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/06/2022 | N/A | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 |  |  | 112.00 CD |  | SB NO. 3 CY 2021 GF | 1000000 |  | 1000000 | 996517.43 |  | 996517.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 01/04/2022 | 01/04/2022 | 01/04/2022
21018 | Construction of Dalicno Waterworks, Ampucao, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 126.00 CD |  | 20% PDF CY 2021 | 4000000 |  | 4000000 | 3998401.1 |  | 3998401.1 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
GF - 22065 | Improvement of Tocmo Brgy. Road, Loacan, Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  |  | 58.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 994325.5 |  | 994325.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB3-2021-10 | Improvement of Drainage Canal at Bakong, Loacan, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 84.00 CD |  | SB NO. 3 CY 2021 GF | 1500000 |  | 1500000 | 1498410.4 |  | 1498410.4 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
SB1-2021-72 | Construction of Slope Protection near Barangay Hall (Provincial Road), Virac, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 80.00 CD |  | SB NO.1 CY 2021 GF | 1500000 |  | 1500000 | 1497644.31 |  | 1497644.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
21001 | Upgrading of Hospital Water System at Itogon District Hospital | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 65.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1497377.58 |  | 1497377.58 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
SB1-2021-90 | Improvement of Domesic Waterworks GKNWE Ucab, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/16/2022 | 03/16/2022 |  |  | 88.00 CD |  | SB No. 1 GF 2021 | 1100000 |  | 1100000 | 1094590.18 |  | 1094590.18 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-37 | Construction of Open Gym at Tapsan Elementary School, Ampucao, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 |  |  | 238.00 CD |  | SB NO.1 CY 2021 GF | 5500000 |  | 5500000 | 5499762.84 |  | 5499762.84 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22062 | Improvement of FMR at Peday to Orengao, Loakan, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/12/2022 | 04/12/2022 |  |  | 81.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1980500.93 |  | 1980500.93 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022144 | Improvement of Calhorr Road Kias Virac,Itogon | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 50.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 996151.15 |  | 996151.15 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022142 | Opening and Improvement of Road From Simpa to Poblacion, Poblacion, Itogon | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 69.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1997969.88 |  | 1997969.88 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB3-2021-11 | Construction of Satellite Market, Ampucao, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 140.00 CD |  | SB No. 3 GF CY 2021 | 3000000 |  | 3000000 | 2999545.91 |  | 2999545.91 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022004 | Improvement along Kias-Padcal-Philex Provincial Road, Itogon, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 97.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998628.65 |  | 4998628.65 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Kabayan
SB1-2021-65 | Improvement of Cotcot Barangay Road, Poblacion, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/04/2022 | 01/04/2022 |  |  | 77.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1997582.65 |  | 1997582.65 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-87 | Opening and Improvement of Pongol - Binaljan - Abat- FMR, Adaoay, Kabayan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/26/2022 | 01/26/2022 |  |  | 118.00 CD |  | SB NO.1 CY 2021 GF | 2500000 |  | 2500000 | 2496775.44 |  | 2496775.44 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-24 | Improvement of Sokong - Telmud FMR, Eddet, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/04/2022 | 01/04/2022 | 02/10/2022 |  | 34.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 499558.79 |  | 499558.79 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21082 | Improvement of Senior Citizen's Building, Poblacion, Kabayan | [19 empty] | PLGU-Benguet | No | Negotiated | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/26/2022 | 01/26/2022 |  |  | 140.00 CD |  | GF CY 2021 | 1500000 |  | 1500000 | 1498009.16 |  | 1498009.16 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB3-2021-09 | Construction of Drainage Canal along Todjacap - Bekes - Balangabang - Singapayew Access Road Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 75.00 CD |  | SB NO. 3 CY 2021 GF | 1000000 |  | 1000000 | 998000 |  | 998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22077 | Improvement of Patakan, Tinaleb FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/07/2022 | 03/07/2022 |  |  | 40.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998998 |  | 998998 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022149 | Improvement of Lacaan Bito Farm to Market Road, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 37.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999615.26 |  | 999615.26 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022037 | Completion of Child Development Center, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/25/2022 | N/A | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/07/2022 | 03/07/2022 |  |  | 56.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 999327.08 |  | 999327.08 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22080 | Construction of Concrete Canal-Upper Dimapayas Junction FMR, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 |  |  | 40.00 CD |  | GF CY 2022 | 1500000 |  | 1500000 | 1498500 |  | 1498500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022147 | Improvement along Bato-An Farm to Market Road, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 48.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1998000 |  | 1998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022005 | Improvement along National Junction-Diboong-Bangao Provincial Road, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/16/2022 | 02/24/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 59.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4997500 |  | 4997500 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022061 | Improvement/Concreting of Drainage Canal at Bekes Balangabang Farm to Market Road, Duacan, Kabayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 |  |  | 35.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998087.5 |  | 998087.5 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/08/2022 | 03/08/2022 | 03/08/2022
GF 22075 | Improvement of Bumagat-Mongol FMR, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  |  | 63.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22078 | Construction of Concrete Canal at Tabayo, Ballay, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 48.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1993567 |  | 1993567 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022150 | Improvement Along Bumagat Farm to Market Road Batan Proper, Batan, Kabayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 61.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995442.3 |  | 1995442.3 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Kapangan
21035 | Construction of Barangay Multi-Purpose Building, Taba-ao, Kapangan (phase II) | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 |  |  | 148.00 CD |  | 20% PDF CY 2021 | 3000000 |  | 3000000 | 2999481.21 |  | 2999481.21 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21086 | Construction of 2 Units Slab Footbridge and Foot Trail with Hand Railings, Basisil and Paayosan, Pudong, Kapangan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/26/2022 | 01/26/2022 |  |  | 112.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 994091.64 |  | 994091.64 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-96 | Improvement of Balakbak Multi-Purpose Hall, Balakbak, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/23/2022 | 02/23/2022 |  |  | 77.00 CD |  | SB #1 2021 GF | 1500000 |  | 1500000 | 1497334.57 |  | 1497334.57 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
GF 21091 | Improvement of Multi-Purpose Hall & Ground Development, Central, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 123.00 CD |  | GF CY 2021 | 1500000 |  | 1500000 | 1497489.46 |  | 1497489.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
20053 | Improvement of Kapangan Public Market Building Annex C, Lomon, Paykek, Kapangan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 03/01/2022 | 03/01/2022 |  |  | 266.00 CD |  | 20% PDF CY 2020 | 3000000 |  | 3000000 | 2992299.54 |  | 2992299.54 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
LDRRMF 22-11 | Rehabilitation/ Improvement along Lomon-Sagubo Provinical Road, Kapangan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 |  |  | 63.00 CD |  | LDRRMF CY 2022 | 2000000 |  | 2000000 | 1999099.05 |  | 1999099.05 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022008 | Improvement along Lomon-Paykek Provincial Road, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 120.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3997297.97 |  | 3997297.97 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022013 | Improvement along Lomon-Sagubo Provincial Road, Kapangan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 61.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4995151.35 |  | 4995151.35 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Kibungan
SEF 2018-21001 | A) Construction of Multi-Purpose Building for Madaymen National High School in Madaymen, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 | 01/26/2022 |  | 198.98CD |  | A) SEF-SB N0. 1 CY 2018 | 1500000 |  | 1500000 | 2399336.22 |  | 2399336.22 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SEF 2019-21004 | B) Construction of Multi-Purpose Building for Madaymen National High School, Kibungan, Benguet (ADDITIONAL) | [35 empty] | B) SEF-SB N0. 2 CY 2019 | 900000 | 900000
GF 22104 | Improvement of Pakpakitan - Taliboy-oc - Lamut Farm to Market Road,Madaymen,Kibungan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 37.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999999.7 |  | 999999.7 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022012 | Improvement along Halsema-Madaymen Provincial Road, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/22/2022 | 03/22/2022 |  |  | 130.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4998000 |  | 4998000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022160 | Opening of Beyeng to Almasi Farm to Market Road, Palina, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 |  |  | 117.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4999000.01 |  | 4999000.01 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022159 | Improvement of Riverside-Tagpaya-Kuadsil Access Road, Madaymen, Kibungan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 04/12/2022 | 04/12/2022 |  |  | 71.00 CD |  | 20% PDF CY 2022 | 3000000 |  | 3000000 | 2999000 |  | 2999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
La Trinidad
2021-25 | Improvement of Various Road (Cawa and Motorpool - Extension) at Wangal, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 |  |  | 166.00 CD |  | SB NO. 3 CY 2019 GF | 3000000 |  | 3000000 | 2996803.83 |  | 2996803.83 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-16 | Construction of Farm to Market Footbridge & Footpath at Dinubangan, Beckel, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 12/15/2021 | N/A | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/04/2022 | 01/04/2022 |  |  | 70.00 CD |  | SB NO.1 CY 2021 GF | 500000 |  | 500000 | 498662.76 |  | 498662.76 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-77 | Road Opening and Improvement of Bineng to Kawa Farm to Market Road, Bineng, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/14/2022 | 01/14/2022 |  |  | 72.00 CD |  | SB NO.1 CY 2021 GF | 1100000 |  | 1100000 | 1097000 |  | 1097000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB3-2021-05 | Construction of Benguet Provincial Jail Kitchen with Dining Hall (Additional Amount) | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/06/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 |  |  | 47.00 CD |  | SB NO. 3 CY 2021 GF | 300000 |  | 300000 | 299663.39 |  | 299663.39 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022 | 01/04/2022 | 01/04/2022 | 01/04/2022
20106 | Road Opening/ Improvement of Pagal - Talingting - Danas Farm to Market Road, Shilan, La Trinidad, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 139.00 CD |  | 20% PDF CY 2020 | 3000000 |  | 3000000 | 2998525.09 |  | 2998525.09 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
LGSF-21-04-04 | Rehabilitation along Alapang - Alno - Tuel Provincial Road, Alapang, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 1970-01-01 | 01/18/2022 | 01/26/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/23/2022 | 03/23/2022 |  |  | 224.00 CD |  | LGSF-DRRAP FY 2021- TRUST FUND | 10000000 |  | 10000000 | 9859648.19 |  | 9859648.19 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | [6 empty] | REBID- FAILED (Aug. 24, 2021)
GF 21032 | Improvement of Road at Windy Hill (Cenon Garcia Area), Poblacion, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 03/07/2022 | 03/07/2022 |  |  | 40.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 999399.72 |  | 999399.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
21054 | Improvement of Drainage Canal, Siadto Malinias Luspian Cores Area, Poblacion, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  |  | 65.00 CD |  | 20% PDF CY 2021 | 1500000 |  | 1500000 | 1499999.72 |  | 1499999.72 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022009 | Improvement along Alno-Tuel-Balway Provincial Road, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/15/2022 | 03/15/2022 |  |  | 118.00 CD |  | 20% PDF CY 2022 | 8000000 |  | 8000000 | 7987830.92 |  | 7987830.92 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022062 | Construction of Drainage Canal at Akes to Benguet National HS Annex, Alno, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/02/2022 | N/A | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/07/2022 | 03/15/2022 | 03/15/2022 |  |  | 60.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998977.02 |  | 998977.02 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22120 | Improvement of Balucas Community Road, Shilan, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/04/2022 | N/A | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 |  |  | 42.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998933.49 |  | 998933.49 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22127 | Improvement of Puguis - Buyagan - Poblacion PR Junction (Rotonda) - LTO - Motorpool, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-02-18 | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 49.00 CD |  | GF CY 2022 | 10000000 |  | 10000000 | 9990430.31 |  | 9990430.31 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22126 | Improvement of Alapang - Alno - Tuel Provincial Road, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | 2022-02-18 | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 120.00 CD |  | GF CY 2022 | 10000000 |  | 10000000 | 9997717.4 |  | 9997717.4 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22111 | Completion of the Perimeter Fence at La Trinidad National High School, Lubas, La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 37.00 CD |  | GF CY 2022 | 500000 |  | 500000 | 496846.55 |  | 496846.55 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22112 | Completion of Barangay Hall Extension of Barangay Balili,La Trinidad | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 47.00 CD |  | GF CY 2022 | 700000 |  | 700000 | 698509.14 |  | 698509.14 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22124 | Improvement/ Construction of Flood Control at Dong-oy River, Bahong, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 84.00 CD |  | GF CY 2022 | 2000000 |  | 2000000 | 1998805.16 |  | 1998805.16 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22116 | Improvement along Motorpool-Wangal Extension Barangay Road, Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 63.00 CD |  | GF CY 2022 | 2600000 |  | 2600000 | 2594808.71 |  | 2594808.71 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21115 | Ground Improvement of Trade Fair Area at Wangal, La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 05/04/2022 | 05/04/2022 |  |  | 84.00 CD |  | GF 2021 | 5000000 |  | 5000000 | 4994310.03 |  | 4994310.03 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22117 | Construction of School Building at Puguis National High School, Longlong, Puguis,La Trinidad | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/08/2022 | 03/16/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 05/04/2022 | 05/04/2022 |  |  | 268.00 CD |  | GF CY 2022 | 6000000 |  | 6000000 | 5991252.43 |  | 5991252.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 03/08/2022
Mankayan
GF 22132 | Improvement of Bato-Liwang FMR, Bato, Tabio, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/03/2022 | N/A | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/15/2022 | 03/15/2022 |  |  | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999200 |  | 999200 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022069 | Continuation & Improvement of the Main Canal of the following: Sitios-Sesecan Upper/Lower Labaan-Dalumpinas-Mabilig, Tabio, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/23/2022 | 03/23/2022 |  |  | 94.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995179.82 |  | 1995179.82 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022173 | Construction of Makilikil Farm to Market Road, Makilikil, Cabiten, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/19/2022 | N/A | 02/24/2022 | 02/24/2022 | 02/24/2022 | 02/24/2022 | 03/07/2022 | 03/07/2022 |  |  | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998505.07 |  | 998505.07 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22138 | Improvement Along Dimuyog - Pashaan Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/25/2022 | N/A | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/07/2022 | 03/07/2022 |  |  | 53.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 998729.17 |  | 998729.17 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022171 | Opening and Improvement of Lamut FMR, Caew, Bulalacao, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/23/2022 | 03/23/2022 |  |  | 117.00 CD |  | 20% PDF CY 2022 | 4000000 |  | 4000000 | 3994666.46 |  | 3994666.46 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022172 | Improvement of Akmet Farm to Market Road,Akmet,Bulalacao, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/12/2022 | N/A | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/16/2022 | 03/23/2022 | 03/23/2022 |  |  | 31.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998116.9 |  | 998116.9 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang |  | 03/08/2022 | 03/08/2022 | 03/08/2022
2022167 | Improvement of Nalikob-Agaki Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/15/2022 | 02/23/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 03/08/2022 | 04/26/2022 | 04/26/2022 |  |  | 57.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995141.07 |  | 1995141.07 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022168 | Improvement of Paykek Farm to Market Road, Paykek & Am-am, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 60.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995051.43 |  | 1995051.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 20020 | A) Construction of Barangay Hall for Brgy. Taneg Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/17/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/26/2022 | 04/26/2022 |  |  | 140.00CD |  | A) GF CY 2020 | 1000000 |  | 1000000 | 2998548.96 |  | 2998548.96 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21064 | B) Construction of Barangay Hall (Additional Fund), Taneg, Mankayan | [35 empty] | B) GF CY 2021 | 2000000 |  | 2000000
2022166 | Improvement of Dagadag-Solin Farm to Market Road, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/27/2022 | 03/07/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 84.00 CD |  | 20% PDF CY 2022 | 2000000 |  | 2000000 | 1995249.37 |  | 1995249.37 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22133 | Improvememnt of Daycong - Tam-awan Farm to Market Road, Tam-awan, Balili, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/17/2022 | N/A | 03/23/2022 | 03/23/2022 | 03/23/2022 | 03/23/2022 | 04/05/2022 | 04/05/2022 |  |  | 36.00 CD |  | GF CY 2022 | 1000000 |  | 1000000 | 999080.54 |  | 999080.54 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022169 | Improvement of Ambaokok-Degway Road Pavement, Bedbed, Mankayan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 03/24/2022 | N/A | 03/29/2022 | 03/29/2022 | 03/29/2022 | 03/29/2022 | 04/19/2022 | 04/19/2022 |  |  | 30.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 998862.75 |  | 998862.75 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Sablan
SB1-2021-06 | Improvement of Domestic Water Works Tinekey to Lower Poblacion, Sablan | [19 empty] | PLGU-Benguet | No | Negotiated | N/A | 12/03/2021 | N/A | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 01/14/2022 | 01/14/2022 |  |  | 138.00 CD |  | SB No. 1 -20% PDF CY 2021 | 2000000 |  | 2000000 | 1999958.7 |  | 1999958.7 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-110 | Improvement of Road Leading to Municipal Hall at Poblacion, Sablan, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 02/28/2022 | 02/28/2022 |  |  | 70.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1979961.44 |  | 1979961.44 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21108 | Installation of Pipelines, Faucet and other Accessories at Agro-Eco Farm, Bulala, Bayabas, Sablan | [19 empty] | PLGU-Benguet | No | SVP | N/A | 01/26/2022 | N/A | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/02/2022 | 02/18/2022 | 02/18/2022 |  |  | 54.00 CD |  | GF CY 2021 | 1000000 |  | 1000000 | 999912.29 |  | 999912.29 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
LDRRMF 22-14 | Rehabilitation/Improvement along Monglo-Bayabas Provincial Road | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/03/2022 | 02/11/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 02/23/2022 | 03/22/2022 | 03/22/2022 |  |  | 56.00 CD |  | LDRRMF CY 2022 | 2000000 |  | 2000000 | 1998011.93 |  | 1998011.93 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22145 | Construction of Gym, Ampaguey Elementary School, Balluay, Sablan | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 04/12/2022 | 04/12/2022 |  |  | 119.00 CD |  | GF CY 2022 | 3000000 |  | 3000000 | 2998825.88 |  | 2998825.88 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
Tuba
21016 | Construction of Rural Health Unit, Phase II, Poblacion, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/04/2022 | 01/04/2022 |  |  | 182.00 CD |  | 20% PDF CY 2021 | 4000000 |  | 4000000 | 3999565.27 |  | 3999565.27 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-100 | Construction of a Storage Building with Comfort Room & Lavatories Phase II at San Pascual, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/30/2021 | 12/09/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 12/21/2021 | 01/14/2022 | 01/14/2022 |  |  | 154.00 CD |  | SB NO.1 CY 2021 GF | 2000000 |  | 2000000 | 1998222.57 |  | 1998222.57 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
SB1-2021-11 | Construction of Police Compac (Sub-Station) at Sitio Poyopoy, Taloy Sur, Tuba, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 154.00 CD |  | SB NO. 1 (GF 2021) | 2000000 |  | 2000000 | 1999000 |  | 1999000 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
2022180 | Improvement of Liwliw FMR,Camp 4,Tuba | [19 empty] | PLGU-Benguet | No | SVP | N/A | 02/08/2022 | N/A | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/11/2022 | 02/18/2022 | 02/18/2022 |  |  | 38.00 CD |  | 20% PDF CY 2022 | 1000000 |  | 1000000 | 997976.56 |  | 997976.56 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022003 | Improvement along Camp 1 Indaoac - Twin Peaks Provincial Road | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/18/2022 | 01/26/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 02/08/2022 | 03/01/2022 | 03/01/2022 |  |  | 35.00 CD |  | 20% PDF CY 2022 | 5000000 |  | 5000000 | 4994596.33 |  | 4994596.33 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
2022011 | Improvement along Poyopoy-Begis Provincial Road, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 03/02/2022 | 03/10/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 03/22/2022 | 04/26/2022 | 04/26/2022 |  |  | 112.00 CD |  | 20% PDF CY 2022 | 6000000 |  | 6000000 | 5997775.23 |  | 5997775.23 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 21084 | A) Construction of Belis Gymnasium, Taloy Norte, Tuba | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 02/19/2022 | 03/01/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 03/15/2022 | 05/04/2022 | 05/04/2022 |  |  | 168.00CD |  | A) GF CY 2021 | 3000000 |  | 3000000 | 5997678.92 |  | 5997678.92 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
GF 22168 | B) Construction of Covered Court/Gym Phase II - Belis Taloy Norte Elementary School, Taloy Norte, Tuba | [35 empty] | B) GF CY 2022 | 3000000 |  | 3000000
Tublay | [34 empty] | 168.00CD
GF 21102 | Construction of Baayan Multi-Purpose Building, Baayan, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 10/27/2021 | 11/05/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 01/04/2022 | 01/04/2022 |  |  | 91.00 CD |  | GF 2021 | 2000000 |  | 2000000 | 1998993.23 |  | 1998993.23 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
19019 | Completion of Gym, Ambassador, Tublay, Benguet | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 11/11/2021 | 11/19/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 01/14/2022 | 01/14/2022 |  |  | 104.89 CD |  | 20% PDF CY 2019 | 1500000 |  | 1500000 | 1497765.43 |  | 1497765.43 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang
21036 | Improvement of Municipal Evacuation Center/ Municipal Gymnasium of Tublay at Caponga, Tublay | [19 empty] | PLGU-Benguet | No | Public Bidding | N/A | 01/06/2022 | 01/14/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 01/26/2022 | 02/18/2022 | 02/18/2022 |  |  | 77.00 CD |  | 20% PDF CY 2021 | 3000000 |  | 3000000 | 2994137.28 |  | 2994137.28 | PICPA Representative , Ms. Marcelita D. Cawilan , Engr. Benedict Pineda , Mr. Miguel P. Luma-ang | 01/04/2022
[38 empty] | 321922000 | 900000 | 321022000 | 321352626.62 | 0 | 321352626.62
Total Alloted Budget of Procurement Activities | [37 empty] | 321922000
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 321352626.62
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 569373.38
0N-GOING PROCUREMENT ACTIVITIES
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement